## BLT
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Bridges, Landslips and Traffic Management (BLT-PIU)
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
701 - Infrastructure Development Fund
Bridges Reconstruction Programme
1 | CP40 B1/1 EMR South Quay | Bridge reconstruction | 72141107 | 2023-12-01 | Apr 2024/Jan 2025 | 10mths | Open Bidding | 10 working days | Fixed Price
2 | CP44 B1/43 Paria Main Rd Toco (Shark River) | Bridge reconstruction | 72141107 | 2023-12-01 | Jun 2024/Nov 2026 | 18mths | Open Bidding | 10 working days | Fixed Price
3 | Phase 3B - Designs | Procurement of 2 Consultants for the Design Services and Construction Supervision for 12 Bridges | 81100000 | 2023-11-01 | Mar 2024/Oct 2024 | 8mths | Open Bidding | 10 working days | Fixed Price
Landslip Repairs Programme
1 | L02 - North Coast Road 7.7km | Landslip rehabilitation | 77111603 | 2024-02-01 | Sep 2024/Jun 2025 | 10mths | Open Bidding | 10 working days | Fixed Price
2 | L05 - Paria Morne Bleu Rd (5.6km) | Landslip rehabilitation | 77111603 | 2023-12-01 | Jun 2024/Mar 2025 | 10mths | Open Bidding | 10 working days | Fixed Price
3 | L06 -Paria Main Rd (69.3km) | Landslip rehabilitation | 77111603 | 2023-12-01 | Jun 2024/Mar 2025 | 10mths | Open Bidding | 10 working days | Fixed Price
4 | L10- Bonair Road (Lp 177-178) | Landslip rehabilitation | 77111603 | 2023-12-01 | Jun 2024/Mar 2025 | 10mths | Open Bidding | 10 working days | Fixed Price
5 | L12 - Cumoto Road (Lp 301-303) | Landslip rehabilitation | 77111603 | 2023-12-01 | Jun 2024/Mar 2025 | 10mths | Open Bidding | 10 working days | Fixed Price
6 | L15- Sisters Road 5.50km | Landslip rehabilitation | 77111603 | 2023-12-01 | Jun 2024/Jan 2025 | 8mths | Open Bidding | 10 working days | Fixed Price
7 | L16-Sisters Road 5.1km | Landslip rehabilitation | 77111603 | 2023-12-01 | Jun 2024/Jan 2025 | 8mths | Open Bidding | 10 working days | Fixed Price
8 | L 34 - Moreau Rd #1(LP226), Marac | Landslip rehabilitation | 77111603 | 2023-12-01 | Jun 2024/Mar 2025 | 10mths | Open Bidding | 10 working days | Fixed Price
9 | Phase 2B - Designs | Procurement of 3 Consultants for the Design Sevices and Construction Supervision for 35 Landslips | 81100000 | 2024-03-01 | Sep 2024/Aug 2025 | 12mths | Open Bidding | 10 working days | Fixed Price
Traffic Management Programme
1 | CP#13 - Supply and Installation: AASHTO W-Type Metal Beam Guard Rail: CRH (The Crossings, Arima to Antigua Road, St. George East) | Installation of traffic management and safety systems | 46161500 | 2023-12-01 | Jun 2024/Aug 2024 | 3mths | Open Bidding | 10 working days | Fixed Price
2 | CP#17 - Churchill Roosevelt Highway North Bound And South Bound (St George East District From Prisons Ground Road 20.217km to Demerara Road 29.753km | Installation of traffic management and safety systems | 46161500 | 2023-12-01 | Jun 2024/Sep 2024 | 4mths | Open Bidding | 10 working days | Fixed Price
3 | CP#18 - Uriah Butler Highway Northbound and Southbound (Caroni District) From Guayamare River 8.033km to Chaguanas Overpass 15.376km | Installation of traffic management and safety systems | 46161500 | 2023-12-01 | Jun 2024/Sep 2024 | 4mths | Open Bidding | 10 working days | Fixed Price
DP
1 | File No. 9/2/11 | Supply of Telephone Services for the BLT PIU Telephone charges ftp: 15 Sep 2023 - 15 Aug 2024 - (Payment of bills) | 83111501 | N/A | N/A | N/A | Sole Select | Not applicable | Not applicable
2 | Information Technology Dep't | Renewal of Design Software Licenses | 43230000 | 2023-11-01 | 2023-12-01 | 1 mth | Sole Select | Not applicable | Fixed Price
3 | Information Technology Dep't | Purchase of Printers, computers and other office equipment | 44120000 | 2023-11-01 | 2024-01-01 | 3 mths | Open Bidding | 10 working days | Fixed Price
4 | File No. 9/2/11 | Purchase of local stamps | 44121500 | 2023-11-01 | 2023-11-01 | 1mth | Request for Quotation | Not applicable | Fixed Price
5 | File No. 9/2/11 | Purchase of 2 vehicles | 25100000 | 2023-11-01 | 2024-01-01 | 3 mths | Open Bidding | 10 working days | Fixed Price
6 | File No. 9/2/11 | Supply of office supplies | 44120000 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
7 | File No. 9/2/11 | Supply of stationery | 14111509 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
8 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Toyota Prado | 78181500 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
9 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Nissan Pathfinder | 78181500 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
10 | File No. 9/2/11 | Repairs and maintenance of office equipment | 81112306 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
11 | File No. 9/2/11 | Publication of Advertisements and Notices | 55101500 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
12 | File No. 9/2/11 | Services required for hosting Community Engagement Sensitization Sessions | 80141902 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
13 | File No. 9/2/11 | Supply safety equipment for the BLT PIU staff | 46180000 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
14 | File No. 9/2/11 | Training for Staff Members | 86100000 | 2024-01-01 | 2024-01-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
15 | Information Technology Dep't | Supply of Various Software Licenses | 43231500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
16 | File No. 9/2/11 | Repairs and Maintenance to office space | 72101500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
17 | File No. 9/2/11 | Provision of Employee Assistance Programme / Counselling / Mentoring Workshops | 86100000 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
18 | File No. 9/2/11 | Supply of office supplies | 44120000 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
19 | File No. 9/2/11 | Supply of stationery | 14111509 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
20 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Toyota Prado | 78181500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
21 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Nissan Pathfinder | 78181500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
22 | File No. 9/2/11 | Repairs and maintenance of office equipment | 81112306 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
23 | File No. 9/2/11 | Publication of Advertisements and Notices | 55101500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
24 | File No. 9/2/11 | Services required for hosting Community Engagement Sensitization Sessions | 55101500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
25 | File No. 9/2/11 | Training for Staff Members | 86100000 | 2024-05-01 | 2024-05-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
26 | File No. 9/2/11 | Supply of office supplies | 44120000 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
27 | File No. 9/2/11 | Supply of stationery | 14111509 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
28 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Toyota Prado | 78181500 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
29 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Nissan Pathfinder | 78181500 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
30 | File No. 9/2/11 | Repairs and maintenance of office equipment | 81112306 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
31 | File No. 9/2/11 | Publication of Advertisements and Notices | 55101500 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
32 | File No. 9/2/11 | Services required for hosting Community Engagement Sensitization Sessions | 80141902 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
33 | File No. 9/2/11 | Training for Staff Members | 86100000 | 2024-08-01 | 2024-08-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
34 | File No. 9/2/11 | Supply of office supplies | 44120000 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
35 | File No. 9/2/11 | Supply of stationery | 14111509 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
36 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Toyota Prado | 78181500 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
37 | File No. 9/2/11 | Vehicle Repairs and Service - 1 Nissan Pathfinder | 78181500 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
38 | File No. 9/2/11 | Repairs and maintenance of office equipment | 81112306 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
39 | File No. 9/2/11 | Publication of Advertisements and Notices | 55101500 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
40 | File No. 9/2/11 | Services required for hosting Community Engagement Sensitization Sessions | 80141902 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price

## Coastal Protection
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Coastal Protection Unit
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | File No. 25/3/17 Sub II | Supply of Telephone Services for the CoPU Telephone charges ftp: 15 Sep 2023 - 15 Aug 2024 - (Payment of bills) | 83111501 | N/A | N/A | N/A | Sole Selct | Not applicable | Not applicable
2 | Information Technology Dep't | Renewal of Design Software Licenses | 81112500 | 2023-11-01 | 2023-12-01 | 1 mth | Limited Bidding | 10 working days | Fixed Price
3 | Information Technology Dep't | Purchase of Printers, computers and other office equipment | 44120000 | 2023-11-01 | 2024-01-01 | 3 mths | Limited Bidding | 10 working days | Fixed Price
4 | File No. 25/3/17 Sub II | Purchase of local stamps | 44121500 | 2023-11-01 | 2023-11-01 | 1mth | Request for Quotation | Not applicable | Fixed Price
5 | File No. 25/3/17 Sub II | Purchase of office chairs, filing cabinets and other office furniture | 56101720 | 2023-11-01 | 2024-01-01 | 3 mths | Request for Quotation | Not applicable | Fixed Price
6 | File No. 25/3/17 Sub II | Application for Certificate of Enviromental Clearance | 77111500 | 2023-11-01 | 2023-11-01 | 1mth | Limited Bidding | 10 working days | Fixed Price
7 | File No. 25/3/17 Sub II | Supply of office supplies | 44120000 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
8 | File No. 25/3/17 Sub II | Supply of stationery | 14111509 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
9 | File No. 25/3/17 Sub II | Vehicle Repairs and Service | 78181500 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
10 | File No. 25/3/17 Sub II | Repairs and maintenance of office equipment | 81112306 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
11 | File No. 25/3/17 Sub II | Publication of Advertisements and Notices | 55101500 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
12 | File No. 25/3/17 Sub II | Services required for hosting Community Engagement Sensitization Sessions, interviews and meetings | 80141902 | 2023-12-01 | 2023-12-01 | 1 mth | Open Bidding | 10 working days | Fixed Price
13 | File No. 25/3/17 Sub II | Supply safety equipment and tools | 46180000 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
14 | File No. 25/3/17 Sub II | Airline, Ferry Tickets and Accomodation for Employees | 90111900 | 2023-12-01 | 2023-12-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
15 | File No. 9/2/11 | Training for Staff Members | 86100000 | 2024-01-01 | 2024-01-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
16 | Information Technology Dep't | Supply of Various Software Licenses | 43231500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
17 | File No. 9/2/11 | Repairs and Maintenance to office space | 72101500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
18 | File No. 9/2/11 | Provision of Employee Assistance Programme / Counselling / Mentoring Workshops | 86100000 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
19 | File No. 25/3/17 Sub II | Supply of office supplies | 44120000 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
20 | File No. 25/3/17 Sub II | Supply of stationery | 14111509 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
21 | File No. 25/3/17 Sub II | Vehicle Repairs and Service | 81112306 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
22 | File No. 25/3/17 Sub II | Repairs and maintenance of office equipment | 81112306 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
23 | File No. 25/3/17 Sub II | Publication of Advertisements and Notices | 55101500 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
24 | File No. 25/3/17 Sub II | Services required for hosting Community Engagement Sensitization Sessions, interviews and meetings | 80141902 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
25 | File No. 25/3/17 Sub II | Airline, Ferry Tickets and Accomodation for Employees | 90111900 | 2024-03-01 | 2024-03-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
26 | File No. 9/2/11 | Training for Staff Members | 86100000 | 2024-05-01 | 2024-05-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
27 | File No. 25/3/17 Sub II | Supply of office supplies | 44120000 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
28 | File No. 25/3/17 Sub II | Supply of stationery | 14111509 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
29 | File No. 25/3/17 Sub II | Vehicle Repairs and Service | 81112306 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
30 | File No. 25/3/17 Sub II | Repairs and maintenance of office equipment | 81112306 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
31 | File No. 25/3/17 Sub II | Publication of Advertisements and Notices | 55101500 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
32 | File No. 25/3/17 Sub II | Services required for hosting Community Engagement Sensitization Sessions, interviews and meetings | 80141902 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
33 | File No. 25/3/17 Sub II | Airline, Ferry Tickets and Accomodation for Employees | 90111900 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
34 | File No. 9/2/11 | Training for Staff Members | 86100000 | 2024-08-01 | 2024-08-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
35 | File No. 25/3/17 Sub II | Supply of office supplies | 44120000 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
36 | File No. 25/3/17 Sub II | Supply of stationery | 14111509 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
37 | File No. 25/3/17 Sub II | Vehicle Repairs and Service | 81112306 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
38 | File No. 25/3/17 Sub II | Repairs and maintenance of office equipment | 81112306 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
39 | File No. 25/3/17 Sub II | Publication of Advertisements and Notices | 55101500 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
40 | File No. 25/3/17 Sub II | Services required for hosting Community Engagement Sensitization Sessions, interviews and meetings | 80141902 | 2024-09-01 | 2024-09-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
41 | File No. 25/3/17 Sub II | Airline, Ferry Tickets and Accomodation for Employees | 90111900 | 2024-06-01 | 2024-06-01 | 1 mth | Request for Quotation | Not applicable | Fixed Price
701 - Infrastructure Development Fund
1 | 701/43/003/11/P/021 | Rehabilitation of the exisitng seawall at Lady Hailes Avenue, San Fernando | 72141200 | 2024-04-01 | Sep 2024/Feb 2026 | 18mths | Open Bidding | 10 working days | Fixed Price
2 | 701/43/003/11/P/027 | Granville Shoreline Stabilization Works | 72141200 | 2023-12-01 | Jun 2024/May 2026 | 10mths | Open Bidding | 10 working days | Fixed Price
3 | 701/43/003/11/P/030 | Paria Main Road Coastal Protection - Design Services and Construction | 81102100 | 2023-12-01 | Apr 2024/Mar 2025 | 12mths | Open Bidding | 10 working days | Fixed Price
4 | 701/43/003/11/P/032 | Manzanilla Beach Facility Improvement Works | 72141200 | 2023-12-01 | Apr 2024/Sep 2025 | 18mths | Open Bidding | 10 working days | Fixed Price
5 | 701/43/003/11/P/034 | Salybia Shoreline Management Project | 81102101 | 2023-12-01 | Apr 2024/Mar 2025 | 12mths | Open Bidding | 10 working days | Fixed Price
6 | 701/43/003/11/P/035 | Cumana Fishing Facility Coastal Improvement Works | 72141200 | 2023-12-01 | Apr 2024/Mar 2025 | 12mths | Open Bidding | 10 working days | Fixed Price
7 | 701/43/003/11/P/036 | Mayaro/Guayaguayare Coastal Management Programme (West Guayaguayare) | 81102101 | 2023-12-01 | Apr 2024/Sep 2025 | 18mths | Open Bidding | 10 working days | Fixed Price
8 | 701/43/003/11/P/NEW | Coastal Protection Design Consultancy Works for the South Beach at the Magdalena Beach and Golf Resort | 81102100 | 2023-12-01 | Apr 2024/Mar 2025 | 12mths | Limited Bidding | 10 working days | Fixed Price

## CPU (hidden)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
Central Planning Unit (CPU)
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## Central Planning Unit CPU
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Central Planning Unit (CPU)
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 02/004/03 | Uniforms | V Guard hats
safety glasses
high visibility vest
high visibility vest
face mask
gloves
safety boots
|  |  | umbrellas | 53102700 | 2023-10-01 | 2024-09-30 | Annually | Request for Quotations | Not applicable | Quotations
2 | 02/004/10 | Office Stationery & Supplies | Paper - (8 1/2 x 11), ( 8 1/2 x 14),
(11 x 17)
Envelopes
toner & waste toner- photocopiers
Ink for HP printers
flash drives
post-it, tag it,
|  |  | glue, markers, pens, staplers | 44120000 | 2023-10-01 | 2024-12-31 | Quarterly | Request for Quotations | Not applicable | Quotations
3 | 02/004/11 | Books & Periodicals | Materials of Flood &Coastal Erosion
Risk Management
Risk & Crisis Mgmt in Public Sector
Ethics in Management
|  |  | Project Management | 60102300 | 2023-10-01 | 2024-09-30 | Annually | Request for Quotations | Not applicable | Quotations
4 | 02/004/15 | Repairs & Maintenance | Servicing of (2) coloured photocopiers
|  | (Equipment) | with printers, fax and scanner options
replacement of parts
servicing of shredder
|  |  | fax machine | 81112306 | 2023-10-01 | 2024-12-31 | Quarterly | Request for Quotations | Not applicable | Quotations
5 | 02/004/17 | Training | Courses for Technical Officers & Admin | 86100000
staff: Project Management Concepts and
Applications
Presentations using power point
Human Resource Management for
non-HR professionals,
|  |  | Customer Service Excellence | 86100000 | 2023-10-01 | 2024-09-30 | Annually | Request for Quotations | Not applicable | Quotations
6 | 02/004/57 | Postage | local & Foreign stamps | 44121500 | 2023-10-01 | 2024-09-30 | Annually | Request for Quotations | Not applicable | Quotations
7 | 02/004/66 | Hosting of Conferences, | hosting meetings | 80141902
|  | seminars & Other | catering food & drinks,
stationery for meetings
|  |  | transportation |  | 2023-10-01 | 2024-12-31 | Quarterly | Request for Quotations | Not applicable | Quotations
8 | 03/004/02 | Office Equipment | Purchase of Laptops | 44000000
|  |  | External Hard Drives | 44000000
|  |  | fans, portable A/C Units | 44000000 | 2023-10-01 | 2024-09-30 | Annually | Request for Quotations | Not applicable | Quotations
9 | 03/004/03 | Furniture & Furnishings | Purchase of chairs, office partitioning, tables, cabinets | 56000000 | 2023-10-01 | 2024-09-30 | Annually | Request for Quotations | Not applicable | Quotations
10 | 03/004/04 | Other Minor Equipment | Binding machine, heavy duty staplers, | 44000000
|  |  | digital voice recorders with batteries | 44100000 | 2023-10-01 | 2024-09-30 | Annually | Request for Quotations | Not applicable | Quotations

## Construction
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Construction
No. | Project Number | Brief Description |  | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
Recurrent Expenditure
1 | 02/008/10 | Acqusition of Office Stationery |  | 14111509 | 2023-11-01 | 2024-01-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
2 | 02/008/10 | Acqusition of Cleaning Supplies |  | 47000000 | 2023-12-01 | 2024-02-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
3 | 02/008/10 | Acqusition of Office Supplies |  | 14111509 | 2024-01-01 | 2024-03-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
4 | 02/008/11 | Acqusition of Training Journals |  | 14111800 | 2023-12-01 | 2024-01-01 | 1 month | Sole Select | Not applicable | Not applicable
5 | 02/008/11 | Acqusition of Training Journals |  | 14111800 | 2024-06-01 | 2024-07-01 | 1 month | Sole Select | Not applicable | Not applicable
6 | 02/008/12 | Acqusition of Mat. And Supplies for Furniture Branch |  | 56000000 | 2023-10-01 | 2024-01-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
7 | 02/008/12 | Acqusition of Mat. And Supplies for Furniture Branch |  | 56000000 | 2023-10-01 | 2024-01-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
8 | 02/008/12 | Acqusition of PPE |  | 46180000 | 2024-12-01 | 2023-03-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
9 | 02/008/12 | Acqusition of Mat. And Supplies for Furniture Branch |  | 56000000 | 2024-06-01 | 2024-08-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
10 | 02/008/13 | Acqusition of Parts for Vehicle |  | 78181500 | 2024-01-01 | 2024-03-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
11 | 02/008/13 | Acqusition of Parts for Vehicle |  | 78181500 | 2024-06-01 | 2024-08-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
12 | 02/008/13 | Acqusition of Cleaning materials |  | 47000000 | 2024-02-01 | 2024-04-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
13 | 02/008/15 | Servicing and Repairs of Office Equipment |  | 81112306 | 401/04/2023 | 2024-06-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
14 | 02/008/16 | Hiring of 17 CAD Technicians |  | 80111700 | 2024-01-01 | 2024-03-01 | 1 month | Sole select | Not applicable | Not applicable
15 | 02/008/17 | Training for staff |  | 86100000 | 2024-01-01 | 2024-02-01 | 1 month | Sole select | Not applicable | Not applicable
16 | 02/008/21 | Acqusition of Construction Materials for repairs |  | 22101900 | 2023-12-01 | 2024-02-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
17 | 02/008/21 | Acqusition of Construction Materials for repairs |  | 22101900 | 2024-04-01 | 2024-06-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
18 | 02/008/22 | Hiring of a Lathe Machine Operator for one year |  | 22101900 | 2023-12-01 | 2024-03-01 | 1 month | Sole select | Not applicable | Not applicable
19 | 02/008/28 | Acqusition of Companies to conduct Geological surveys |  | 81101514 | 2024-02-01 | 2024-04-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
20 | 02/008/37 | Acqusition of Company to remove waste |  | 76121600 | 2023-11-01 | 2024-02-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
21 | 02/008/57 | Payment of postage and courier services |  | 44121500 | 2024-05-01 | 2024-05-01 | 1 month | Sole Select | Not applicable | Not applicable
22 | 02/008/58 | As per Agreement, Daily-Paid workers attached to Furniture Branch to do Yearly Examination |  | 86101800 | 2024-06-01 | 2024-07-01 | 1 month | Sole Select | Not applicable | Not applicable
23 | 02/008/96 | Payment to Comptroller i.r.o fuel usage of vehicles |  | 15000000 | 2023-11-01 | 2023-12-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
24 | 02/008/96 | Acqusition of Office Stationery |  | 14111509 | 2024-02-01 | 2024-03-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
25 | 02/008/96 | Acqusition of Office Stationery |  | 14111509 | 2024-07-01 | 2024-08-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
26 | 03/008/01 | Acquisition of Vehicle |  | 25100000 | 2024-01-01 | 2024-03-01 | 1 month | Three Quote Sys. | Not applicable | Not applicable
PSIP /CF/IDF
1 | 4/5/6 Sub II | Sangre Grande Works Office , Guaico: Construction of Wirewall and Blockwall security fencing | Construction of perimeter fencing | 30151800 | 2023-10-01 | 2024-02-01 | 90 days | Open Bidding | 10 working days | Measured Works Contract
2 | 4/5/3 Sub I | Mechanical Services Department, Caroni - The Construction of Mezzanine Floor in Workshop | Constuction of a mezzanine floor | 30161700 | 2023-10-01 | 2024-02-01 | 90 days | Open Bidding | 10 working days | Fixed Term Contract
3 | 4/5/31 | Geotechnical Proposal New Office Building: Southern Main Road, Curepe | Geotechnical investigations | 72141500 | 2023-10-01 | 2024-02-01 | 60 days | Selective | 10 working days | Fixed Term Contract
4 | 4/5/11 Sub VI | Service Contract for Pest control at D'Abadie Furniture Branch and Stores | Pest control | 72102100 | 2023-10-01 | 2024-02-01 | 30 days | Selective | 10 working days | Fixed Term Contract
5 | 4/5/3 Sub I | Construction of wire wall fencng at Mechanical Services Division, Caroni | Construction of perimeter fencing | 30151800 | 2023-10-01 | 2024-02-01 | 90 days | Open Bidding | 10 working days | Measured Works Contract
6 | 4/5/11 Sub VI | Construction of wire wall fencng at D'D'Abadie Furniture Branch and Stores | Construction of perimeter fencing | 30151800 | 2023-10-01 | 2024-02-01 | 90 days | Open Bidding | 10 working days | Measured Works Contract
7 | 4/5/32 | District Ofices Repairs | plumbing and electrical upgrades and general refurbishment to buildings | 72101500 | 2023-11-01 | 2024-04-01 | 120 days | Open Bidding | 10 working days | Measured Works Contract
8 | 4/5/11 Sub VIIII | D'Abadie Furniture Branch and Stores - Expeller fans | Supply and install of expeller fans | 72101500 | 2023-10-01 | 2024-02-01 | 30 days | Selective | 10 working days | Fixed Term Contract
9 | XXXX | Geotechnical Proposal New Office Building: Frederick Street, POS | Geotechnical investigations | 72141500 | 2023-10-01 | 2024-02-01 | 60 days | Selective | 10 working days | Fixed Term Contract
10 | XXXX | Service Contract for Pest control at Beetham Stockpile for a period of 1yr | Pest control | 72102100 | 2023-10-01 | 2024-02-01 | 30 days | Selective | 10 working days | Fixed Term Contract
11 | XXXX | Geotechnical Proposal South Regional Head Office, San Fernando | Geotechnical investigations | 72141500 | 2023-11-01 | 2024-04-01 | 60 days | Selective | 10 working days | Fixed Term Contract

## CTO (hidden)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
CTO
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## Drainage Division
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Drainage Division
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
Recurrent Expenditure
2 | 02/005/03 | Uniforms | 53102700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
3 | 02/005/04 | Electricity | 83101800 | 1st Quarter Fiscal 2024 | 2024-09-01 | 1 year | Sole Select | Not applicable | Not applicable
4 | 02/005/05 | Telephone | 83111501 | 1st Quarter Fiscal 2024 | 2024-09-01 | 1 year | Sole Select | Not applicable | Not applicable
5 | 02/005/06 | WASA | 83101500 | 1st Quarter Fiscal 2024 | 2024-09-01 | 1 year | Sole Select | Not applicable | Not applicable
6 | 02/005/08 | Rent/Lease-Office Accommodation | 80131500 | 1st Quarter Fiscal 2024 | 2024-09-01 | 1 year | Single Source | Not applicable | Not applicable
7 | 02/005/09 | Rent/Lease of Vehicle Equipment | 72141700 (equipment) | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotation | Not applicable | Not applicable
8 | 02/005/10 | Stationery and Supplies | 44120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
9 | 02/005/11 | Books and Periodicals | 14111800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
10 | 02/005/12 | Materials and Supplies |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
11 | 02/005/13 | Maintenance of Vehicles | 78181500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
12 | 02/005/15 | Repairs & M'tce of Equipment | 81112306 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
14 | 02/005/17 | Training | 86100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 month | Request for Quotation | Not applicable | Not applicable
15 | 02/005/21 | Repairs & Maintenance of Buildings | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 3 months | Request for Quotation | Not applicable | Not applicable
17 | 02/005/28 | Other Contracted Services |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 3 months | Limited Bidding | 10 working days | Fixed Term Contract
18 | 02/005/37 | Janitorial Services | 76110000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 year | Open Bidding | 10 working days | Fixed Term Contract
19 | 02/005/43 | Security Services | 92120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 year | Open Bidding | 10 working days | Fixed Term Contract
20 | 02/005/57 | Postage | 44121500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
21 | 02/005/58 | Medical Expenses | 85000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
22 | 02/005/62 | Promotion, Publicity & Printing | 80171600 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
23 | 02/005/66 | Hosting of Seminars & Other Functions | 80141902 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
24 | 02/005/96 | Fuel & Lubricants | 15000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
25 | 03/005/01 | Replacement of Motor Vehicles | 25100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Open Bidding | 10 working days | Fixed Term Contract
26 | 03/005/02 | Office Equipment | 44000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
27 | 03/005/03 | Furniture & Furnishings | 56000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
28 | 03/005/04 | Minor Equipment | 44100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotation | Not applicable | Not applicable
1 | 02/005/28 | Construction of a R.C. Wall Along Dunderhill Ravine. Works will include the Construction of a 3.65m (H) x 20m (L) Reinforced Concrete Retaining Wall and the Construction of 6m (W) x 10m (L) Riprap | 72141205 | Fiscal 2022 (Completed) | 2023-09-05 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
2 | 02/005/28 | Construction of Reinforced Concrete Invert Along Oropuna River. | 72141205 | Fiscal 2022 (Completed) | 2023-11-30 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
3 | 02/005/28 | Construction of a R.C. Wall Along Oropouche Road. Works will include the Construction of 30m (L) x 4.7m (H) Reinforced Concrete Retaining Wall | 72141205 | Fiscal 2022 (Completed) | 2023-05-02 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
4 | 02/005/28 | Construction of a Gabion Basket Wall at Enid Village, Rio Claro. Gabion Basket Wall - 4m (H) x 70m (L) | 72141205 | Fiscal 2022 (Completed) | 2023-06-22 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
5 | 02/005/28 | Desilting Indian Trail Main Drain. | 72141205 | Fiscal 2022 (Awarded) | 2023-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
6 | 02/005/28 | Construction of a Reinforced Concrete Wall Along Bagatelle River. 85m x 3.05m RC Wall and to realign a section of the watercourse. | 72141205 | Fiscal 2022 (Completed) | 2023-08-01 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
7 | 02/005/28 | Bermudez Drain - To install 4 Flood Flaps and rehabilitate concrete invert & side walls & embankment works. | 72141205 | Fiscal 2022 (Ongoing) | 2024-03-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
8 | 02/005/28 | Construction of R.M. Walls Along St. Ann’s River, Ariapita Road (Emergency Works). Two rubble masonry walls 18m (L) x 3.67m (H), 15m (L) x 3.2m (H) and 5m (W) x 2m (L) x 1.8m (H) reinforced concrete L-Section. | 72141205 | Fiscal 2022 (Completed) | 2023-05-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
9 | 02/005/28 | Aripo River - La Platta Gardens, Valencia in the vicinity of WASA Sub Station. Construction of a R.C. Wall 4m (H) x 60m (L) and a R.C. Box Drain 1m (W) x 1m (H) x 20m (L). | 72141205 | Fiscal 2022 (Completed) | 2024-08-01 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
10 | 02/005/28 | Construction of Reinforced Concrete U-Section along The Marabella River at #25 Crescent Ave, Gopaul Lands, Marabella. U-section 45m long x 2m high (right bank) and 1.2m high (left bank), Demolition &amp; removal works and Embankment Works. | 72141205 | Fiscal 2022 (Completed) | 2024-05-15 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
11 | 02/005/28 | Inverness River - Construction of R.C. Box Drain 4m (W) x 2m(H) x 60m (L | 72141205 | Fiscal 2022 (Ongoing) | 2024-03-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
12 | 02/005/28 | IDC Drain, Diamond Vale Industrial Estate, Diego Martin - Rehabilitation of 138 linear metres of Mass Concrete Paving / Invert 4.5 metres wide. | 72141205 | 1st Quarter Fiscal 2024 | 2024-08-30 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
13 | 02/005/28 | Kavi Crescent - a) R.C. Stepped U-Section 3m (W) x 3m (H) x 30m (L) b) Rip Rap 3.7m W x 2m L & Embankment works | 72141205 | Fiscal 2023 (Ongoing) | 2024-08-30 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
14 | 02/005/28 | Curampo River - Mendez Trace, Siparia - R.C. Retaining Wall 3m (H) x 60m (L) | 72141205 | Fiscal 2023 (Awarded) | 2024-08-30 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
15 | 02/005/28 | Canque River - Corner Kitchener Street and Cunapo Southern Road - R. C. Retaining Wall 3.65m (H) x 70m (L) w/3m (L) Wingwall upstream and downstream. R. C. Retaining Wall 3m (H) x 16m (L) w/3m (H) wing wall upstream & downstream | 72141205 | Fiscal 2023 (Ongoing) | 2024-08-30 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
16 | 02/005/28 | Rampartap Tr. Drain - 1/2 mm Rampartap Tr. Off 2 mm Cunapo Southern Main Rd - Gabion Basket Retaining Wall 3m (H) x 10m (L) | 72141205 | Fiscal 2023 (Ongoing) | 2024-03-30 | 90 days | Open Bidding | 10 working days | Fixed Term Contract
17 | 02/005/28 | Construction of High Security Fence at the Sea Lots Pump Station, Abbattoir Road, POS: | 72141205 | Fiscal 2023 (Ongoing) | 2024-01-01 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
18 | 02/005/28 | Construction of High Security Fence at South Quay Pump Station, POS: | 72141205 | Fiscal 2023 (Ongoing) | 2024-01-01 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
19 | 02/005/28 | Construction of Reinforced Concrete U-Section at #20 Kaylan Trace: | 72141205 | Fiscal 2023 (Ongoing) | 2023-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
20 | 02/005/28 | Construction of a R.C Wall on the St. Joseph River at LP#13 Riverside Road, Curepe. | 72141205 | Fiscal 2023 ( Completed) | 2023-07-24 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
21 | 02/005/28 | Construction of a Reinforced Concrete Wall Along Mausica River | 72141205 | Fiscal 2023 ( Completed) | 2023-08-24 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
22 | 02/005/28 | Construction of a Reinforced Concrete Wall at Lp 53 Capildeo Lands, Morne Coco Road, Petit Valley | 72141205 | Fiscal 2023 ( Completed) | 2023-08-08 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
23 | 02/005/28 | Construction of R.C Wall along Malick River | 72141205 | Fiscal 2023 ( Completed) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
24 | 02/005/28 | Construction of a Reinforced Concrete Wall Downstream Samaroo Village | 72141205 | Fiscal 2023 ( Procuring) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
25 | 02/005/28 | Construction of a Reinforced Concrete Revetment Wall along Maraval River, St. Joseph's Convent Grounds | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
26 | 02/005/28 | Embankment Works along Mausica River, T&TEC O'Meara Substation | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
27 | 02/005/28 | Rehabilitation Works along New Cut Channel, in the vicinity of Pluck Road, Debe | 72141205 | Fiscal 2023 (Ongoing) | 2023-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
28 | 02/005/28 | Manzanilla Beach Facility Seawall Repair Works (Emergency Works) | 72141205 | Fiscal 2023 ( Completed) | 2023-09-05 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
29 | 02/005/28 | Rehabilitation & Strengthening of Embankment along Caroni River at La Paille Gardens, Caroni | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
30 | 02/005/28 | Rehabilitation Works to Guayabal River, Mohan Street, Bamboo #2 | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
31 | 02/005/28 | Rehabilitation & Strengthening of Embankment Valsayn Main Drain, Nabie Street, Bamboo #2 | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
32 | 02/005/28 | Rehabilitation of Embankment to the Caroni River at Railway Road, Caroni Village | 72141205 | Fiscal 2023 ( Procuring) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
33 | 02/005/28 | Rehabilitation of Embankment to the Caroni River at Tulloch St., La Paille Village, Caroni | 72141205 | Fiscal 2023 ( Procuring) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
34 | 02/005/28 | Rehabilitation of Eastern Embankment to St. Joseph River at Nipaul Street, Bamboo #2 | 72141205 | Fiscal 2023 ( Procuring) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
35 | 02/005/28 | Rehabilitation of Embankment to the Caroni River at Caroni South Bank Road, St Helena | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
36 | 02/005/28 | Rehabilitation & Strengthening of Embankment along Caroni River in the Vicinity of Ibis Gardens | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
37 | 02/005/28 | Construction of a Gabion Wall Along Couva River, Central Park Circular South | 72141205 | Fiscal 2023 ( Awarded) | 2024-09-06 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
38 | 02/005/28 | Emergency Works: Embankment Works along the St. Joseph River at Northern Ave Bamboo #3 | 72141205 | Fiscal 2023 ( Completed) | 2023-04-28 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
39 | 02/005/28 | Embankment Works along Drain #5, El Socorro Extension Road No. 1 | 72141205 | Fiscal 2023 ( Completed) | 2023-06-14 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
40 | 02/005/28 | Construction of R.C wall along La Puerta Ravine Diego Martin. R.C wall 30m (L) × 3.65m H | 72141205 | Fiscal 2023 ( Procuring) | 2023-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Open Bidding | 10 working days | Fixed Term Contract
41 | 02/005/28 | Malick River Desilting Works along South of Churchill-Roosevelt Highway, Barataria San Juan/Barataria | 72141205 | 1 st Quarter Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
42 | 02/005/28 | Construction of Reinforced box drain and construction of rip rap along Aripo River at WASA Sub Station, La Platta Gardens, Valencia (R.C Box Drain ( 1m (W) x 1m (H) x 20m (L) Rip Rap 7m x 3m x 0.4m) | 72141205 | 1 st Quarter Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
43 | 02/005/28 | Construction of two RC retaining walls at Tahadille Road, Pierre Road, Charlieville | 72141205 | 1 st Quarter Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
44 | 02/005/28 | Construction of Gabion Basket Wall along Guaracara River - 1 Esmeralda Road Williamsville | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
45 | 02/005/28 | Rehabilitation along the Oropouche River | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
46 | 02/005/28 | Construction of a Reinforced Concrete Retaining Wall along Tributary to Coromata River ( R.C. Wall 30m (L) x 2.4m (H)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
47 | 02/005/28 | Construction of Gabion Basket Wall along Mission River (4m (H) x 30m (L) ) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
48 | 02/005/28 | Construction of Gabion Basket Wall along Guaracara River - 1 Esmeralda Road Williamsville | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
49 | 02/005/28 | Rehabilitation along the Oropouche River at LP # 70 Toco Road | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
50 | 02/005/28 | Construction of a Reinforced Concrete Retaining Wall along Tributary to Coromata River at 712 Penal Rock Road, Penal (30m (L) x 2.4m (H)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
51 | 02/005/28 | Construction of Gabion Basket Wall along Mission River at B 2/48 Paria Main Road, Mission Village (6m (H) x 30 (L)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
52 | 02/005/28 | Reconstruction of North Embankment along Couva River and reallignment of a section of the Carli Bay Road | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
53 | 02/005/28 | Construction of a Reinforced Concrete Box Drain at Barker Tr. Drain - 1 MM Barker Tr. Off Cunapo 1 1/2 mm Southern Main Rd (1.2m (W) x 1m (H) x 30m (L)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
54 | 02/005/28 | Construction of reinforced concrete wall along Mandillon River at #205 Southern Main Road, Claxton Bay (2.4m (H) x 100m (L) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
55 | 02/005/28 | Construction of a Reinfroced Concrete Wall along Tributary to Dunlop River at South Central Road Point Fortin (3m (H) x 75m (L)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
56 | 02/005/28 | Construction of U-Section along Mandillion river at Mathura lane, Union Rd, Claxton Bay (30m (L) x 4m (W) x 2m (H)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
57 | 02/005/28 | Construction of R.C drain along Cunapo River at San Francique Penal (Walling and Paving 70m (L) x 2.4m (W) x 1.8m (H)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
58 | 02/005/28 | East Dry River Desilting Works Between Beetham Highway & outfall at sea, Sea Lots Port-of-Spain | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
59 | 02/005/28 | Construction of R.C drain along Reform Drain at #32A Railway Road, Reform Village (Walling and Paving 150m (L) x 2.0m (W) x 1.0m (H)) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
60 | 02/005/28 | Construction of Gabion Basket Walls along Anglais River at Bridge on Toco Road, Cumana (4m (H) x 20 (L) Upstream) 4m (H) x 3m (L) Downstream) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
61 | 02/005/28 | Rehabilitation Works to the Morne Coco Ravine at Morne Coco Road Maraval, betweeen L.P 189 & 195 | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
62 | 02/005/28 | Construction of Reinforced Concrete Retaining Wall along Canque River. Construction of box drain at #17 Sookdeo Street, Biche | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
63 | 02/005/28 | Construction of RC open Box Drain from Rodney Road to Jerningham Railway Road, Endeavour from Rodney Road to Jerningham Railway Road, Endeavour (200m Long x 2.1m high x 3.5m wide) | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
64 | 02/005/28 | Rehabilitation of Concrete Paving / Invert on the IDC Drain, Diamond Vale Industrial Estate, Diego Martin | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
65 | 02/005/28 | Construction of RC Block Box Drain at Sonny Ladoo Outfall Drain, SMR, Couva at Sonny Ladoo Outfall Drain/ S.M.R Mc. Bean , Couva | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
66 | 02/005/28 | Construction of Reinforced Concrete Paving Arima River at South of Churchill - Roosevelt Highway, Arima near Arawak Chicken Factory | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
67 | 02/005/28 | Rehabilitation & Embankment Works along La Cuesa River at Southern Main Road to Orange Field Road, Carapichaima | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
68 | 02/005/28 | Construction of Reinforced Concrete Walls along the St. Joseph River at LP #108 Maracas Royal Road, St. Joseph Maracas | 72141205 | 1 st Quarter of Fiscal 2024 | 2024-12-31 | 455 days ( 90days for project duration and 365 days for defects liability period) | Limited Bidding | 10 working days | Fixed Term Contract
09&28
1 | 02/005/09 | Caroni river 3km-4km mark from Tumpuna Bridge - North Bank | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
2 | 02/005/09 | Caroni river 3km-4km mark from Tumpuna Bridge - South Bank | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
3 | 02/005/09 | Caroni River | 70171800 | 2024-01-23 | 2024-03-23 | 750 hours | Invoice Order | Not applicable | Not applicable
4 | 02/005/09 | Guanapo River | 70171800 | 2024-01-23 | 2024-03-23 | 620 hours | Invoice Order | Not applicable | Not applicable
5 | 02/005/09 | Cascade River | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
6 | 02/005/09 | Morne Coco Silt Trap and downstream | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
7 | 02/005/09 | Perserverance Silt Trap | 70171800 | 2024-01-23 | 2024-03-23 | 120 hours | Invoice Order | Not applicable | Not applicable
8 | 02/005/09 | San Juan River Weir | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
9 | 02/005/09 | Camacho & Cocorite silt traps | 70171800 | 2024-01-23 | 2024-03-23 | 100 hours | Invoice Order | Not applicable | Not applicable
10 | 02/005/09 | Mt Dor Silt Trap | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
11 | 02/005/09 | Blue Range Silt Trap | 70171800 | 2024-01-23 | 2024-03-23 | 50 hours | Invoice Order | Not applicable | Not applicable
12 | 02/005/09 | Sunrise park Silt Trap and Drain | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
13 | 02/005/09 | Malick Silt Trap and Desilting Upstream | 70171800 | 2024-01-23 | 2024-03-23 | 175 hours | Invoice Order | Not applicable | Not applicable
14 | 02/005/09 | St Ann's Silt Trap | 70171800 | 2024-01-23 | 2024-03-23 | 100 hours | Invoice Order | Not applicable | Not applicable
15 | 02/005/09 | La Seiva Ravine & Silt Trap | 70171800 | 2024-01-23 | 2024-03-23 | 100 hours | Invoice Order | Not applicable | Not applicable
16 | 02/005/09 | John John silt traps | 70171800 | 2024-01-23 | 2024-03-23 | 100 hours | Invoice Order | Not applicable | Not applicable
17 | 02/005/09 | Bournes Road Ravine and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable | `
18 | 02/005/09 | Maraval River | 70171800 | 2024-01-23 | 2024-03-23 | 1250 hours | Invoice Order | Not applicable | Not applicable
19 | 02/005/09 | San Juan River | 70171800 | 2024-01-23 | 2024-03-23 | 830 hours | Invoice Order | Not applicable | Not applicable
20 | 02/005/09 | Petit Valley Ravine and Trib | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
21 | 02/005/09 | Tunapuna River | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
22 | 02/005/09 | Blackman Ravine and Tributary | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
23 | 02/005/09 | Blue Basin Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
24 | 02/005/09 | La Horquette River | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
25 | 02/005/09 | Diego Martin River | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
26 | 02/005/09 | Bagatelle Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
27 | 02/005/09 | Blue Basin Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
28 | 02/005/09 | Hawkins Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 600 hours | Invoice Order | Not applicable | Not applicable
29 | 02/005/09 | Diego Martin River | 70171800 | 2024-01-23 | 2024-03-23 | 720 hours | Invoice Order | Not applicable | Not applicable
30 | 02/005/09 | St. Anns / East Dry River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
31 | 02/005/09 | Cane Farm Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
32 | 02/005/09 | Carapo Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
33 | 02/005/09 | Sam Boucaud Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
34 | 02/005/09 | Santa Cruz | 70171800 | 2024-01-23 | 2024-03-23 | 450 hours | Invoice Order | Not applicable | Not applicable
35 | 02/005/09 | Santa Cruz River | 70171800 | 2024-01-23 | 2024-03-23 | 470 hours | Invoice Order | Not applicable | Not applicable
36 | 02/005/09 | Arouca River | 70171800 | 2024-01-23 | 2024-03-23 | 750 hours | Invoice Order | Not applicable | Not applicable
37 | 02/005/09 | Gasparillo River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
38 | 02/005/09 | Patna Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 100 hours | Invoice Order | Not applicable | Not applicable
39 | 02/005/09 | Mora Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 470 hours | Invoice Order | Not applicable | Not applicable
40 | 02/005/09 | Carapo River | 70171800 | 2024-01-23 | 2024-03-23 | 220 hours | Invoice Order | Not applicable | Not applicable
41 | 02/005/09 | Majuba Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
42 | 02/005/09 | Barataria Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 140 hours | Invoice Order | Not applicable | Not applicable
43 | 02/005/09 | St Joseph River | 70171800 | 2024-01-23 | 2024-03-23 | 650 hours | Invoice Order | Not applicable | Not applicable
44 | 02/005/09 | Thomas trace Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
45 | 02/005/09 | Dunderhill main drain | 70171800 | 2024-01-23 | 2024-03-23 | 180 hours | Invoice Order | Not applicable | Not applicable
46 | 02/005/09 | Runway Drain | 70171800 | 2024-03-23 | 2024-06-23 | 100 hours | Invoice Order | Not applicable | Not applicable
47 | 02/005/09 | Mt Lambert Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 150 hours | Invoice Order | Not applicable | Not applicable
48 | 02/005/09 | Covigne Ravine | 70171800 | 2024-03-23 | 2024-06-23 | 350 hours | Invoice Order | Not applicable | Not applicable
49 | 02/005/09 | Saut d'eau ravine | 70171800 | 2024-03-23 | 2024-06-23 | 150 hours | Invoice Order | Not applicable | Not applicable
50 | 02/005/09 | Smith Hill River | 70171800 | 2024-03-23 | 2024-06-23 | 100 hours | Invoice Order | Not applicable | Not applicable
51 | 02/005/09 | Factory Road Drain | 70171800 | 2024-03-23 | 2024-06-23 | 350 hours | Invoice Order | Not applicable | Not applicable
52 | 02/005/09 | Industry River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
53 | 02/005/09 | Rich Plain River | 70171800 | 2024-03-23 | 2024-06-23 | 150 hours | Invoice Order | Not applicable | Not applicable
54 | 02/005/09 | La Puerta River | 70171800 | 2024-03-23 | 2024-06-23 | 100 hours | Invoice Order | Not applicable | Not applicable
55 | 02/005/09 | Scorpion Ravine | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
56 | 02/005/09 | Guayabal ravine | 70171800 | 2024-03-23 | 2024-06-23 | 250 hours | Invoice Order | Not applicable | Not applicable
57 | 02/005/09 | N.U.G.F.W Drain and Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 250 hours | Invoice Order | Not applicable | Not applicable
58 | 02/005/09 | Oropune River | 70171800 | 2024-03-23 | 2024-06-23 | 550 hours | Invoice Order | Not applicable | Not applicable
59 | 02/005/09 | Arima River | 70171800 | 2024-03-23 | 2024-06-23 | 700 hours | Invoice Order | Not applicable | Not applicable
60 | 02/005/09 | Blackwater Ravine | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
61 | 02/005/09 | Tacarigua River | 70171800 | 2024-03-23 | 2024-06-23 | 850 hours | Invoice Order | Not applicable | Not applicable
62 | 02/005/09 | Cannings Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 250 hours | Invoice Order | Not applicable | Not applicable
63 | 02/005/09 | Mausica River | 70171800 | 2024-03-23 | 2024-06-23 | 730 hours | Invoice Order | Not applicable | Not applicable
64 | 02/005/09 | Centeno River | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
65 | 02/005/09 | Malick River | 70171800 | 2024-03-23 | 2024-06-23 | 350 hours | Invoice Order | Not applicable | Not applicable
66 | 02/005/09 | La Pastora River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
67 | 02/005/09 | Carib Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 150 hours | Invoice Order | Not applicable | Not applicable
68 | 02/005/09 | Tributary to Arthur Lok Jack Drain | 70171800 | 2024-06-23 | 2024-09-23 | 100 hours | Invoice Order | Not applicable | Not applicable
69 | 02/005/09 | Martin Main Drain and Trib | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
70 | 02/005/09 | Valsayn Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
71 | 02/005/09 | Macoya Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
72 | 02/005/09 | Ansa Drain | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
73 | 02/005/09 | La Horquetta Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 270 hours | Invoice Order | Not applicable | Not applicable
74 | 02/005/09 | Arena Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 270 hours | Invoice Order | Not applicable | Not applicable
75 | 02/005/09 | Miss Gutter Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 460 hours | Invoice Order | Not applicable | Not applicable
76 | 02/005/09 | Caroni River | 70171800 | 2024-06-23 | 2024-09-23 | 270 hours | Invoice Order | Not applicable | Not applicable
77 | 02/005/09 | New Blue Waters Drain | 70171800 | 2024-06-23 | 2024-09-23 | 170 hours | Invoice Order | Not applicable | Not applicable
78 | 02/005/09 | Skimming Drain | 70171800 | 2024-06-23 | 2024-09-23 | 130 hours | Invoice Order | Not applicable | Not applicable
79 | 02/005/09 | Cemetery Drain | 70171800 | 2024-06-23 | 2024-09-23 | 120 hours | Invoice Order | Not applicable | Not applicable
80 | 02/005/09 | West Moorings Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 100 hours | Invoice Order | Not applicable | Not applicable
81 | 02/005/09 | Capriatta Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
82 | 02/005/09 | L'anse Mitan Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 130 hours | Invoice Order | Not applicable | Not applicable
83 | 02/005/09 | College Main Drain and Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
84 | 02/005/09 | Macoya River | 70171800 | 2024-06-23 | 2024-09-23 | 220 hours | Invoice Order | Not applicable | Not applicable
85 | 02/005/09 | Arouca River | 70171800 | 2024-06-23 | 2024-09-23 | 300 hours | Invoice Order | Not applicable | Not applicable
86 | 02/005/09 | Niherst Science Centre Drain and Interlots Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
87 | 02/005/09 | Detention Pond | 70171800 | 2024-06-23 | 2024-09-23 | 100 hours | Invoice Order | Not applicable | Not applicable
88 | 02/005/09 | Rincon River | 70171800 | 2024-06-23 | 2024-09-23 | 220 hours | Invoice Order | Not applicable | Not applicable
89 | 02/005/09 | Mexico River | 70171800 | 2024-06-23 | 2024-09-23 | 300 hours | Invoice Order | Not applicable | Not applicable
90 | 02/005/09 | Agua Santa River | 70171800 | 2024-06-23 | 2024-09-23 | 300 hours | Invoice Order | Not applicable | Not applicable
91 | 02/005/09 | Talparo River | 70171800 | 2024-06-23 | 2024-09-23 | 230 hours | Invoice Order | Not applicable | Not applicable
92 | 02/005/09 | Repost Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
93 | 02/005/09 | PBR Crossing Beetham Gardens | 70171800 | 2024-06-23 | 2024-09-23 | 220 hours | Invoice Order | Not applicable | Not applicable
94 | 02/005/09 | Maracas Bay River | 70171800 | 2024-06-23 | 2024-09-23 | 220 hours | Invoice Order | Not applicable | Not applicable
95 | 02/005/09 | Mariners Haven Drain | 70171800 | 2024-06-23 | 2024-09-23 | 100 hours | Invoice Order | Not applicable | Not applicable
96 | 02/005/09 | Old Blue Waters Drain | 70171800 | 2024-06-23 | 2024-09-23 | 100 hours | Invoice Order | Not applicable | Not applicable
97 | 02/005/09 | Granford River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
98 | 02/005/09 | Guanapo River | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
99 | 02/005/09 | Dunderhill Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
100 | 02/005/09 | Lopinot River | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
101 | 02/005/09 | Sin Verguanza River | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
102 | 02/005/09 | Salegam Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
103 | 02/005/09 | Trainline Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
104 | 02/005/09 | Morvant River | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
105 | 02/005/09 | Baratarian Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
106 | 02/005/09 | Corbeau Drain | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
107 | 02/005/09 | Collector Drain | 70171800 | 2024-06-23 | 2024-09-23 | 350 hours | Invoice Order | Not applicable | Not applicable
108 | 02/005/09 | NP Drain | 70171800 | 2024-06-23 | 2024-09-23 | 30 hours | Invoice Order | Not applicable | Not applicable
109 | 02/005/09 | CGA Drain | 70171800 | 2024-06-23 | 2024-09-23 | 30 hours | Invoice Order | Not applicable | Not applicable
110 | 02/005/09 | Hell Yard Drain (TELCO) | 70171800 | 2024-06-23 | 2024-09-23 | 30 hours | Invoice Order | Not applicable | Not applicable
111 | 02/005/09 | Wharton Street (Servol) | 70171800 | 2024-06-23 | 2024-09-23 | 30 hours | Invoice Order | Not applicable | Not applicable
112 | 02/005/09 | Mc Alister Drain | 70171800 | 2024-06-23 | 2024-09-23 | 30 hours | Invoice Order | Not applicable | Not applicable
113 | 02/005/09 | VMCOTT | 70171800 | 2024-06-23 | 2024-09-23 | 30 hours | Invoice Order | Not applicable | Not applicable
114 | 02/005/09 | Beetham Drain Parallel to PBR | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
115 | 02/005/09 | Caroni River | 70171800 | 2024-06-23 | 2024-09-23 | 300 hours | Invoice Order | Not applicable | Not applicable
116 | 02/005/09 | Oropouche River | 70171800 | 2024-01-23 | 2024-03-23 | 350 hours | Invoice Order | Not applicable | Not applicable
117 | 02/005/09 | New Cut Channel | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
118 | 02/005/09 | Mungal Channel | 70171800 | 2024-01-23 | 2024-03-23 | 120 hours | Invoice Order | Not applicable | Not applicable
119 | 02/005/09 | Duck Pond River | 70171800 | 2024-01-23 | 2024-03-23 | 180 hours | Invoice Order | Not applicable | Not applicable
120 | 02/005/09 | St Louis River | 70171800 | 2024-01-23 | 2024-03-23 | 220 hours | Invoice Order | Not applicable | Not applicable
121 | 02/005/09 | Mahaut River | 70171800 | 2024-01-23 | 2024-03-23 | 220 hours | Invoice Order | Not applicable | Not applicable
122 | 02/005/09 | Cunapo River | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
123 | 02/005/09 | Bhagmania River | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
124 | 02/005/09 | Murocupano River | 70171800 | 2024-01-23 | 2024-03-23 | 130 hours | Invoice Order | Not applicable | Not applicable
125 | 02/005/09 | Cipero River | 70171800 | 2024-01-23 | 2024-03-23 | 120 hours | Invoice Order | Not applicable | Not applicable
126 | 02/005/09 | Coromata River | 70171800 | 2024-01-23 | 2024-03-23 | 350 hours | Invoice Order | Not applicable | Not applicable
127 | 02/005/09 | Black Water Channel | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
128 | 02/005/09 | Black Water Channel and Tributary | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
129 | 02/005/09 | Erin River and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
130 | 02/005/09 | Morne Roche River | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
131 | 02/005/09 | Marabella River | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
132 | 02/005/09 | Trinidad River & Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 350 hours | Invoice Order | Not applicable | Not applicable
133 | 02/005/09 | Trinidad River | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
134 | 02/005/09 | Tarouba River | 70171800 | 2024-03-23 | 2024-06-23 | 220 hours | Invoice Order | Not applicable | Not applicable
135 | 02/005/09 | Chinnebass River | 70171800 | 2024-03-23 | 2024-06-23 | 315 hours | Invoice Order | Not applicable | Not applicable
136 | 02/005/09 | Lengua River | 70171800 | 2024-03-23 | 2024-06-23 | 220 hours | Invoice Order | Not applicable | Not applicable
137 | 02/005/09 | Fairfield River | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
138 | 02/005/09 | Gucharon Retention Pond | 70171800 | 2024-03-23 | 2024-06-23 | 150 hours | Invoice Order | Not applicable | Not applicable
139 | 02/005/09 | Gucharon River | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
140 | 02/005/09 | Silver Stream River | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
141 | 02/005/09 | Moonsie River | 70171800 | 2024-03-23 | 2024-06-23 | 170 hours | Invoice Order | Not applicable | Not applicable
142 | 02/005/09 | Techier 1 & 2 | 70171800 | 2024-03-23 | 2024-06-23 | 170 hours | Invoice Order | Not applicable | Not applicable
143 | 02/005/09 | Dunlop River | 70171800 | 2024-03-23 | 2024-06-23 | 400 hours | Invoice Order | Not applicable | Not applicable
144 | 02/005/09 | Guapo River & Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
145 | 02/005/09 | Cap-de-Ville River | 70171800 | 2024-06-23 | 2024-09-23 | 220 hours | Invoice Order | Not applicable | Not applicable
146 | 02/005/09 | Papourie River | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
147 | 02/005/09 | Blackwater River | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
148 | 02/005/09 | Narine Persad Drain | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
149 | 02/005/09 | 40 Foot River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
150 | 02/005/09 | Curampo River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
151 | 02/005/09 | Vistabella River | 70171800 | 2024-06-23 | 2024-09-23 | 120 hours | Invoice Order | Not applicable | Not applicable
152 | 02/005/09 | Alley's Creek | 70171800 | 2024-06-23 | 2024-09-23 | 140 hours | Invoice Order | Not applicable | Not applicable
153 | 02/005/09 | Scotts Road 1&2 | 70171800 | 2024-06-23 | 2024-09-23 | 185 hours | Invoice Order | Not applicable | Not applicable
154 | 02/005/09 | Moolai River | 70171800 | 2024-06-23 | 2024-09-23 | 120 hours | Invoice Order | Not applicable | Not applicable
155 | 02/005/09 | Congo River | 70171800 | 2024-06-23 | 2024-09-23 | 225 hours | Invoice Order | Not applicable | Not applicable
156 | 02/005/09 | Subrattie Drain | 70171800 | 2024-06-23 | 2024-09-23 | 140 hours | Invoice Order | Not applicable | Not applicable
157 | 02/005/09 | Beharry Drain | 70171800 | 2024-06-23 | 2024-09-23 | 140 hours | Invoice Order | Not applicable | Not applicable
158 | 02/005/09 | Tributary to Guaico River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
159 | 02/005/09 | Cemetery River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
160 | 02/005/09 | Quare River | 70171800 | 2024-01-23 | 2024-03-23 | 150 hours | Invoice Order | Not applicable | Not applicable
161 | 02/005/09 | Tributary To Poole River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
162 | 02/005/09 | Tributary to Cunaripo River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
163 | 02/005/09 | Yaigual River and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
164 | 02/005/09 | Big River and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
165 | 02/005/09 | Tributary to Cuchee River | 70171800 | 2024-01-23 | 2024-03-23 | 130 hours | Invoice Order | Not applicable | Not applicable
166 | 02/005/09 | Mahaut River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
167 | 02/005/09 | Lagoon Mouths & Sea Outlets | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
168 | 02/005/09 | Caigual River | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
169 | 02/005/09 | Tributary to Cunapo River | 70171800 | 2024-01-23 | 2024-03-23 | 170 hours | Invoice Order | Not applicable | Not applicable
170 | 02/005/09 | Tributary To Mantacool River | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
171 | 02/005/09 | Tributary to Arena River | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
172 | 02/005/09 | Canque River | 70171800 | 2024-01-23 | 2024-03-23 | 720 hours | Invoice Order | Not applicable | Not applicable
173 | 02/005/09 | Tributary to Matura River | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
174 | 02/005/09 | Salazar River | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
175 | 02/005/09 | Kernaham River & Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 900 hours | Invoice Order | Not applicable | Not applicable
176 | 02/005/09 | Cunapo River | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
177 | 02/005/09 | Sangre Chiquito River | 70171800 | 2024-01-23 | 2024-03-23 | 600 hours | Invoice Order | Not applicable | Not applicable
178 | 02/005/09 | Bamboo River and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 140 hours | Invoice Order | Not applicable | Not applicable
179 | 02/005/09 | Salazar River | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
180 | 02/005/09 | Guaico River | 70171800 | 2024-01-23 | 2024-03-23 | 450 hours | Invoice Order | Not applicable | Not applicable
181 | 02/005/09 | Tributaries to Matura River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
182 | 02/005/09 | Tribuyary To Mantacool River | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
183 | 02/005/09 | James Smart River | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
184 | 02/005/09 | Le Branche River | 70171800 | 2024-01-23 | 2024-03-23 | 550 hours | Invoice Order | Not applicable | Not applicable
185 | 02/005/09 | Cushe River | 70171800 | 2024-01-23 | 2024-03-23 | 460 hours | Invoice Order | Not applicable | Not applicable
186 | 02/005/09 | Manning Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 65 hours | Invoice Order | Not applicable | Not applicable
187 | 02/005/09 | Samuel River | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
188 | 02/005/09 | Manning Ravine | 70171800 | 2024-01-23 | 2024-03-23 | 250 hours | Invoice Order | Not applicable | Not applicable
189 | 02/005/09 | Wynappie River | 70171800 | 2024-01-23 | 2024-03-23 | 260 hours | Invoice Order | Not applicable | Not applicable
190 | 02/005/09 | Tributary to Oropouche River | 70171800 | 2024-01-23 | 2024-03-23 | 850 hours | Invoice Order | Not applicable | Not applicable
191 | 02/005/09 | Tributary To Ortoire River | 70171800 | 2024-03-23 | 2024-06-23 | 400 hours | Invoice Order | Not applicable | Not applicable
192 | 02/005/09 | Tributary to Guaico River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
193 | 02/005/09 | Kernaham River & Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 600 hours | Invoice Order | Not applicable | Not applicable
194 | 02/005/09 | Bamboo River and Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
195 | 02/005/09 | Tributary To Killdeer River | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
196 | 02/005/09 | Tributary to Cunaripo River | 70171800 | 2024-03-23 | 2024-06-23 | 150 hours | Invoice Order | Not applicable | Not applicable
197 | 02/005/09 | Tributary To Salazar River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
198 | 02/005/09 | Wynappie River | 70171800 | 2024-03-23 | 2024-06-23 | 260 hours | Invoice Order | Not applicable | Not applicable
199 | 02/005/09 | Tributary to Caigual River | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
200 | 02/005/09 | New Bolt River and Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 350 hours | Invoice Order | Not applicable | Not applicable
201 | 02/005/09 | Tributary to Ortoire River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
202 | 02/005/09 | Guaico River (Downstream) | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
203 | 02/005/09 | Lagoon Mouths & Sea Outlets | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
204 | 02/005/09 | Popwell drain | 70171800 | 2024-03-23 | 2024-06-23 | 100 hours | Invoice Order | Not applicable | Not applicable
205 | 02/005/09 | Cunapo River | 70171800 | 2024-03-23 | 2024-06-23 | 350 hours | Invoice Order | Not applicable | Not applicable
206 | 02/005/09 | Tributary to Salazar River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
207 | 02/005/09 | Tributary to Sangre Chiquito River | 70171800 | 2024-03-23 | 2024-06-23 | 150 hours | Invoice Order | Not applicable | Not applicable
208 | 02/005/09 | Tributary To Killdeer River | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
209 | 02/005/09 | Tributary to Mahaut River | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
210 | 02/005/09 | Mainline River | 70171800 | 2024-03-23 | 2024-06-23 | 560 hours | Invoice Order | Not applicable | Not applicable
211 | 02/005/09 | Lagoon Mahaut River | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
212 | 02/005/09 | Tributary to Le Branche River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
213 | 02/005/09 | Tributary to Mahaut River | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
214 | 02/005/09 | Tributary To Poole River | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
215 | 02/005/09 | Sangre Chiquito River | 70171800 | 2024-03-23 | 2024-06-23 | 250 hours | Invoice Order | Not applicable | Not applicable
216 | 02/005/09 | Comparo River and Tributaries (Upstream) | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
217 | 02/005/09 | Tributary to the Cunapo River | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
218 | 02/005/09 | Lagoon Mahaut River | 70171800 | 2024-03-23 | 2024-06-23 | 280 hours | Invoice Order | Not applicable | Not applicable
219 | 02/005/09 | La Savanne River upstream and downstream | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
220 | 02/005/09 | Killdeer River | 70171800 | 2024-06-23 | 2024-09-23 | 260 hours | Invoice Order | Not applicable | Not applicable
221 | 02/005/09 | Kernaham River & Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 600 hours | Invoice Order | Not applicable | Not applicable
222 | 02/005/09 | Tributary To Mantacool River | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
223 | 02/005/09 | Tributary to Cunapo River | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
224 | 02/005/09 | Cato Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 140 hours | Invoice Order | Not applicable | Not applicable
225 | 02/005/09 | Tributary To Nariva River | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
226 | 02/005/09 | Tributary to Cunaripo River | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
227 | 02/005/09 | Tributary To Ortoire River | 70171800 | 2024-06-23 | 2024-09-23 | 440 hours | Invoice Order | Not applicable | Not applicable
228 | 02/005/09 | Tributary to Cunaripo River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
229 | 02/005/09 | Nariva River and Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 260 hours | Invoice Order | Not applicable | Not applicable
230 | 02/005/09 | Tributary To Nariva River | 70171800 | 2024-06-23 | 2024-09-23 | 260 hours | Invoice Order | Not applicable | Not applicable
231 | 02/005/09 | Tributaries to Le Branche River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
232 | 02/005/09 | Tributary To Poole River | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
233 | 02/005/09 | Black Swamp River | 70171800 | 2024-06-23 | 2024-09-23 | 260 hours | Invoice Order | Not applicable | Not applicable
234 | 02/005/09 | Tributary to Cunapo River | 70171800 | 2024-06-23 | 2024-09-23 | 280 hours | Invoice Order | Not applicable | Not applicable
235 | 02/005/09 | Valencia River | 70171800 | 2024-06-23 | 2024-09-23 | 120 hours | Invoice Order | Not applicable | Not applicable
236 | 02/005/09 | Tributary To Killdeer River | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
237 | 02/005/09 | Tributary to Cuchee River | 70171800 | 2024-06-23 | 2024-09-23 | 130 hours | Invoice Order | Not applicable | Not applicable
238 | 02/005/09 | Tambolatay River | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
239 | 02/005/09 | Ocean Sands Drain | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
240 | 02/005/09 | La Savanne River upstream and downstream | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
241 | 02/005/09 | Tributary To Mantacool River | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
242 | 02/005/09 | Tributary to Bamboo River | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
243 | 02/005/09 | Tributary to Mahaut River | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
244 | 02/005/09 | Tributary to Le Branche River | 70171800 | 2024-06-23 | 2024-09-23 | 250 hours | Invoice Order | Not applicable | Not applicable
245 | 02/005/09 | Tributary To Ortoire River | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
246 | 02/005/09 | Tributaries to Le Branche River | 70171800 | 2024-06-23 | 2024-09-23 | 340 hours | Invoice Order | Not applicable | Not applicable
247 | 02/005/09 | Tributary to Guaico River | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
248 | 02/005/09 | Tributary to Cunapo River | 70171800 | 2024-06-23 | 2024-09-23 | 100 hours | Invoice Order | Not applicable | Not applicable
249 | 02/005/09 | Tributaries to Le Branche River | 70171800 | 2024-06-23 | 2024-09-23 | 340 hours | Invoice Order | Not applicable | Not applicable
250 | 02/005/09 | Tributaries to New Bolt River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
251 | 02/005/09 | Tributaries to Sangre Chiquito River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
252 | 02/005/09 | Biche River | 70171800 | 2024-06-23 | 2024-09-23 | 220 hours | Invoice Order | Not applicable | Not applicable
253 | 02/005/09 | Tributaries to Le Branche River | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
254 | 02/005/09 | Tributary to Guaico River | 70171800 | 2024-06-23 | 2024-09-23 | 150 hours | Invoice Order | Not applicable | Not applicable
255 | 02/005/09 | Ghandiah River & Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
256 | 02/005/09 | Tributary to Caparo River | 70171800 | 2024-01-23 | 2024-03-23 | 280 hours | Invoice Order | Not applicable | Not applicable
257 | 02/005/09 | Mamoral River & Tributary | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
258 | 02/005/09 | Caparo River (D/S) and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 1540 hours | Invoice Order | Not applicable | Not applicable
259 | 02/005/09 | Caparo River (U/S) and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 320 hours | Invoice Order | Not applicable | Not applicable
260 | 02/005/09 | Honda River & Bi-Furcation System | 70171800 | 2024-01-23 | 2024-03-23 | 320 hours | Invoice Order | Not applicable | Not applicable
261 | 02/005/09 | Clarke River and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 240 hours | Invoice Order | Not applicable | Not applicable
262 | 02/005/09 | Bull Bull River & Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
263 | 02/005/09 | La Cuesa River | 70171800 | 2024-01-23 | 2024-03-23 | 700 hours | Invoice Order | Not applicable | Not applicable
264 | 02/005/09 | Chandanagore River & Tributary | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
265 | 02/005/09 | Diana River (Downstream) | 70171800 | 2024-01-23 | 2024-03-23 | 50 hours | Invoice Order | Not applicable | Not applicable
266 | 02/005/09 | Diana River | 70171800 | 2024-01-23 | 2024-03-23 | 840 hours | Invoice Order | Not applicable | Not applicable
267 | 02/005/09 | Spring Vale Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
268 | 02/005/09 | Esparanza Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
269 | 02/005/09 | Waterloo High School Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 460 hours | Invoice Order | Not applicable | Not applicable
270 | 02/005/09 | Waterloo Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 280 hours | Invoice Order | Not applicable | Not applicable
271 | 02/005/09 | Calcutta #2 Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 280 hours | Invoice Order | Not applicable | Not applicable
272 | 02/005/09 | Ablack Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 180 hours | Invoice Order | Not applicable | Not applicable
273 | 02/005/09 | Perseverance Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 120 hours | Invoice Order | Not applicable | Not applicable
274 | 02/005/09 | Tributary to Pranz Gardens | 70171800 | 2024-01-23 | 2024-03-23 | 140 hours | Invoice Order | Not applicable | Not applicable
275 | 02/005/09 | Guayamare Compound and Irrigation drains | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
276 | 02/005/09 | Melvin Canal and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 320 hours | Invoice Order | Not applicable | Not applicable
277 | 02/005/09 | G.S.B Canal & D1 Irrigation Drain | 70171800 | 2024-01-23 | 2024-03-23 | 240 hours | Invoice Order | Not applicable | Not applicable
278 | 02/005/09 | Mc Lellan Drain | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
279 | 02/005/09 | Lallan River | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
280 | 02/005/09 | Marchine River | 70171800 | 2024-01-23 | 2024-03-23 | 500 hours | Invoice Order | Not applicable | Not applicable
281 | 02/005/09 | Felicity Pumpsite Collector Drains | 70171800 | 2024-01-23 | 2024-03-23 | 240 hours | Invoice Order | Not applicable | Not applicable
282 | 02/005/09 | Guru Persad Drain and Detention Ponds #1 & #2, | 70171800 | 2024-01-23 | 2024-03-23 | 320 hours | Invoice Order | Not applicable | Not applicable
283 | 02/005/09 | Lukhur Drain | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
284 | 02/005/09 | Cunupia River | 70171800 | 2024-01-23 | 2024-03-23 | 800 hours | Invoice Order | Not applicable | Not applicable
285 | 02/005/09 | Boycato Outfall Drain | 70171800 | 2024-01-23 | 2024-03-23 | 140 hours | Invoice Order | Not applicable | Not applicable
286 | 02/005/09 | Saroop Outfall | 70171800 | 2024-01-23 | 2024-03-23 | 100 hours | Invoice Order | Not applicable | Not applicable
287 | 02/005/09 | Campo Main Drain & Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 320 hours | Invoice Order | Not applicable | Not applicable
288 | 02/005/09 | Econo Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
289 | 02/005/09 | Agriculture Main Drain and Tributaries | 70171800 | 2024-01-23 | 2024-03-23 | 240 hours | Invoice Order | Not applicable | Not applicable
290 | 02/005/09 | Balfour Main Drain & Tribs | 70171800 | 2024-01-23 | 2024-03-23 | 240 hours | Invoice Order | Not applicable | Not applicable
291 | 02/005/09 | Tributary to Balfour Main Drain | 70171800 | 2024-01-23 | 2024-03-23 | 240 hours | Invoice Order | Not applicable | Not applicable
292 | 02/005/09 | Caroni River Embankment | 70171800 | 2024-01-23 | 2024-03-23 | 180 hours | Invoice Order | Not applicable | Not applicable
293 | 02/005/09 | Tributary to Caroni River | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
294 | 02/005/09 | Caroni River Embankment | 70171800 | 2024-01-23 | 2024-03-23 | 80 hours | Invoice Order | Not applicable | Not applicable
295 | 02/005/09 | San Juan River | 70171800 | 2024-01-23 | 2024-03-23 | 300 hours | Invoice Order | Not applicable | Not applicable
296 | 02/005/09 | Aranguez Road East and West | 70171800 | 2024-01-23 | 2024-03-23 | 240 hours | Invoice Order | Not applicable | Not applicable
297 | 02/005/09 | Collector drain Aranguez South | 70171800 | 2024-01-23 | 2024-03-23 | 160 hours | Invoice Order | Not applicable | Not applicable
298 | 02/005/09 | St. Joseph River | 70171800 | 2024-01-23 | 2024-03-23 | 480 hours | Invoice Order | Not applicable | Not applicable
299 | 02/005/09 | Tacarigua River | 70171800 | 2024-01-23 | 2024-03-23 | 400 hours | Invoice Order | Not applicable | Not applicable
300 | 02/005/09 | Sadoo Trace Ext Outfall Drain | 70171800 | 2024-01-23 | 2024-03-23 | 200 hours | Invoice Order | Not applicable | Not applicable
301 | 02/005/09 | Tributary to Barataria Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
302 | 02/005/09 | Tributary to Diana River (U/S & D/S) | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
303 | 02/005/09 | Chin Johnson Oufall Drain | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
304 | 02/005/09 | Pranz Garden Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
305 | 02/005/09 | Mc. Bean Main Drain #1 | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
306 | 02/005/09 | Mc. Bean Main Drain #2 | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
307 | 02/005/09 | Mc. Bean Main Drain #3 | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
308 | 02/005/09 | Exchange Main Drain, McBean to Perseverance Road | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
309 | 02/005/09 | Orange Valley Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
310 | 02/005/09 | Preysal River | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
311 | 02/005/09 | Upper Carapichaima River | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
312 | 02/005/09 | Guayamare River New Cut (Upstream) | 70171800 | 2024-03-23 | 2024-06-23 | 320 hours | Invoice Order | Not applicable | Not applicable
313 | 02/005/09 | Warren Main Drain and Trib. | 70171800 | 2024-03-23 | 2024-06-23 | 400 hours | Invoice Order | Not applicable | Not applicable
314 | 02/005/09 | Endeavour Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 320 hours | Invoice Order | Not applicable | Not applicable
315 | 02/005/09 | Latchu Main Drain & Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
316 | 02/005/09 | Felicity Outfall Drains | 70171800 | 2024-03-23 | 2024-06-23 | 400 hours | Invoice Order | Not applicable | Not applicable
317 | 02/005/09 | Borough Drain & Tributaries and Detention Pond #3 | 70171800 | 2024-03-23 | 2024-06-23 | 400 hours | Invoice Order | Not applicable | Not applicable
318 | 02/005/09 | Coolie Canal | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
319 | 02/005/09 | Bovel Canal | 70171800 | 2024-03-23 | 2024-06-23 | 820 hours | Invoice Order | Not applicable | Not applicable
320 | 02/005/09 | Munroe Road Outfall Drains | 70171800 | 2024-03-23 | 2024-06-23 | 320 hours | Invoice Order | Not applicable | Not applicable
321 | 02/005/09 | Warrenville Main Outfall Drain | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
322 | 02/005/09 | Guayamare Compound and Irrigation drains | 70171800 | 2024-03-23 | 2024-06-23 | 400 hours | Invoice Order | Not applicable | Not applicable
323 | 02/005/09 | Caroni River Embankment | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
324 | 02/005/09 | Palm Drive Outfall Drain | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
325 | 02/005/09 | Governer Trace Drain | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
326 | 02/005/09 | Pandora Ravine | 70171800 | 2024-03-23 | 2024-06-23 | 220 hours | Invoice Order | Not applicable | Not applicable
327 | 02/005/09 | Cascabelle Ravine | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
328 | 02/005/09 | Cunupia River (D/S) & Tribs | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
329 | 02/005/09 | Cunupia River (D/S) & Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
330 | 02/005/09 | Cunupia River (D/S) | 70171800 | 2024-03-23 | 2024-06-23 | 620 hours | Invoice Order | Not applicable | Not applicable
331 | 02/005/09 | Welcome North Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
332 | 02/005/09 | St Helena Main Drain, Downstream and Tribs. | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
333 | 02/005/09 | China Man Ravine | 70171800 | 2024-03-23 | 2024-06-23 | 180 hours | Invoice Order | Not applicable | Not applicable
334 | 02/005/09 | Madoo Singh Ravine | 70171800 | 2024-03-23 | 2024-06-23 | 280 hours | Invoice Order | Not applicable | Not applicable
335 | 02/005/09 | Skimming Drain and Tribs | 70171800 | 2024-03-23 | 2024-06-23 | 320 hours | Invoice Order | Not applicable | Not applicable
336 | 02/005/09 | La Paille Outfall Drain | 70171800 | 2024-03-23 | 2024-06-23 | 320 hours | Invoice Order | Not applicable | Not applicable
337 | 02/005/09 | Ibis Gardens Outfall drain | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
338 | 02/005/09 | Vishnu Boys Outfall | 70171800 | 2024-03-23 | 2024-06-23 | 120 hours | Invoice Order | Not applicable | Not applicable
339 | 02/005/09 | Maraj Outfall Drain | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
340 | 02/005/09 | Caroni River Airport 1,2,3,4 and Tributary | 70171800 | 2024-03-23 | 2024-06-23 | 320 hours | Invoice Order | Not applicable | Not applicable
341 | 02/005/09 | Collector Drain & Tibutary | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
342 | 02/005/09 | Muller Canal West | 70171800 | 2024-03-23 | 2024-06-23 | 120 hours | Invoice Order | Not applicable | Not applicable
343 | 02/005/09 | Muller Canal East | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
344 | 02/005/09 | T&TEC Substation Outfall Drains | 70171800 | 2024-03-23 | 2024-06-23 | 120 hours | Invoice Order | Not applicable | Not applicable
345 | 02/005/09 | Caparo River (D/S) and Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 440 hours | Invoice Order | Not applicable | Not applicable
346 | 02/005/09 | Welcome North Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 300 hours | Invoice Order | Not applicable | Not applicable
347 | 02/005/09 | Mt Moriah Outfall and Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 280 hours | Invoice Order | Not applicable | Not applicable
348 | 02/005/09 | Macaulay Main Drain | 70171800 | 2024-03-23 | 2024-06-23 | 200 hours | Invoice Order | Not applicable | Not applicable
349 | 02/005/09 | Sonny Ladoo Main Drain & Tributaries | 70171800 | 2024-03-23 | 2024-06-23 | 160 hours | Invoice Order | Not applicable | Not applicable
350 | 02/005/09 | Diana River | 70171800 | 2024-03-23 | 2024-06-23 | 80 hours | Invoice Order | Not applicable | Not applicable
351 | 02/005/09 | U.T.T Drain | 70171800 | 2024-03-23 | 2024-06-23 | 240 hours | Invoice Order | Not applicable | Not applicable
352 | 02/005/09 | Honda River | 70171800 | 2024-03-23 | 2024-06-23 | 320 hours | Invoice Order | Not applicable | Not applicable
353 | 02/005/09 | Factory Road Drain | 70171800 | 2024-03-23 | 2024-06-23 | 120 hours | Invoice Order | Not applicable | Not applicable
354 | 02/005/09 | Tributary to Exchange Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 100 hours | Invoice Order | Not applicable | Not applicable
355 | 02/005/09 | Carapichaima Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 360 hours | Invoice Order | Not applicable | Not applicable
356 | 02/005/09 | Guayamare River New Cut | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
357 | 02/005/09 | Guayamare River (Upstream) | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
358 | 02/005/09 | Guayamare River Old Cut (Upstream) | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
359 | 02/005/09 | Guayamare River Old Cut | 70171800 | 2024-06-23 | 2024-09-23 | 320 hours | Invoice Order | Not applicable | Not applicable
360 | 02/005/09 | Ramlal Trace Main Drain and Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
361 | 02/005/09 | Genspec Drain | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
362 | 02/005/09 | Bridal Road Outfall Drain | 70171800 | 2024-06-23 | 2024-09-23 | 280 hours | Invoice Order | Not applicable | Not applicable
363 | 02/005/09 | Guayamare Compound and Irrigation drains | 70171800 | 2024-06-23 | 2024-09-23 | 400 hours | Invoice Order | Not applicable | Not applicable
364 | 02/005/09 | Harkoo Outfall and Trib. | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
365 | 02/005/09 | Manodath Outfall & Trib | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
366 | 02/005/09 | Crystal Drive Outfall and Tributary | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
367 | 02/005/09 | Tributary to Arena River | 70171800 | 2024-06-23 | 2024-09-23 | 320 hours | Invoice Order | Not applicable | Not applicable
368 | 02/005/09 | Huda Drive Outfall and Tributary | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
369 | 02/005/09 | Saphire Outfall and Trib. | 70171800 | 2024-06-23 | 2024-09-23 | 140 hours | Invoice Order | Not applicable | Not applicable
370 | 02/005/09 | Esparanza Outfall and Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 180 hours | Invoice Order | Not applicable | Not applicable
371 | 02/005/09 | Balata Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 300 hours | Invoice Order | Not applicable | Not applicable
372 | 02/005/09 | Tributaries to Balata Ravine | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
373 | 02/005/09 | El Carmen Main Drain & Tributary | 70171800 | 2024-06-23 | 2024-09-23 | 260 hours | Invoice Order | Not applicable | Not applicable
374 | 02/005/09 | Seeraj Outfall and Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 300 hours | Invoice Order | Not applicable | Not applicable
375 | 02/005/09 | Guayamare River (U/S) | 70171800 | 2024-06-23 | 2024-09-23 | 1120 hours | Invoice Order | Not applicable | Not applicable
376 | 02/005/09 | Caroni River Embankment Outfall | 70171800 | 2024-06-23 | 2024-09-23 | 320 hours | Invoice Order | Not applicable | Not applicable
377 | 02/005/09 | Caroni River Embankment | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
378 | 02/005/09 | Bamboo #1 Collector and Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
379 | 02/005/09 | Chootoo Drain | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
380 | 02/005/09 | Collector Drain | 70171800 | 2024-06-23 | 2024-09-23 | 320 hours | Invoice Order | Not applicable | Not applicable
381 | 02/005/09 | Drain #5 & #10 | 70171800 | 2024-06-23 | 2024-09-23 | 160 hours | Invoice Order | Not applicable | Not applicable
382 | 02/005/09 | Valsayn Main Drain | 70171800 | 2024-06-23 | 2024-09-23 | 80 hours | Invoice Order | Not applicable | Not applicable
383 | 02/005/09 | Collage Drain Outfall and Trib. | 70171800 | 2024-06-23 | 2024-09-23 | 80 hours | Invoice Order | Not applicable | Not applicable
384 | 02/005/09 | St. Augustine Irrigation Drains | 70171800 | 2024-06-23 | 2024-09-23 | 120 hours | Invoice Order | Not applicable | Not applicable
385 | 02/005/09 | Bi-furication Compound and Caparo Embankment | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
386 | 02/005/09 | Mandillon River | 70171800 | 2024-06-23 | 2024-09-23 | 400 hours | Invoice Order | Not applicable | Not applicable
387 | 02/005/09 | Cunupia River (D/S) | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
388 | 02/005/09 | Caroni River Embankment | 70171800 | 2024-06-23 | 2024-09-23 | 300 hours | Invoice Order | Not applicable | Not applicable
389 | 02/005/09 | UBH Southbound Bamboo #3 Outfall Drain | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
390 | 02/005/09 | Bamboo #3 Release Drain | 70171800 | 2024-06-23 | 2024-09-23 | 80 hours | Invoice Order | Not applicable | Not applicable
391 | 02/005/09 | Boundry Outfall Drain & Tributary | 70171800 | 2024-06-23 | 2024-09-23 | 140 hours | Invoice Order | Not applicable | Not applicable
392 | 02/005/09 | Powdharie River | 70171800 | 2024-06-23 | 2024-09-23 | 280 hours | Invoice Order | Not applicable | Not applicable
393 | 02/005/09 | Arena River | 70171800 | 2024-06-23 | 2024-09-23 | 380 hours | Invoice Order | Not applicable | Not applicable
394 | 02/005/09 | Soledad River and Tributarties | 70171800 | 2024-06-23 | 2024-09-23 | 440 hours | Invoice Order | Not applicable | Not applicable
395 | 02/005/09 | La Cuesa River | 70171800 | 2024-06-23 | 2024-09-23 | 200 hours | Invoice Order | Not applicable | Not applicable
396 | 02/005/09 | Beaucarro Main Drain and Tributaries | 70171800 | 2024-06-23 | 2024-09-23 | 240 hours | Invoice Order | Not applicable | Not applicable
397 | 02/005/09 | Caparo River downstream | 70171800 | 2024-06-23 | 2024-09-23 | 720 hours | Invoice Order | Not applicable | Not applicable
PSIP /CF/IDF
1 | 43/09/003/11A/001 | Caroni River Rehabilitation and Improvement Works Project - Phase II - Construction Works at New Street, Caroni; Rehabilitation Works off Trantrill Road, St. Augustine and Rock River, St. Helena. | 70171800 | 1st Quarter Fiscal 2023 (Ongoing) | 2025-09-17 | 3 years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
2 | 43/09/003/11A/003 | Flood Reduction Works at Marie Dulay and Guaracara River - Construction and Rehabilitation Works to prevent erosion and flooding and health hazards in the Gasparillo area | 70171803 | 2nd Quarter Fiscal 2023 (Procuring) | 2026-09-17 | 3 years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
3 | 43/09/003/11A/003 | Irrigation & Drainage Structures in Caroni Irrigation Area (Phase III) - Rehabilitation works to Drainage Structures in Caroni Irrigation Area: Bamboo #1 and #2; Guayamare River to mitigate flooding | 70171803 | Fiscal 2022 (Ongoing) | 2025-09-17 | 3 years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
4 | 701/43/001/11A/ 003 701/43/003/11A/ 011 | The execution of Structural Measures inclusive of works in the following areas: Caroni, North Oropouche and South Oropouche. These projects were designed in Component 2 of the Technical Grant from CAF. Also the land acquisition component of this programme would be initiated. | 72141205 | Pending CAF Loan Agreement, the expected date to be determined | 2025-09-17 | 3 years | Open Tendering through procurement agency or internal procurement unit | 10 working days | FIDIC Suite
1 | 701/43/003/11A/ 005 | Reinforced Concrete Invert Rehabilitation- St. Ann’s River proceeding upstream from bridge on lady young to bridge of cascade road - 0.00 to 516m | 72141205 | Fiscal 2022 (Ongoing) | 2024-04-30 | 2 Years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
2 | 701/43/003/11A/ 005 | Construction of Reinforced Concrete Wall 2.4m (H) x 5m (L), Revetment Wall Repair, Rubble Masonry Wall Underpinning & Invert Rehabilitation - Maraval River. Pinhurst Park to Fens Furniture. Ch. 804m to 1291m (Phase I) | 72141205 | Fiscal 2022 (Completed) | 2023-05-26 | 2 Years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
3 | 701/43/003/11A/ 005 | Reinforced Concrete Invert Rehabilitation -Diego Martin River from bridge on Wendy Fitzwilliam Blvd. proceeding upstream - 528.5m | 72141205 | Fiscal 2022 (Completed) | 2023-06-24 | 2 Years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
4 | 701/43/003/11A/ 005 | Reinforced Concrete Invert Rehabilitation - St. Ann’s River proceeding upstream from bridge on lady young to bridge of cascade road - 516 to 595m | 72141205 | Fiscal 2022 (Ongoing) | 2024-04-30 | 2 Years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
5 | 701/43/003/11A/ 005 | Construction of Reinforced Concrete Wall 2.4m (H) x 18m (L), Reinforced Concrete Cross Wall 1m (W) x 1.5m (H) x 1.5m (L), Rubble Masonry Wall 2.4m (H) x 16m (L) & Invert Rehabilitation - Maraval Rive, Bridge at Simpson Drive to Pinehurst Park. Ch. 0.00m to 804m (Phase II) | 72141205 | Fiscal 2022 (Completed) | 2023-05-26 | 2 Years | Open Tendering through procurement agency (NIDCO) | 10 working days | FIDIC Red Book
1 | 701/43/003/11A/007 | Construction of a R.C Wall at LP#41 Santa Cruz Old Road, San Juan. | 72141205 | Fiscal 2023 (Completed) | 2023-08-31 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
2 | 701/43/003/11A/007 | Construction of a R.C Wall along Laventille Road, San Juan. | 72141205 | Fiscal 2023 (Completed) | 2023-08-18 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
3 | 701/43/003/11A/007 | Construction of a R.C Wall along the San Juan River at Hidden Orchards, Santa Cruz. | 72141205 | Fiscal 2023 (Completed) | 2023-08-21 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
4 | 701/43/003/11A/007 | Construction of a U-Section along Dyette Main -Jerningham Railway Rd, Cunupia Rd to Jerningham Railway Rd | 72141205 | Fiscal 2023 (Ongoing) | 2024-08-31 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
5 | 701/43/003/11A/007 | Rehabilitation Works Along Malick River, Eastern Main Road, Barataria | 72141205 | Fiscal 2023 (Ongoing) | 2024-08-31 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
6 | 701/43/003/11A/007 | Rehabilitation Works Along La Horquette River, Carenage | 72141205 | Fiscal 2023 (Completed) | 2023-07-24 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
7 | 701/43/003/11A/007 | Construction of a R.C Wall along Maraval River, Simpson Drive | 72141205 | Fiscal 2023 (Completed) | 2023-07-23 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
8 | 701/43/003/11A/007 | Construction of Gabion Basket Walls Along Maraval River, St. Andrews Golf Course | 70171706 | Fiscal 2023 (Completed) | 2023-08-21 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
9 | 701/43/003/11A/007 | Construction of a R.C Wall at La Pastora Gardens, Santa Cruz | 72141205 | Fiscal 2023 (Completed) | 2023-08-31 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
10 | 701/43/003/11A/007 | Bank Rehabilitation along Powdharie River, Balmain, Couva | 72141205 | Fiscal 2023 (Ongoing) | 2025-08-31 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
11 | 701/43/003/11A/007 | Construction of Gabion Basket Walls along the Matelot River, Matelot Community College, Paria Main Road | 70171706 | Fiscal 2023 (Ongoing) | 2025-07-31 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
12 | 701/43/003/11A/007 | Rehabilitation to Petit Valley Ravine adjacent to La Burnham Villas, Petit Valley | 72141205 | Fiscal 2023 (Completed) | 2023-08-03 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
13 | 701/43/003/11A/007 | Rehabilitation Works to Cunupia River at #263 Southern Main Road, Cunupia | 72141205 | Fiscal 2023 (Ongoing) | 2024-06-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
14 | 701/43/003/11A/007 | Rehabilitation Works to San Juan River, Sundarsingh Drive, Aranguez, San Juan | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
15 | 701/43/003/11A/007 | Construction of a R.C U-Section at #1 St. Michael Village, Las Cuevas | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
16 | 701/43/003/11A/007 | Construction of Reinforced Concrete Wall along Arima River in the vicinity of Buena Vista | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
17 | 701/43/003/11A/007 | Rehabilitation Works Along the Tunapuna River., in the vicinity of Jorden, Terrace Tunapuna | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
18 | 701/43/003/11A/007 | Rehabilitation Works along the St. Joseph River - in the vicinity of La Joya Administrative Complex | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
19 | 701/43/003/11A/007 | Construction of Reinforced Concrete Section at Bamboo #3 Pumpsite | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
20 | 701/43/003/11A/007 | Construction of a Reinforced Concrete U-Section at LP#52 Queen Drive, Bagatelle Road, Diego Martin | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
21 | 701/43/003/11A/007 | Tributary to Lagoon Mahout River - B 1/1 Mayaro Guayaguayare Road | 72152707 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
22 | 701/43/003/11A/007 | Oropouche River, New Colonial Road Barrackpore | 72152707 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
23 | 701/43/003/11A/007 | Redefinition of the Caroni River from the Uriah Butler Highway to the Gulf of Paria | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
24 | 701/43/003/11A/007 | Clearing and Desilting of the Diego Martin River Mouth | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
25 | 701/43/003/11A/007 | Wattley Circular, Mt, Pleasant | 72152707 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
26 | 701/43/003/11A/007 | Rehabilitation Works on the Diego Martin River from the bridge on Diego Martin Main Road | 72141205 | Fiscal 2023 (Completed) | 2023-09-06 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
27 | 701/43/003/11A/007 | Rehabilitation Works, Arima River In The Vicinity Of The Crossings, Arima. | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
28 | 701/43/003/11A/007 | Construction of R.C Wall Downstream Cipero River from Gulf View Link Road Bridge To WASA Treatment Plant | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
29 | 701/43/003/11A/007 | Construction of Reinforced Concrete Wall along Simeon Ravine, Sparrow Drive Ext. Petit Valley. | 72141205 | Fiscal 2023 (Procuring) | 2025-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
30 | 701/43/003/11A/007 | Construction of Reinforced Concrete Wall along Cunupia River, Manzana Drive | 72141205 | Fiscal 2023 (Procuring) | 2025-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
31 | 701/43/003/11A/007 | Rehabilitation works along the St. Ann’s River behind Pizza Boys for a distance of 358m long between Chainage 595 to Chainage 953 | 72141205 | Fiscal 2023 (Procuring) | 2025-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
32 | 701/43/003/11A/007 | Construction of Reinforced Concrete Wall along Guapo River/ Guapo River Road, at Guapo Village, Point Fortin | 72141205 | Fiscal 2023 (Ongoing) | 2024-07-01 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
33 | 701/43/003/11A/007 | Construction of a Reinforced Concrete Wall along the Arima River off Trisha Avenue, Mandalay Gardens, Arima. | 72141205 | Fiscal 2023 (Procuring) | 2025-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
34 | 701/43/003/11A/007 | Construction of a Reinforced Concrete Wall along Maraval River, Opposite Chaconia Home Away from Home | 72141205 | Fiscal 2023 (Procuring) | 2025-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
35 | 701/43/003/11A/007 | Clearing and Desilting of the Guaico River & Embankment from bridge on Eastern Main Road to Bridge on Foster Road, Sangre Grande. | 70171800 | Fiscal 2023 (Procuring) | 2025-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
36 | 701/43/003/11A/007 | Rehabilitation & Desilting works along Cipero River Mouth | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
37 | 701/43/003/11A/007 | Vistabella River | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
38 | 701/43/003/11A/007 | Esmeralda Main Drain / Johnathan Trace Cunupia Downstream | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
39 | 701/43/003/11A/007 | Crescent Ravine | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
40 | 701/43/003/11A/007 | Guaico River | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
41 | 701/43/003/11A/007 | Bournes Rd Ravine | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
42 | 701/43/003/11A/007 | Fernando Lane Outfall Drain /LP #6 Fernando Lane, Esmeralda Road, Cunupia | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
43 | 701/43/003/11A/007 | Construction of a Reinforced Concrete Wall along Cunapo River, Eastern Main Road, Sangre Grande - Brooklyn Settlement Sangre Grande | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
44 | 701/43/003/11A/007 | Construction of a Reinforced Concrete Wall along Aripo River, LP#58, Carib Circular, La Platta Gardens | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
45 | 701/43/003/11A/007 | Valencia River Phase 1 | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
46 | 701/43/003/11A/007 | Construction of Reinforced Concrete Retaining Wall on Nagessar Channel | 77111603 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
47 | 701/43/003/11A/007 | Construction of a Reinforced Concrete Wall along Petit Valley Ravine, D/S Morne Coco Road, Petit Valley | 77111603 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
48 | 701/43/003/11A/007 | Lallan River / from Egypt Trace to Jerningham Railway Road, Endeavour | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
49 | 701/43/003/11A/007 | Williamsville Phase I (Reia Dass) | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
50 | 701/43/003/11A/007 | La Cuesa River / Alongside Northbound Ramp, Freeport Underpass heading Downstream | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
51 | 701/43/003/11A/007 | Williamsville Phase II (Coconut Drive) | 72152707 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
52 | 701/43/003/11A/007 | Construction of Reinforced Concrete Wall at Michael Lewis, Arena River | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
53 | 701/43/003/11A/007 | Construction of Reinforced Concrete Wall along Mausica River in the Vicinity of the Basketball Court on Mendez Trace, Arima. | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
54 | 701/43/003/11A/007 | Rehabilitation Works along Arima River downstream of the Churchill Roosevelt Highway | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
55 | 701/43/003/11A/007 | Construction of Reinforced Concrete Wall Off Ramdularie Lane, Southern Main Road, Cunupia | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
56 | 701/43/003/11A/007 | Construction of a Reinforced Concrete Wall along the San Juan River, Saddle Road, Lower Santa Cruz | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book
57 | 701/43/003/11A/007 | Construction Of A Reinforced Concrete Wall Along San Juan River, E.P. #53 Saddle Road, San Juan | 72141205 | 1st Quarter of Fiscal 2024 | 2026-09-30 | 2 Years | Open Tendering through procurement agency (NIPDEC) | 10 working days | FIDIC Red Book

## EHSU
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Environment, Health & Safety Unit
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 1/2/55 | Supply and delivery of uniforms | Shirts and Polos with EHSU Logo | 53102700 | 2023-10-01 | 2023-11-01 | 30 days | Three quote system | Not applicable | Not applicable
2 | 1/2/59 | Purchase stationery | Toners, Paper, Pens Etc. | 44120000 | 2024-03-01 | 2024-04-01 | 30 days | Three quote system | Not applicable | Not applicable
3 | 1/4/21 | Repair to Equipment | Servicing of Printer | 81112306 | 2023-12-01 | 2024-02-01 | 60 days | Single Source Selection | Not applicable | Not applicable
4 | 1/4/21 | Purchase of Office equipment | Purchase of printer/ copier, 16 keyboards and 16 mouse | 44120000 | 2024-03-01 | 2024-05-01 | 60 days | Three quote system | Not applicable | Not applicable
5 | 1/2/55 | Purchase of Minor Equipment | Purchase of one desk printer and 16 desktop computers | 44100000 | 2024-01-01 | 2024-03-01 | 60 days | Three quote system | Not applicable | Not applicable
6 | 1/4/20 | Purchases for Maintence of Vehicles for PDD5582 | Supply of battery(825 Amps), 8 gallons oil, 4 oil filters, 4 air filters, 4 diesel filters, 4 cabin filters, 1 gallon coolant, 3 wiper blade (front and back) , 4 tyres, 1 set mats, 12 air freshners and Suspension parts (As required) | 78181500 | 2023-12-01 | 2024-01-01 | 30 days | Three quote system | Not applicable | Not applicable
7 | 1/4/21 | Purchase of Furniture and Furnishings | Supply and Delivery of 6 ergonomically designed chairs and 3 four drawer cabinet, a Refridgerator, Microwave and 2 kettles | 56101720 | 2023-12-01 | 2024-01-01 | 31 days | Three quote system | Not applicable | Not applicable
8 | 1/4/21 | Attendance to Conference and HSE Training | Attendance to HSE Conference and training | 86100000 | 2023-10-01 | 2023-10-01 | 30 days | Single Source Selection | Not applicable | Not applicable
9 | 1/4/21 | Printing Materials | HSE Brochures and Posters for Offices | 82121500 | 2023-11-01 | 2024-01-01 | 90 days | Three quote system | Not applicable | Not applicable
10 | 1/4/21 | Purchase of First Aid Equipment | Purchase of 3 x 25 persons first aid kits | 56121200 | 2024-01-01 | 2024-02-01 | 30 days | Three quote system | Not applicable | Not applicable
11 | 2/16/56 | Purchase of sanitisation chemical | Purchase of 10 gallons sanitization chemical | 42281700 | 2023-10-01 | 2023-11-01 | 30 days | Three quote system | Not applicable | Not applicable
6 | 43:02/009/17 Training | Training courses | Amdam Coference in Exhibition | 86100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Minimum 3 quote system used through RFQs | Not applicable | Minimum 3 quote system used through RFQs

## General Admini (GA)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
General Administration G.A. ( Accounts, I.T., Facilities Management, Legal, H.R., Communications, Transport Board, CTO, Internal Audit, Estate police, D.P.S. & P.S. Secretariat)
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill Period (If applicable)- No. of days | Contract Type
RECURRENT EXPENDITURE
Information Technology Unit
1 | Ref# 2/7/2 | Renewal of Forticlient EMS Subscription | Anti-Virus software used to access the corporate network at Head Office, Maritime Services, Licensing Division and TSTT Datacentre. | 81111800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 yr | Limited Bidding | 10 working days | Fixed Term Contract
2 | Ref# 2/7/2 | Renewal of Wireless Access Points at Head Office | Upgrades to the firewall is necessary to avoid security risk to the corporate network. | 81111801 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 yr | Limited Bidding | 10 working days | Fixed Term Contract
3 | Ref# 2/7/2 | Acquisition of 2 Forticlient 600E Firewall Redundant Power supply |  | 81111801 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
4 | Ref# 2/7/2 | Upgrade of digitisation Hyper-Converged Infrastructure at Head Office |  | 81111500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 yr | Limited Bidding | 10 working days | Fixed Term Contract
5 | Ref# 2/7/2 | Acquisition of Datacentre Resources for MOWT Services to the Public | Acquisition of modern ICT to enable the digitisation projects. | 81111500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 yr | Limited Bidding | 10 working days | Fixed Term Contract
6 | Ref# 2/7/2 | Acquisition of computer systems and hardware for | This project is aimed at transforming physical files into digital records. | 81112300 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 yr | Limited Bidding | 10 working days | Fixed Term Contract
7 | Ref# 2/7/2 | UTURN Change Request |  | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Single Source Selection | Not applicable | Fixed Term Contract
8 | Ref# 2/7/2 | UTURN Software SLA | Preventative Maintenance - on-site support, corrective maintenance license. | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Single Source Selection | Not applicable | Fixed Term Contract
9 | Ref# 2/7/2 | Upgrade Electronic Vehicle Inspection System (EVIS) | To facilitate Examiner Renewal and Enforcement, Examiner Suspension, Proprietor Renewal Enforcement, Proprietor Suspensions, Improve Audit Reporting, Improve Dashboard, Display List of Proprietors conducting Inspections and Printable Digitally Signed Examiner and Proprietor Certificates and voiding of stickers | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Single Source Selection | Not applicable | Fixed Term Contract
10 | Ref# 2/2/6 | Online Appointment and Queue Management System |  | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Single Source Selection | Not applicable | Fixed Term Contract
11 | Ref# 2/2/6 | Online Provisional Permit System (OPPS) | To provide Online Appointment System, Form redirect, OPPS Reviewer Unlock option, OPPS Approval screen, OPPS Archival feature and allow for OAS Validation ID settings for the Licensing Division | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Single Source Selection | Not applicable | Fixed Term Contract
12 | Ref# 3/1/2 | Vehicle Transfer |  | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Single Source Selection | Not applicable | Fixed Term Contract
13 | Ref# 3/1/2 | Enterprise Content Document Management System |  | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Single Source Selection | Not applicable | Fixed Term Contract
14 | Ref# 2/7/2 | Network Equipment |  | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Limited Bidding | 10 working days | Fixed Term Contract
15 | Ref# 2/2/5 | Software Purchases |  | 43231500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1yr | Limited Bidding | 10 working days | Fixed Term Contract
Facilities Management Unit
1 | XXXX | Routine Maintenance Services at the Head Office Building | Provision of routine maintenance services | 72101500 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Annual | Open Tendering | 10 working days | Fixed Term Contract
2 | XXXX | Provision of Janitorial Services | Supply of Janitorial Services for Head Office, DAO's, Traffic Warden & Licensing | 76110000 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Annual | Open Tendering | 10 working days | Fixed Term Contract
3 | XXXX | Provision of Security Services | Supply of Security Services for Head Office & Other Ministry Buildings | 92120000 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Annual | Open Tendering | 10 working days | Fixed Term Contract
4 | XXXX | Lift Maintenance | Maintenance & Repairs of Elevators to Main Office. Specialist service company required. | 72101500 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Annual | Limited Bidding | 10 working days | Fixed Term Contract
5 | XXXX | Entrance Door Maintenance | Maintenance Works to Automatic Sliding Entrance Door & Shutter Type Basement Gate | 72101500 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Annual | Limited Bidding | 10 working days | Fixed Term Contract
6 | XXXX | Technical Services - Electrical & Plumbing | Maintenance & Repairs of any electrical and plumbing works to Main Office | 72101500 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Annual | Open Tendering | 10 working days | Fixed Term Contract
7 | XXXX | Fire Alarm Notification System | Annual Inspection of Fire Notification System | 72101500 | 3rd Quarter Fiscal 2024 | 2024-08-01 | Annual | Limited Bidding | 10 working days | Fixed Term Contract
8 | XXXX | Maintenance of Chill Water System | Service Contract for Maintenance Work. | 72101500 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Quarterly | Open Tendering | 10 working days | Fixed Term Contract
9 | XXXX | Maintenance of Generator | Annual servicing of Generator completed by Mechanical Department. Materials required will be procured. | 72101500 | 3rd Quarter Fiscal 2024 | 2024-08-01 | Once a year | Open Tendering | 10 working days | Fixed Term Contract
10 | XXXX | Fire Suppression Maintenance | Semi-Annual Inspection of all Fire Extinguishers. | 72101500 | 2nd Quarter Fiscal 2024 | 2024-07-01 | Every 6 months | Open Tendering | 10 working days | Fixed Term Contract
11 | XXXX | Re-location of FMU Department | Renovation works to spaces identified | 72101500 | 1st Quarter Fiscal 2024 | 2023-12-01 | Three Months | Open Tendering | 10 working days | Fixed Term Contract
12 | XXXX | Maintenance and Upgrade Works at District Administration Offices | Upgrade of DAO offices -Painting and the maintenance of light fixtures and the refurbishing or replacing of A/C Units as some are obsolete and no longer functional | 72101507 | 3rd Quarter Fiscal 2024 | 2024-09-01 | Quarterly | Open Tendering for Repairs & Supply of Matrerials | 10 working days | Fixed Term Contract
13 | XXXX | Minor Equipment Purchases | Office Equipment, furniture and furnishings, other minor equipments | 56000000 | 3rd Quarter Fiscal 2024 | 2024-08-01 | As required | Open Tendering | 10 working days | Fixed Term Contract
Chief Technical Officer
1 | XXXX | Office Stationery Supplies | Paper, paper clips, file jackets, temporary file jackets, manilla folders, steno pads, post its, glue sticks, liquid glue, 3-tiered trays, dips, pens, ink cartridges, rulers, erasers, treasury tags, stamp pad, envelopes, notebooks, ixl apex binder, binder combs, mountain tape, masking tape, scotch tape, duct tape, binder clips, bristol board, transparency film, highlighters, whiteboard markers, permanent markers, scissors, electronic calculator, Printer, fans, computers, microwave oven, mini refrigerator, office chairs, executive chairs | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Deputy Permanent Secretary Secretariat
1 | XXXX | Small /Minor Equipment and Stationery | Printer, computer, refrigerator, microwave, kettle, electric sharpener, guillotine, laminating machine, heavy duty staple machine, office chairs, copy paper, envelopes, pens, glue, staple removers, paper punch, staple machine, liquid paper, highlighters, markers, rulers, folders, scissors, steno pads, note books, labels, post its, lysol spray, sanitiser, napkins, hands soap, dish washing soap, stamps, rotary stamp holder | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Corporate Communication
1 | XXXX | Small /Minor Equipment and Stationery | Notepads (small and large), AAA Batteries, AA Batteries, Highlighters, Pens, Pencils, Post its, Masking Tape, Scotch Tape, White Letter Size Envelopes, White Board, White Board Markers, Puncher, Notebooks, Attendance Register,Copy Paper, Temporary File Jacket, File Jackets, Fans, Ergonomic Office Chairs, L-Shape Office Desk, Kettle, Microwave, Mini Fridge, Electric Sharpener, Coffee Maker, Milo, Teas, Water, Milk, Sugar/Condensed Milk, Sanitary Coffee Cups, Dishwashing liquid, Lysol Spray, Hand Sanitizers, Napkins, Telephone Cleaner, Desk Organizers, Voice Recorder, Table Cloths, Umbrellas, Three tier books shelf with Cabinet | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Transport Board
1 | XXXX | Small /Minor Equipment and Stationery | Paper, paper clips, file jackets, temporary file jackets, manilla folders, steno pads, post its, glue sticks, liquid glue, 3-tiered trays, dips, pens, ink cartridges, rulers, erasers, treasury tags, stamp pad, envelopes, notebooks, ixl apex binder, binder combs, mountain tape, masking tape, scotch tape, duct tape, binder clips, bristol board, transparency film, highlighters, whiteboard markers, permanent markers, scissors, electronic calculator, Printer, fans, computers, microwave oven, mini refrigerator, office chairs, executive chairs | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Supplemental Police Unit
1 | XXXX | Minor Equipment and Stationery | Printer, Microwave, Executive Chairs, Station diaries, Pocket diaries, Attendance registers, correspondence logs, uniforms, glue sticks, notebooks, file jackets, envelopes, printing papers, batteries, pens, pencils, erasers, notebooks, flashlights, staples, inks, filing cabinets, stamps. | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Interal Audit
1 | XXXX | Minor Equipment and Stationery | office stationary, reflective vest, rolloing measuring wheels, fans, tier dips, desk calculators, measuring tapes | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Computerization
1 | XXXX | Small /Minor Equipment and Stationery | Paper, Electric Sharpener, Toners, Treasury Tags, Staplers, Pencils, Pens, Paperclips, Manila Files, Clear tape, Glue Sticks, Highlighters, Rubber Bands, Markers, Liquid paper, erasers, file jackets, pens, Post its, Printer, Microwave, Calculators, adding machines, standing fans, heavy duty fan, filing cabinets, Ergonomic Chairs, Laptops, Wall Clock, Maintenance Kits, Staples, Work Desks, Desktop Computers, Table, phones, Paper punches, notebooks, kettle, telephone cleaners, first aid Kits | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Human Resource Department
1 | XXXX | Training in various engineering and technical fields | Continuous supply of training services for various technical programmes | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
2 | XXXX | Workshops in Alternative Dispute Resolution and Conflict Management | Conducting workshops in Alternative Dispute Resolution | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
3 | XXXX | Labour Studies and Industrial Relations Training | Conducting training in Labour Studies and Industrial Relations | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
4 | XXXX | Executive workshops in Leadership and Management | Conducting workshops in Leadership and Management for Managers and Directors | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
5 | XXXX | Fundamentals of Building Codes Training | Training in understanding the Fundamentals of developing/identifying Building Codes | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
6 | XXXX | Maintenance of Civil Engineering Structures | Maintenance of Civil Engineering Structures | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | SOLE SELECT | Not applicable | Not applicable
7 | XXXX | FIDIC Contract Management Training | Training in principles of FIDIC Contract Management | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
8 | XXXX | Coastal Navigation Training | Conducting training in Coastal Navigation | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | SOLE SELECT | Not applicable | Not applicable
9 | XXXX | Training in various project management procedures | Provide training in various project management disciplines | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
10 | XXXX | Provision of Books and Periodicals | Provision of Books and Periodicals to serve as reference for key technical and administrative matters of the Ministry | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
11 | XXXX | Workshops in Stress, Time Management, Emotional Intelligence, Ethics, Diversity, Interpersonal Communications and Work-Life Balance | Providing training in Stress, Time Management and Work-Life Balance to enhance the quality of the staff's personal lives | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
12 | XXXX | Training in various types of counselling | Training HR Officers and Managers in understanding the tenants of employee counselling | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
13 | XXXX | Training in Business Process Re-Engineering | Training Managers, Senior Technical and Administrative Officers in understanding the tenants of business process re-engineering | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
14 | XXXX | Training in various report writing | Conduct Training in technical report writing, incident report writing and business report writing | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
15 | XXXX | Employee Assistance Programme | Provide Employee Assitance and Counselling services to employees of the Ministry of Works and Transport | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
16 | XXXX | Various Training for the Maritime Services Division | Conduct training in key technical areas for the Maritime Services Division | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
17 | XXXX | Various Training for the Maritime Services Division | Conduct training in key technical areas for the Transport Division | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | SOLE SELECT | Not applicable | Not applicable
18 | XXXX | Training in various report writing | Conduct Training in technical report writing, incident report writing and business report writing | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
19 | XXXX | Management of Bids, Negotiations and Contracts | To conduct training in the art of contract negotiations and bidding | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
20 | XXXX | Business Communications and Presentation Skills | Training in business communication and presentation skills for managers and senior officers | 86100000 | 2024-01-08 | 2024-09-27 | Duration of Training TBD with service provider | Request for Quotation | Not applicable | Invoice/ Quotation
21 | XXXX | Minor Equipment and Stationery | Paper, post-its, pens, pencils, notebooks, envelopes, sticky notes, paper clips, glues, rulers, staplers, cartridges, folders, rubber bands, glues, markers, staplers, heavy duty hole duty punchers, scissors, desk organisers, staples, forwarding forms, temporary file folders, tapes, bull dog clips, printer, envelopes, stamp pads, stamp pad ink, heavy duty scanner, incoming/outgoing registers, attendance register, electric sharpener, standing fan, speakers, computers, monitors, telephones, scanners, desks, chairs, foot stools, tables, erasers, thumbtacks, plastic dips, stamps, air fresheners, large pendaflex, desk cleaner, treasury tags, 3 hole puncher, toners, webcam, correction fluid thinners, notebooks, legal pads, 3-in-1 copy/scanner/printer, whiteboard markers, whiteboard, guillotine, bindr cases, toner kits, steno pads, letter openers, boxes. | 44120000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Legal Unit
1 | XXXX | Fees | Law Texts and Legal Subscriptions | 14111800 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
2 | XXXX | Fees | Litigation Fees: Retention of External Counsel | 80122000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
3 | XXXX | Fees | Title Searches and Title Opinions | 80122000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
4 | XXXX | Fees | Miscellaneous Expenses: Postage, Service of legal process fees, Commissioner of Affidavits fees | 80122000 | 2024-07-01 | 2024-09-01 | Annual | Request for Quotation | Not applicable | Invoice/ Quotation
Note on I60: Akido Ford

## Highways
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Highways Division
No. | Project Number | Project Name | Brief Description | UNSPEC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill Period (If applicable)- No. of days | Contract Type
RECURRENT EXPENDITURE
2 | 02/002/08 | Rent/Lease Office Accomodation and Storage | Rental of Office Space | 80131500 | 2023-11-01 | 2024-01-01 | 90 days | Single Source | Not applicable | Fixed Term Contract
3 | 02/002/11 | Books + Periodicals | Books, Magazines, Newspaper | 14111800 | 2023-11-01 | 2024-01-01 | 90 days | Request for Quotation | Not applicable | Invoice
4 | 02/002/17 | Training | Training for Members of Staff | 86100000 | 2023-11-01 | 2024-01-01 | 90 days | Request for Quotation | Not applicable | Invoice
5 | 02/002/43 | Security Services | Security Services Highways Compound | 92120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 year | Open Tendering | 10 working days | Fixed Term Contract
6 | 02/002/57 | Postage | Stamps | 44121500 | 2023-11-01 |  |  | Request for Quotation | Not applicable | Invoice
7 | 02/002/58 | Medical Expenses | Pharmaceutical Items | 85000000 | 2023-11-01 | 2024-01-01 | 90 days | Request for Quotation | Not applicable | Invoice
8 | 02/002/62 | Promotions | Advertisement for Highways Dept. | 55101500 | 2023-11-01 | 2024-01-01 | 90 days | Request for Quotation | Not applicable | Invoice
9 | 03/002/02 | Office Equipment | Photocopying Machine, Laptops etc | 44000000 | 2023-10-01 | 2023-11-01 | 30 days | Request for Quotation | Not applicable | Invoice
10 | 03/002/03 | Furniture and Furnishings | Chairs, Desks, Tables, Cabinets | 56000000 | 2023-11-01 | 2024-02-01 | 90 days | Request for Quotation | Not applicable | Invoice
1 | 1/2024 | Supply and Delivery of Copy Paper | Supply and Delivery of A4, Letter Size, Legal Size and Ledger Paper | 14111507 | 2023-10-23 | 2020-09-01 | 120 days | Request for Quotations | Not applicable | Invoice
2 | 2/2024 | Supply and Delivery of Ink/Toners | Ink/Toner for use in (8) District Offices | 44120000 | 2023-10-23 | 2024-02-20 | 120 days | Request for Quotations | Not applicable | Invoice
3 | 3/2024 | Supply and Delivery of Other Stationery | Supply and Delivery of Notebooks, Envelopes, File Folders, Steno Pads, Paper Clips, Staple Machines, Staples, Glue, Scissors, Paper Punch, Pencils, Pens, Carbon Paper, Correction Pens, Post It, Treasury Tags, Rulers, Bristol Board, Mouse Pads, Erasers, Self Inking Stamps. | 44120000 | 2023-10-23 | 2024-02-20 | 120 days | Request for Quotations | Not applicable | Invoice
4 | 4/2024 | Supply and Delivery of Cleaning Supplies | Supply and Delivery of Toilet Bowl Cleaner, Toilet Tissue, Soap, Dishwashing Liquid, Bleach for Sanitizing for use in (8) District Offices. | 47131800 | 2023-10-23 | 2024-02-20 | 120 days | Request for Quotations | Not applicable | Invoice
5 | 5/2024 | Provisions for Interviews | 12 Occasions per year | 80111700 | 2023-10-23 | 2024-02-20 | 120 days | Not applicable | Not applicable | Not applicable
6 | 6/2024 | Supply and Deliver of Furniture and Furnishings |  | 56000000 | 2023-10-23 | 2024-02-20 | 120 days | Request for Quotations | Not applicable | Invoice
1 | 02/002/09 | Bridge on CRH over San Juan River, immediately West of East Bound to South Bound Overpass | Desilting/Debris Removal Works Average Area under Bridge - 72m x 26m, desilting 100m US and 100m DS of bridge | 72141107 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
2 | 02/002/09 | Blackman River Crossing at CRH, immediately east of the Curepe Interchange | Desilting work, culvert cleaning and removal of debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
3 | 02/002/09 | Crossing at CRH in the vicinity of Savannah Drive | Desilting work along channel and culvert cleaning works | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
4 | 02/002/09 | Churchill Roosevelt Highway, westbound (from Aranguez Overpass Entrance to Advance Commercial Equipment Ltd) | Roadside drain cleaning work 0.75lin. m., with debris removal | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 24 days | Open Bidding | 10 working days | Fixed Term Contract
5 | 02/002/09 | Bridges over the Caroni River: along the Uriah Butler Highway, along Southern Main Road, along St. Helena Bypass Road | Vegetation control and roadside drain cleaning work, with debris removal | 72141107 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
6 | 02/002/09 | B 1/2 Valencia Road, Toco | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | 72141107 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Open Bidding | 10 working days | Fixed Term Contract
7 | 02/002/09 | B 1/40 Toco Road, Toco | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | 72141107 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Open Bidding | 10 working days | Fixed Term Contract
8 | 02/002/09 | Churchill Roosevelt Highway (eastbound from Mausica to O'Meara) | Clean and regrade 2km of earthern drain, as well as remove vegetation and debris, and cleaning of road verge. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Open Bidding | 10 working days | Fixed Term Contract
9 | 02/002/09 | Churchill Roosevelt Highway, Eastbound from the University of the West Indies to Pasea Extension) | Clean and regrade 1km of earthern drain, as well as remove vegetation and debris, and cleaning of road verge. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Open Bidding | 10 working days | Fixed Term Contract
10 | 02/002/09 | Intersection of Audrey Jeffers Highway and Western Main Road, in the vicinity of Cocorite Fishing Facility | Cleaning and desilting of roadside drain and Culvert Crossing. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 12 days | Open Bidding | 10 working days | Fixed Term Contract
11 | 02/002/09 | Priority Bus Route, eastbound from Ultimate Car Care to Republic Bank, St. Augustine. | Clearing and Removal of vegetation and debris along the box drain. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 20 days | Open Bidding | 10 working days | Fixed Term Contract
12 | 02/002/09 | B 2/20 Churchill Roosevelt Highway, Wallerfield | Desilting of the underside of bridge, with vegetation control and debris removal. | 72141107 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 24 days | Open Bidding | 10 working days | Fixed Term Contract
13 | 02/002/09 | Antigua Road, Wallerfield | Grass cutting along road verges, northbound and southbound, approximately 1.5km long. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 20 days | Open Bidding | 10 working days | Fixed Term Contract
14 | 02/002/09 | Intersection of Eastern Main Road and Priority Bus Route, in Success / Laventille Composite Secondary School. | Roadside drain cleaning work, with the cleaning of two (2) underground crossing and desilting work. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
15 | 02/002/09 | Uriah Butler Highway, southbound & northbound, from Chaguanas Flyover to Endeavour Connector Road. | Clean and regrade drain, as well as remove vegetation and debris, approximately 1.5km long. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 20 days | Open Bidding | 10 working days | Fixed Term Contract
16 | 02/002/09 | Solomon Hochoy Highway, southbound in the vicinity of Brentwood Mall, Chaguanas and northbound from Chase Village Walkover to Mid Center Mall. | Clean and regrade drain, as well as cleaning of cylinder crossing, inclusive of the removal of vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
17 | 02/002/09 | Southern Main Road, Aripero 66.5km (in the vicinity of Davey's Radiator Works) | Cleaning of underground double cylinder crossing (6.5m long x 0.60m diameter bore), inclusive of the removal of vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 10 days | Open Bidding | 10 working days | Fixed Term Contract
18 | 02/002/09 | Uriah Butler Highway 9.40 to 9.50 km Bovell Channel, Munroe Road | Clean drain between Ramlal Trace ext. to Warren Road. Clean inlet, median and outfall of Bovell channel, to remove vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
19 | 02/002/09 | Solomon Hochoy Highway, B 1/4 Chase Village Flyover, 3.55km | Cleaning of two (2) cylinder crossings, with drain cleaning (500m long), inclusive of the removal of vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
20 | 02/002/09 | Solomon Hochoy Highway, Preysal Flyover (northbound & southbound) | Culvert and catchpit cleaning, with drain cleaning, inclusive of the removal of vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
21 | 02/002/09 | Solomon Hochoy Highway between the Freeport Overpass (21.7km) and the Claxton Bay Overpass (32.5km) | Clearing and Removal of vegetation and debris along the median. Verge edging and grass cutting around the cable barriers (total distance of 21.6km) | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
22 | 02/002/09 | Uriah Butler Highway, northbound & southbound shoulders, from Caroni Flyover to Caroni River Bridge. | Clearing and Removal of vegetation and debris along the median. Verge edging and grass cutting around the cable barriers (total distance of 2km) | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Open Bidding | 10 working days | Fixed Term Contract
23 | 02/002/09 | Solomon Hochoy Highway, Harmony Hall, northbound and southbound and along Gasparillo Bypass Road to T&TEC. | Cleaning and regrading of 1km long earthen drain, inclusive of the removal of all vegetation and debris Desilting of 1m x 1m Box Culvert under highway, and 0.6m x 0.6m Crossing under Gasparillo Bypass Road, as well as catchpits. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 18 days | Open Bidding | 10 working days | Fixed Term Contract
24 | 02/002/09 | BP Compound, Galeota to Victoria East District Office, Matilda, Princes Town | Collection and transportation of Reinforcing Steel from BP compound to MOWT office, Matilda. |  | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
25 | 02/002/09 | Uriah Butler Highway, in the vicinity of John Peter Road. | Desilting of underground cylinder crossing, inclusive of the removal of all vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
26 | 02/002/09 | St. Croix Road, Lengua | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
27 | 02/002/09 | Rivulet Road, Couva | Grass cutting along road verges, westbound, approximately 5.5km long. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
28 | 02/002/09 | Southern Main Road - from Chandernagore Road, Chaguanas to Mc Bean Junction, Couva | Grass cutting along road verges, northbound and southbound, approximately 6km long. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
30 | 02/002/09 | B 1/8 Penal Rock Road, Penal | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
31 | 02/002/09 | Southern Main Road 83.550km Guapo Government School and Southern Main Road 83.70km Guapo Community Centre | Desilting of underground cylinder crossing, inclusive of the removal of all vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
32 | 02/002/09 | Southern Main Road 66.5km Vicinity of Boodoos Air conditioning, Southern Main Road 74.9km Vicinity of M.P's Office and Southern Main Road 74.7km Vicinity of Jackie's Main Road La Brea | Desilting of underground cylinder crossing, and covered box drain, inclusive of the removal of all vegetation and debris. | 72141205 | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
33 | 02/002/09 | Rental of mechanical equipment | excavator, backhoe, hiab, skid steer, gully sucker | 72141205 | N/A, approval is being sought | 4th Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
34 | 02/002/09 | Rental of mechanical equipment | dump truck, crew cab truck | 72141205 | N/A, approval is being sought | 4th Quarter of Fiscal 2024 | 15 days | Open Bidding | 10 working days | Fixed Term Contract
1 | 02/002/28 | Remedial works to B 1/26 Churchill Roosevelt Highway W/B, Arima | Construction of R.C. Retaining Wall, Channel Lining works and Road restoration works. | 72141107 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
2 | 02/002/28 | Scour Protection Works at B 1/16 Priority Bus Route (PBR), Macoya | Channel Lining works | 72141107 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
4 | 02/002/28 | Conditional and Performance Based Assessment and Recommendations for Repair Methods for O 1/1 Western Main Road (St. James Overpass)” | To engage a professional engineering firm to provide engineering solutions for the structural repairs to B 1/6 Mayaro Guayaguayare Road, Mayaro. | 81101500 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
5 | 02/002/28 | Scour protection works at B 2/1 Corosal Road, Brasso, 0.21km mark | Construction of R.C. Retaining Wall, Channel Lining works and Road restoration works. | 72141107 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
6 | 02/002/28 | Scour Protection works at B 2/1 Garth Road, Williamsville, 0.80km mark | Construction of R.C. Channel lining, Desilting of watercourse and Road Restoration works. | 72141107 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
7 | 02/002/28 | Provision of Structural Repairs to B 1/6 Mayaro Guayaguayare Road, Mayaro | To engage a professional engineering firm to provide engineering solutions for the structural repairs to B 1/6 Mayaro Guayaguayare Road, Mayaro. | 81101500 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
8 | 02/002/28 | Rehabilitation works to B 1/1 Mausica Road, Arima | Repairs to bridge structure and Road works. | 72141107 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
9 | 02/002/28 | Emergency Scour Protection works at B 1/38 EMR, Valencia. | Construction of R.C. Channel Lining, Desilting of the watercourse | 72141107 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
6 | 02/002/28 | Emergency Scour Protection works at B 2/20 Cumuto Main Road, Coryal | Construction of R.C. Channel Lining, Desilting of the watercourse | 72141107 | 2023-09-01 | 2024-02-01 | 45 days | Open Bidding | 10 working days | Fixed Term Contract
7 | 02/002/28 | Reconstruction of B 2/1 Vega de Oropouche Road, Sangre Grande | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 72141107 | 2023-09-01 | 2024-04-01 | 60 days | Open Bidding | 10 working days | Fixed Term Contract
8 | 02/002/28 | Reconstruction of B 2/6 Oropouche Road, Sangre Grande | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 72141107 | 2023-09-01 | 2024-04-01 | 60 days | Open Bidding | 10 working days | Fixed Term Contract
9 | 02/002/28 | Handrail Replacement Programme Phase 3 | Replacement of damaged, broken or missing handrails, repainting of Headwalls and existing handrails and vegetation control. | 72141000 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
10 | 02/002/28 | Guardrail Replacement Programme Phase 3 | Installation of new guardrails along the Highways and Main Roads | 72141000 | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
11 | 02/002/28 | Scour Protection works at B 1/9 Saddle Road, Santa Cruz. | Construction of R.C. Channel Lining, Desilting of the watercourse | 72141107 | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
12 | 02/002/28 | Scour Protection works at B 1/26 Churchill Roosevelt Highway, E/B | Construction of R.C. Channel Lining, Desilting of the watercourse | 72141107 | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
13 | 02/002/28 | Repairs to B 1/1 Chin Chin Road and B1/13 SMR, Cunupia | Repairs to Bridge Handrails, Road Restoration Works and Bridge rehabilitation works | 72141107 | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
14 | 02/002/28 | Repairs to B 2/5 Cottage Road, Lengua | Conversion of Timber deck to R.C. Deck Slab, Desilting of watercourse, Construction of R.C. Channel Lining and Road Rehabilitation | 72141107 | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
15 | 02/002/28 | Repairs to B 1/3 Lengua Road, Princes Town | Conversion of Timber deck to R.C. Deck Slab, Desilting of watercourse, Construction of R.C. Channel Lining and Road Rehabilitation | 72141107 | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
16 | 02/002/28 | Scour Protection works at B 1/2 Hermitage Road, Hermitage. | Construction of R.C. Channel Lining, Desilting of the watercourse | 72141107 | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | 10 working days | Fixed Term Contract
17 | 02/002/28 | Widening of B 2/4 Penal Rock Road, Penal | Widening of Bridge and Road restoration works | 72141107 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
18 | 02/002/28 | Reconstruction of B 3/13 Penal Rock Road, Siparia | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 72141107 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
19 | 02/002/28 | Reconstruction of B 2/8 San Francique Road, La Brea | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 72141107 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
20 | 02/002/28 | Widening of 2/2 Sisters Road | Widening of Bridge and Road restoration works | 72141107 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
21 | 02/002/28 | Widening of B 1/4 Sisters Road | Widening of Bridge and Road restoration works | 72141107 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
22 | 02/002/28 | Reconstruction of B 1/1 Robertson Road | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 72141107 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
23 | 02/002/28 | Handrails along Penal Rock Road | Repairs to Handrails | 72141000 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
24 | 02/002/28 | Repairs to B 1/67 Southern Main Road rousillac | Slope stabilization works | 77111603 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | 10 working days | Fixed Term Contract
1 | 02/002/28 | Sectional Milling and Paving along Morne Coco Road, 5km - 10km mark | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
2 | 02/002/28 | Sectional Milling and Paving along Saddle Road, 12km to 19km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
3 | 02/002/28 | Sectional Milling and Paving Works at Beetham Highway, East and Westbound, 0.0km - 4.7km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
4 | 02/002/28 | Sectional Milling and Paving Works at Churchill Rooservelt Highway, East and Westbound, 4.7km - 11.4km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
5 | 02/002/28 | Sectional Milling and Paving Works at Eastern Main Road 1.0km - 11.4km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
6 | 02/002/28 | Sectional Milling and Paving Works at Uriah Butler Highway, North and Southbound 0.0km - 3.8km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
7 | 02/002/28 | Sectional Milling and Paving Works along Churchill Roosevelt Highway, 11.8km to 34.8km, Eastbound | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
8 | 02/002/28 | Sectional Milling and Paving Works along Churchill Roosevelt Highway, 34.8km to 11.8km, Westbound | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
9 | 02/002/28 | Sectional Milling and Paving Works along Trincity Central Road | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
10 | 02/002/28 | Sectional Milling and Paving Works along Eastern Main Road, 11.4km to 34.8km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
11 | 02/002/28 | Sectional Milling and Paving Works along Lopinot Road, 2.9km to 4.6km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
12 | 02/002/28 | Sectional Milling and Paving Works along Cumuto Road, 7.6km to 9.3km marks PHASE 2 | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
13 | 02/002/28 | Sectional Milling and Paving Works along Tamana Road, 4.7km to 6.1km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
14 | 02/002/28 | Sectional Milling and Paving Works along Cumuto Tumpuna Road, 1.4km to 5.3km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
15 | 02/002/28 | Sectional Road Rehabilitation works along Guaico Tamana Road 7km - 15km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
16 | 02/002/28 | Sectional Road Rehabilitation works along Plum Mitan Road 3.5km - 12km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
17 | 02/002/28 | Sectional Road Rehabilitation along Caigual Road 0km - 4km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
18 | 02/002/28 | Sectional Road Rehabiliation along Paria Main Road 51km - 72km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
19 | 02/002/28 | Sectional Road Rehabilitation along Cunapo Southern Road, 9.2km to 21kmkm mark | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
20 | 02/002/28 | Sectional Road Rehabilitation along Grand Fond Road 0km to 6km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
21 | 02/002/28 | Sectional Road Rehabilitation works along Waterloo Road 0.0km - 13.0km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
22 | 02/002/28 | Sectional Road Rehabilitation works along Carli Bay Road 0.0km - 2.1km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
23 | 02/002/28 | Sectional Road Rehabilitation works along Calcutta #2 Road 0.0 - 5.3km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
24 | 02/002/28 | Sectional Milling and Paving along Freeport Todds Road, 3.5km to 5km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
25 | 02/002/28 | Sectional Milling and Paving along Southern Main Road, 26.1km to 28.1km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
26 | 02/002/28 | Sectional Milling and Paving along Southern Main Road, 33.5km to 42km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
27 | 02/002/28 | Sectional Milling and Paving along Caparo valley Brasso Road, 1.9km to 18.8km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
28 | 02/002/28 | Sectional Milling and Paving along Sir Solomon Hochoy, Northbound, 43.5km - 32km mark | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
29 | 02/002/28 | Sectional Milling and Paving Works along Gasparillo Bye Pass Road, 0.0km to 1.6km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
30 | 02/002/28 | Sectional Road Rehabilitation along Hermitage Road, 0.0km - 4.8km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
31 | 02/002/28 | Sectional Road Rehabilitation along Southern Main Road, 42km - 47.0 km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
32 | 02/002/28 | Sectional Road Rehabilitation works along Naparima Mayaro Road 5.6km - 10.0km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
33 | 02/002/28 | Sectional Road Rehabilitation works along M2 Ring Road Road 7.5km - 15.5km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
34 | 02/002/28 | Sectional Road Rehabilitation works along M1 Tasker Road 0.0km - 4.8km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
35 | 02/002/28 | Sectional Road Rehabilitation works along Piparo Road 7km - 8.4km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
36 | 02/002/28 | Sectional Road Rehabilitation along Naparima Mayaro Road, 14.5km - 28km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
37 | 02/002/28 | Sectional Road Rehabilitation along Buen Intento Road 2.8km - 6.5 km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
38 | 02/002/28 | Sectional Milling and Paving along M1 Tasker Road 1.9km - 2.8km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
39 | 02/002/28 | Sectional Milling and Paving along Matilda Road 0.0km - 0.9km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
40 | 02/002/28 | Sectional Road Rehabiliation along St. Julien Road 2.4km - 3.4km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
41 | 02/002/28 | Sectional Road Rehabiliation along Naggee Road 0.5km - 1.5km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
42 | 02/002/28 | Sectional Road Rehabilitation along Mayaro Guayaguayare 18.0km - 21.0 km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
43 | 02/002/28 | Sectional Milling and Paving along Mayaro Guayaguayare 0.0 km - 4.0 km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
44 | 02/002/28 | Sectional Milling and Paving along Tabaquite Rio Claro Road, 35.5km to 37.0km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
45 | 02/002/28 | Sectional Milling and Paving along Naparima Mayaro Road, 31.0km - 40.0km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
46 | 02/002/28 | Sectional Milling and Paving along San Pedro Road, 0.0 km - 2.5km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
47 | 02/002/28 | Sectional Milling and Paving along Biche Ortoire Road, 0.0km to 3km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
48 | 02/002/28 | Sectional Milling and Paving along Naparima Mayaro Road, 52.0km - 59.0km marks | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
49 | 02/002/28 | Road Rehabilitation and Paving works along Southern Main Road 74.0km to 77.5km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
50 | 02/002/28 | Milling, Strenghtening and Paving along Southern Main Road 65.9km to 72km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
51 | 02/002/28 | Sectional Road Rehabilitation and Paving works along Southern Main Road 85.6km to 91.7km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
52 | 02/002/28 | Milling, Strenghtening and Paving works along Mon Desir Delhi Road 0.0km to 2.44km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
53 | 02/002/28 | Sectional Strengthening, Milling and Paving along M2 Ring Road 5km to 7km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
54 | 02/002/28 | Sectional Road Rehabilitation works along SS Erin Road 10.5km to 13.6km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
55 | 02/002/28 | Sectional Road Rehabilitation works along SS Erin Road 15.5km to 19.0km | Sectional Road Rehabilitation Works | 72141000 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Open Tendering | 10 working days | Fixed Term Contract
56 | 02/002/28 | Critical Repairs to Landslip at Saddle Road, 9.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
57 | 02/002/28 | Critical Repairs to Landslip at North Coast Road, 10.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
58 | 02/002/28 | Critical Repairs to Landslips along Aripo Road, 6.2km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
59 | 02/002/28 | Critical Slope Stabilization works along Blanchisseuse Road, 6km- 6.1km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
60 | 02/002/28 | Critical Repairs to Landslip along Cumuto Road, 15.7km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
61 | 02/002/28 | Emergency Slope Stabilisation & Ancilliary Works along Paria Main Road 63.5km | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
62 | 02/002/28 | Emergency Repairs to Landslip at Cumaca Road, 1.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
63 | 02/002/28 | Critical Repairs to Landslip at Guaico Tamana Road, 7.6km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
64 | 02/002/28 | Critical Repairs to Landslip at Fishing Pond Road, 1.6km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
65 | 02/002/28 | Critical Repairs to Landslip along North Manzanilla Road, 0.5km | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
66 | 02/002/28 | Emergency Repairs to Landslip along Todds Station Road, 0.7km to 5.8km marks | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
67 | 02/002/28 | Critical Repairs to Landslip at Tortuga Road, 2km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
68 | 02/002/28 | Critical Repairs to Landslip at Cipero Road, 9.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
69 | 02/002/28 | Critical Repairs to Landslip at Cipero Road, 9.8km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
70 | 02/002/28 | Critical Repairs to Landslips along Corosal Road, 3km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
71 | 02/002/28 | Emergency Repairs to Landslip along Papourie Road, 13km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
72 | 02/002/28 | Critical Repairs to Landslip along Sir Solomon Hochoy Highway, 34.5km mark, Southbound | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
73 | 02/002/28 | Critical Repair to Landslip at St. Croix Road, 6.7km mark in vicinity of LP#29 | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
74 | 02/002/28 | Critical Repairs to Landslip at Garth Road, 4.5 km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
75 | 02/002/28 | Critical Repairs to Landslip at Garth Road, 3.3km mark in vicinity of LP #119 | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
76 | 02/002/28 | Repair to landslips and restoration of roadway along St Julien Road, 1km to 4km marks | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
77 | 02/002/28 | Repairs to Landslip at Naparima Mayaro Road, 31km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
78 | 02/002/28 | Repairs to Landslips along Jaipaulsingh Road, 0.3 km and 0.8 km marks | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
79 | 02/002/28 | Critical Repairs to Landslip at Whatts Road, 3.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
80 | 02/002/28 | Repair to Landslips at Torrib Tabaquite, 2.0km and 2.2km marks | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
81 | 02/002/28 | Repairs to Landslip at Dades Road, 2.5km and reconstruction of crossing at 2.7km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
82 | 02/002/28 | Critical Slope Stabilization Works on Tabaquite Rio Claro Road 49.1km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
83 | 02/002/28 | Critical Repairs to Landslip at Cunapo Southern Road, 28.5km | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
84 | 02/002/28 | Emergency Repairs to Landslip along Southern Main Road, 96.3km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
85 | 02/002/28 | Emergency Repairs to Landslip along Southern Main Road, 106.9km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
86 | 02/002/28 | Emergency Repairs to Landslip along Southern Main Road, 95.6km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
87 | 02/002/28 | Emergency Repairs to Landslip at Penal Rock Road, 13.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
88 | 02/002/28 | Critical Repairs to Landslip at S.S. Erin Road, 12.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
89 | 02/002/28 | Critical Slope Stabilization Works along Fyzabad Branch Road, 3.5km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
90 | 02/002/28 | Critical geotechnical Investigation for Landslip at Realize Road, 1.8km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
91 | 02/002/28 | Critical Slope Stabilization works along Paria Main Road, 52km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
92 | 02/002/28 | Critical Repairs to Landslip at Brasso Caparo Station Road, 4km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
93 | 02/002/28 | Repairs to Landslip along Penal Rock Road, 22.2 km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
94 | 02/002/28 | Repairs to Landslip along Realize road, 1.6km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
95 | 02/002/28 | Critical Repairs to Landslip along Golconda Road, 0.7km | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
96 | 02/002/28 | Repairs to Landslip at Martiste Road, 0.3km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
97 | 02/002/28 | Repairs to Landslip at Siparia Road, 0.1km mark | Slope Stabilization Works | 72103300 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | 10 working days | Fixed Term Contract
1 | 02/002/28 | Engineering Consultancy Services For The Construction Of Cast-In-Place Concrete Barriers At The Median Of The Churchill Roosevelt Highway 4.7km - 7.4km (In The Vicinity Of Solo To Grand Bazaar Interchange) | To construct new median permanent concrete barriers along the highway inclusive of utility relocations | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
2 | 02/002/28 | Topographic Survey for Median Barriers installation along Uriah Butler Highway 8km-16km ( from Guayamare River Bridge to Chaguanas Overpass) | To perform topographic surveys for defining position for new Guard Rails | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
3 | 02/002/28 | Geotechnical Investigation for Papourie Road, 13.0km | To perform approximately 6 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 72141500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
4 | 02/002/28 | Geotechnical Investigation for Reform Road, 1.8km | To perform approximately 5 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 72141500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
5 | 02/002/28 | Geotechnical Investigation for Bon Air Road 0-2km | To perform approximately 6 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 72141500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
6 | 02/002/28 | Geotechnical Investigation for Arima Blanchisseuse Road 6.1km | To perform approximately 3 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 72141500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
7 | 02/002/28 | Construction of a Cylindrical Road Crossing along Trinicity Central Road in the vicinity of Superpharm and East Gates Mall | Construction of a Double Cylindrical Road Crossing (20m long with 600mm diameter bore each) along with associated road works. | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
8 | 02/002/28 | Engineering Consultancy and Traffic Studies along Uriah Butler Highway 14.5km Mark in the vicinity of Priceplaza and Endeavour Pass | Engineering analysis and traffic studies to alleviate congestion | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
9 | 02/002/28 | Engineering Consultancy and Traffic Studies along Sir Solomon Hochoy Highway 5.7km Mark in the vicinity of Chase Village Overpass | Engineering analysis and traffic studies to alleviate congestion | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
10 | 02/002/28 | Engineering Consultancy and Traffic Studies along Sir Solomon Hochoy Highway 26.0km Mark in the vicinity of Tarouba Overpass | Engineering analysis and traffic studies to alleviate congestion | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
11 | 02/002/28 | Engineering Consultancy and Traffic Studies along Sir Solomon Hochoy Highway 22.0km Mark in the vicinity of Gasparillo Overpass | Engineering analysis and traffic studies to alleviate congestion | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
12 | 02/002/28 | Procurement of Materials for Bus Route Passes |  | 43201400 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
1 | 02/002/28 | Mucurapo Overpass | Consultancy and reair of bridge | 81101500 | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | 10 working days | Fixed Term Contract
Capital Expenditure/DP
Agua Santa Operations of
1 | XXXX | Maintenance of Plant & Equipment | Maintenance/repairs of machinery parts for batching drum mix asphalt plant and (loader) | 30121600 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 30days | Three Quote System | Not applicable | Invoice
2 | XXXX | Personal Protective Equipment | PPE includes but is not limited to:-Safety Boots, Steel toe rubber boots, Hard Hat, Coveralls (flame resistant), Goggles, dust masks, welding glooves, Nitrile Glooves, Chemical resistant gloves, double sided gloves | 46180000 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 10 days | Three Quote System | Not applicable | Invoice
3 | XXXX | Purchase of Vehicle & Equipment | Purchase of all government vehicles/machinery Tractors(backhoe),Trucks,SUV. | 25100000 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Open bidding | 10 working days | Fixed Term Contract
4 | XXXX | Material & Supplies- | Purchase of Bitumen, CRSII, Diesel, for the production and application of Hot Mix Asphalt | 30121600 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole select | Not applicable | Fixed Term Contract
5 | XXXX | Office Supplies | Purchase of office stationary, Printer/photocopier, furniture, computers, Paper, other supplies include cleaning materials, toiletries. | 44120000 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Three Quote System | Not applicable | Invoice
6 | XXXX | Quality Control | Consultancy services for quality control. |  | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Three Quote System | Not applicable | Not applicable
7 | XXXX | Maintenance of Facilities | Maintenance of Office Building and compound:-Windows/door repairs, tiling, painting, air conditioning, furniture, cameras, refrigerator | 72101500 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Three Quote System | Not applicable | Invoice
8 | XXXX | Utilities | Electricity, WASA, Phone and Internet | 83101800 83111501 83101500 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole Select | Not applicable | Fixed Term Contract
9 | XXXX | Security Services | Security for the Agua Santa Asphalt Plant compound | 92120000 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Open bidding | 10 working days | Fixed Term Contract
10 | XXXX | Safety Training and Development | All expenses associated with the training and development of staff both locally and abroad including: - cost of overseas travel pertinent to the training - cost of Contracted or Consultancy Services | 86100000 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Sole select | Not applicable | Fixed Term Contract
11 | XXXX | Material & Supplies- | Purchase of Aggregate, Gravel for the production and application of Hot Mix Asphalt | 30121800 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole select | Not applicable | Fixed Term Contract
12 | XXXX | Material & Supplies- | Purchase of Sharp Sand, Limestone and Stone Dust for the production and application of Hot Mix Asphalt | 30121600 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole select | Not applicable | Fixed Term Contract
13 | XXXX | Material & Supplies- | Purchase of Bitumen for the production and application of Hot Mix Asphalt | 30121500 | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole select | Not applicable | Fixed Term Contract
Formulas:
Expected Delivery/ Completion Date = [Expected Delivery/ Completion Date, row above]

## PBR Unit (hidden)
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
PBR Unit
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## PURE (hidden)
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
Programme for Upgrading Roads Efficiency
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## Maritime Division
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Maritime Division
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill Period (If applicable)- No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 02/015/03 | Uniforms | To purchase PPE, shirt, pants, shoes, helmets, gloves, masks, respirators, goggles,safety boots, Life Jacket ,coverall,Eye protection, Ear protection,Chemical gas mask,Chemical suit ,Safety harness etc. | 46180000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
2 | 02/015/04 | Electricity | To pay any energy related charges. | 83101800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
3 | 02/015/05 | Telephones | To pay telephone related charges. | 83111501 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
4 | 02/015/06 | Water & Sewerage Rates | To pay any water and sewerage charges. | 83101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
5 | 02/015/08 | Rent / Lease - Office Accommodation & Storage | Rent / Lease of buildings which houses Government Offices. | 80131500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
6 | 02/015/09 | Rent / Lease - Vehicles & Equipment | Rent / Lease of vehicles & equipment. | 72141700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
7 | 02/015/10 | Office Stationery & Supplies | To purchase office consumables, cleaning supplies, garbage bags, hand cleaner, soap, ink toner , etc . | 44120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
8 | 02/015/11 | Books & Periodicals | To purchase books and navigational aids publications, nautical charts/maps for use in the Maritime Services Division library. | 14111800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
9 | 02/015/12 | Material & Supplies | To purchase consumables for the Maritime Services Division eg Rhino Cables, Battery Chargers, Deep Cycle Marine Batteries, Straw Boards, Buckrum , Bond Paper etc . |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
10 | 02/015/13 | Maintenance of Vehicles | To purchase all parts and consumables for vehicles to conduct preventive maintenance, such as oil, filters and tyres.Refurbishment of the ML Inspector- seating accommodation, electrical wiring, conducting fibreglass repairs to body of vessel and the supply and installation of boat engines. To pay charges associated with additional service cost to vehicles. | 78181500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
11 | 02/015/15 | Repair and Maintenance -Equipment | Labour and parts for printers, repair/change lanterns, bush cutting etc. | 81112306 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
12 | 02/015/21 | Repairs and Maintenance - Buildings | Painting, replace doors/ windows, toilets, sinks, lighting fixtures , etc. | 72101507 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
13 | 02/015/23 | Fees | Payment of Fees for external examiners, surveyors etc. |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Selective Tendering | Not applicable | Fixed Term Contract
13 | 02/015/28 | Other Contracted Services | The sea transportation of Msd personnel to its sea based Atons | 78111700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Limited Bidding | 10 Days | Fixed Term Contract
15 |  |  | Diving Exercise to be conducted on the Thirteen ( 13 ) Buoys located within Trinidad & Tobago - Cleaning & Inspection Works | 81103000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Limited Bidding | 10 Days | Fixed Term Contract
16 |  |  | Cutting, clearing of trees and the construction of stairways leading to Aton location | 72141200 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Limited Bidding | 10 Days | Fixed Term Contract
|  |  | Re establishment of a Remote Monitoring System for the Thirteen ( 13 ) Buoys located within Trinidad & Tobago - Remote Monitoring System | 81103000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Limited Bidding | 10 Days | Fixed Term Contract
| 02/015/37 | Janitorial Services | To pay charges associated with janitorial maintenance and sanitation organizations. | 76110000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Selective Tendering | Not applicable | Fixed Term Contract
17 | 02/015/43 | Security Services | To pay charges associated with all contracted security services. | 92120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
18 | 02/015/61 | Insurance | Insurance coverage for eligible officers of the Maritime Services eg Superintendent of Lighthouses, Navigational Aids Maintenance Officer I/II, Lighthouse Keeper I/II etc. | 84131505 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
19 | 02/015/62 | Promotions, Publicity & Printing | Printing of manuals, forms, brochures, Advertisements in Television, Newspapers and in International Publications etc. | 14111800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
20 | 02/015/66 | Hosting of Conferences, Seminars & Other Functions | Hosting of World Seafarers Day, World Maritime Day , any other functions on behalf of the Maritme Services Division. | 80141902 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
21 | 02/015/96 | Fuel and Lubricants | To purchase diesel, gasoline, renew fleet cards etc. | 15000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Selective Tendering | Not applicable | Fixed Term Contract
22 | 03/015/01 | Vehicles | To purchase vehicles/equipment eg 12 seater bus. | 25100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Limited Bidding | 10 Days | Fixed Term Contract
23 | 03/015/02 | Office Equipment | To purchase office equipment. For example, photocopiers, printers, computers, router,Laptop,Printer/scanner/copier, Tablet with internet access,Mobile telephone with internet access, Digital camera and case, Laser measuring tape, PDF MSD fillable forms “adobe reader”, Ship stability manual creator software, Ship inclining test calculator etc. | 43212100 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
24 | 03/015/03 | Furniture and Furnishings | To purchase office furniture and furnishing. For example, microwaves, filing cabinets and lockers. | 56000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
25 | 03/015/04 | Other Minor Equipment | To purchase minor equipment for the Maritime Services Division eg Refridgerator, Microwave Oven, Electric Kettle,Atmospheric tester, Portable air quality and oxygen monitor, Intrinsic safe flash light, Hand held voltage finder, Multi-tool Leatherman, Clicker Counter etc. | 44100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/Quotations
26 | 04/001/01 | Caribbean Port State | Transfer of funds to this organisational body that The Republic of Trinidad & Tobago is a member state . | 84121600 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not Applicable | Not applicable | Not Applicable
27 | 04/003/02 | International Maritime Consultative Organisation | Transfer of funds to this organisational body that The Republic of Trinidad & Tobago is a member state . | 84121600 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable
28 | 09/003/15/H/789 | Upgrading & Modernization of Navigational Aids | The refurbishment of Galera Point, Brigand Hill and Chacachacare Lighthouse | 41112900 | 2023-09-29 | 2024-10-12 | 230 days | Open Bidding | 10 Days | Fixed Term Contract
29 | 09/003/15/H / 824 | Removal & Disposal of Wrecks & Derelict Vessels | Disposal of Disposal of Wrecks & Derelict Vessels within the territorial waters of Trinidad & Tobago. | 76121500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract

## Maintenance
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Maintenance Division
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill Period (If applicable)- No. of days | Contract Type
RECURRENT EXPENDITURE
1 | XXXX | Purchase of Uniforms | Purchase of steel tip boots, rubber boots, coveralls, shirts, pants, welder apron, safety harness, leather gloves,hemets, googles, ear muff, dust mask, etc. | 53102700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
2 | XXXX | Rental of Equipment | Rental of backhoe, jack hammer, terrazzo machine,hiab, shid steer, aerial work platform,bobcat,cherry picker, etc. | 72141700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
3 | XXXX | Purchase of Office Stationeries and Supplies | Purchase of Toners, computer ink, flash drives, file jackets, hanging folders, notebooks, envelopes, treasury tags, stamp pads, rulers, paper clips, staplers, tapes, markers, etc. | 44120000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
4 | XXXX | Supply and Delivery of Materials for Replenish Maintenance Stores | Material for repairs and routine maintenance - seven (7) MOWT buildings on compound. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Electrical materials. | 39121700
5 | XXXX | Supply and Delivery of Materials for Highways and Drainage Sub Office Mayaro | Routine maintenance. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
6 | XXXX | Supply and Delivery of Materials for Highways Sub District Office Tabaquite | Security lighting and new electrical works. | 72151700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
7 | XXXX | Supply and Delivery of Materials for Works Complex, Matilda Compound | Construction of curb and slipper drain. | 70171800 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Refurbishing and upgrading of toilets, electrical and plumbing. | 72101500
8 | XXXX | Supply and Delivery of Materials for Works Complex, Matilda Maintenance Division | To refurbish kitchen cupboards. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repaint offices and kitchen. | 72101500
|  |  | Refurbishing and upgrading of toilets, electrical and plumbing. | 72101500
9 | XXXX | Supply and Delivery of Materials for Highways Sub Office, New Grant | To refurbish kitchen cupboards. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repaint offices and kitchen. | 78181600
|  |  | Refurbishing and upgrading of toilets, electrical and plumbing. | 72101500
10 | XXXX | Supply and Delivery of Materials for Works Complex Matilda, Highways Division | To refurbish kitchen cupboards. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repaint offices and kitchen. | 78181600
|  |  | Refurbishing and upgrading of toilets, electrical and plumbing. | 72101500
11 | XXXX | Supply and Delivery of Materials for Transport Garage | Repaint offices and watchman booth. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Refurbishing and upgrading of toilets, electrical and plumbing. | 72101500
12 | XXXX | Supply and Delivery of Materials for Highways Sub Office, Penal Rock Road, Maruga | Repaint offices and watchman booth. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Refurbishing and upgrading of toilets, electrical and plumbing. | 72101500
13 | XXXX | Supply and Delivery of Materials for Maintenance Division Chaguanas Compound | To continue existing perimeter fence and gates, general painting and plumbing works. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Demolition to old PIRO Building and prepare for parking space. | 72101500
|  |  | Renovations to old DAO Building. | 72101500
14 | XXXX | Supply and Delivery of Materials for Highways Division St. Yves Chaguanas | Tile works for floor. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
15 | XXXX | Supply and Delivery of Materials for Traffic Wardens, Fredrick Settlement | Tiles works, plumbing, cupboards and vanities. | 72101500 | Oct. 2023 | Sept. 2024
16 | XXXX | Supply and Delivery of Materials for Maintenance / Highways Division Couva Compound | General maintenance, general upgrading and painting works. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
17 | XXXX | Supply and Delivery of Materials for Highways Sub Office, Mayo | Painting of existing sub-office interior, exterior and reconstructing perimeter fence and gates. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
18 | XXXX | Supply and Delivery of Materials for Highways Division, Victoria West | Painting of interior and exterior building also repairs to perimeter fencing. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
19 | XXXX | Supply and Delivery of Materials for Works Complex Siparia | To upgrade existing washroom facilities (5) inclusive of all toilets fixtures. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Upgrade security booth. | 72101500
|  |  | Repainting of stores building, electrical building. | 78181600
|  |  | Repairs to front gates. | 72101500
20 | XXXX | Supply and Delivery of Materials for Maintenance Sub-Office La Brea | General repairs to wood floor, walls and roof | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
21 | XXXX | Supply and Delivery of Materials for Highways Sub Office San Francique | Re-painting of building external and internal. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repairs to tank stand. | 72101500
|  |  | Repair to front gate. | 72101500
22 | XXXX | Supply and Delivery of Materials for Highways Sub Office La Brea | Repairs to building and repairs to container roof. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Re-painting of Building | 78181600
|  |  | and container. | 72101500
23 | XXXX | Supply and Delivery of Materials for Highways Sub Office Cedros | Re-painting of containers, external and internal. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repair to front gates. | 72101500
24 | XXXX | Supply and Delivery of Materials for Maintenance Division Regional Office, Laventille | Painting to the exterior and interior of the building including perimeter fence. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Construction of a drain and upgrading of the existing drainage on the compound | 72101500
|  |  | Paving and repaving of compound. | 72101500
|  |  | Upgrading of the existing plumbing fixtures. | 72151100
25 | XXXX | Supply and Delivery of Materials for Sub District Diego Martin | Painting to the exterior and interior of the building. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Upgrading of the existing water supply and plumbing fixtures. | 72101500
26 | XXXX | Supply and Delivery of Materials for Maintenance Sub District Carenage | Painting to the exterior and interior of the building. | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Burglar proofing of the building. | 72101500
|  |  | Upgrading of plumbing fixture and fittings. | 72151100
27 | XXXX | Supply and Delivery of Materials for Maintenance Sub District St. Joseph Farm Road | Painting to the exterior and interior of the building . | 78181600 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Fencing and burglar proofing of the compound and building. | 30152000
|  |  | Upgrading of the fixtures and fittings. | 72101500
28 | XXXX | Supply and Delivery of Materials for Highways Division Cumuto Sub Office, Cumuto | To construct perimeter fence wall. | 30152000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
Construction of stores and work shed.
|  |  | Painting new works and office building. | 78181600
|  |  | Upgrade to electrical installation | 39121700
|  |  | To supply and install office identification plate signs, directional signs, departmental signs, entrance, exit, etc. | 72101500
29 | XXXX | Supply and Delivery of Materials for Highways Division Tamana Sub Office Guaico | To construct guard booth. |  | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Fabricating steel roof and repairs to building. | 72101500
|  |  | To refurbish stores. | 72101500
To complete upgrade to electrical.
|  |  | Painting interior and exterior of building. | 78181600
|  |  | To supply and install office identification plate signs, directional signs, departmental signs, entrance, exit, etc. | 72101500
30 | XXXX | Supply and Delivery of Materials for Maintenance Division Regional Building, Arima | Redesign office space. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | To ceil perimeter of building. | 72101500
|  |  | To paint all other buildings on the compound. | 78181600
|  |  | To supply and install office identification plate signs, directional signs, departmental signs, entrance, exit, etc. | 72101500
31 | XXXX | Supply and Delivery of Materials for Traffic Management Office and Transport Stores, Guaico | To demolish timber and construct steel roof. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | To supply and install gypsum ceiling replacement of windows and doors. | 72101500
|  |  | Construction of ring beam and repairs to internal partition walls. | 72101500
|  |  | Tiling of floor surface using non-skid porcelain tiles. | 72101500
|  |  | Painting interior and exterior surfaces. | 78181600
|  |  | Plumbing and electrical upgrade. | 72151100
|  |  | To supply and install office identification plate signs, directional signs, departmental signs, entrance, exit, etc. | 72101500
32 | XXXX | Supply and Delivery of Materials for Highways Division O'Meara Stock Pile, Arima | To construct perimeter fence wall. | 30152000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Painting concrete and new metal works. | 78181600
|  |  | Increasing height of existing wall. | 72101500
|  |  | Paving of compound and drain. | 72101500
33 | XXXX | Supply and Delivery of Materials for Highways Division O'Meara Stock Pile, Arima | To supply and install office identification plate signs, directional signs, departmental signs, entrance, exit, etc. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
34 | XXXX | Supply and Delivery of Materials for Highways Division P.I.U Office, Piarco | To construct steel roof. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repairs to building and partition walls. | 72101500
|  |  | Electrical and plumbing works. | 39121700
|  |  | Painting interior and exterior of building. | 78181600
|  |  | To supply and install office identification plate signs, directional signs, departmental signs, entrance, exit, etc. | 72101500
35 | XXXX | Supply and Delivery of Materials for Highways Division Agua Santa Asphalt (Administrative Office Wallerfield) | Renovation works to main office building inclusive of upper and ground floor. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | To supply and install office identification plate signs, directional signs, departmental signs, entrance, exit, etc. | 72101500
36 | XXXX | Supply and Delivery of Materials for Travellers Quarters, Toco | Repairs to travelling quarters inclusive of ceiling works, bathroom and toilet facilities. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Complete repairs and upgrade to kitchen cabinetry. | 72101500
|  |  | Replacement of windows and timber walls with concrete blocks. | 72101500
37 | XXXX | Supply and Delivery of Materials for Travellers Quarters, Blanchisseuse | Repairs to travelling quarters inclusive of ceiling works, bathroom and toilet facilities. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Complete repairs and upgrade to kitchen cabinetry. | 72101500
|  |  | Replacement of windows and timber walls with concrete blocks. | 72101500
38 | XXXX | Supply and Delivery of Materials for Maintenance Sub Office Blanchisseuse | Renovation works to main office building. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | To construct perimeter fence and entrance gate. | 30152000
|  |  | Upgrade of existing kitchen area, storage area, toilet area,etc. | 72101500
39 | XXXX | Maintenance of Vehicles | Windscreen replacement, tyres, routine maintenance, A/C installation, drive shaft replacement, bearing replacement | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
40 | XXXX | Repairs and Maintenance (Equipment) | Repairs of Arc welding plant, brush cutter, chop saw, hammer drill, demolition hammer, tile cutter, pressure washer, disc grinder, brush cutter, electrical jack hammer, screw gun, etc. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
41 | XXXX | Supply and Delivery of Materials for Renovation Works - Works Complex Rio Claro | Air condition servicing. | 72151200 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Additional supplemental scaffolding components. | 78181500
42 | XXXX | Supply and Delivery of Materials for Renovation Works - Works Complex Arima | For the provision of structural repairs, painting works and cleaning services. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Plumbing upgrade. | 72151100
|  |  | Electrical upgrade. | 39121700
|  |  | Air condition services. | 72151200
43 | XXXX | Supply and Delivery of Materials for Renovation Works - Traffic Warden Building Arima | For the provision of structural repairs, painting works and cleaning services. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Plumbing upgrade. | 72151100
|  |  | Electrical upgrade. | 39121700
Electrical re-certification.
44 | XXXX | Supply and Delivery of Materials for Renovation Works - Works Complex Building, Guaico | For the provision of structural repairs, painting works and cleaning services. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Plumbing upgrade. | 72151100
|  |  | Electrical upgrade. | 39121700
Air condition servicing.
45 | XXXX | Supply and Delivery of Materials for Renovation Works - Works Complex Siparia | Repairs to fencing and painting of ground floor internal and external walls of building. | 30152000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Electrical re-certification. | 78181500
46 | XXXX | Supply and Delivery of Materials for Renovation Works - Maintenance Sub Office La Brea | Repairs to fencing , to gates and painting of external walls of building.(Garage) | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
47 | XXXX | Supply and Delivery of Materials for Renovation Works - MP Office Fyzabad | Repairs to fencing, to store and painting of external walls of building. | 30152000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repairs to yard (cold mix) | 78181500
48 | XXXX | Supply and Delivery of Materials for Renovation Works - MP Office Penal | Repairs to fencing. | 30152000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
49 | XXXX | Supply and Delivery of Materials for Renovation Works - Maintenance Regional Office, Farah Street San Fernando | Structural repairs and routine maintenance. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repair and servicing of air conditioning units. | 72151200
50 | XXXX | Supply and Delivery of Materials for Renovation Works - Maintenance Victoria West OAS Compound | Structural repairs and routine maintenance. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repair and servicing of air conditioning units. | 72151200
51 | XXXX | Supply and Delivery of Materials for Renovation Works - Traffic Warden Building OAS Compound | Structural repairs. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Repair and servicing of air conditioning units. | 72151200
Routine maintenance.
52 | XXXX | Supply and Delivery of Materials for Renovation Works - Maintenance Sub Office Couva | To enclose steel frame structure to provide for relocation of stores and office accommodation. | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Electrical upgrade. | 39121700
|  |  | Air condition upgrade. | 72151200
53 | XXXX | Supply and Delivery of Materials for Renovation Works - Works Complex Maintenance Division, Main Office St. George East District | Electrical re-certification. | 39121700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
554 | XXXX | To Supply Services to Works Complex Rio Claro | Annual certifying of scaffolding, scaffolding component inclusive of harness and lanyard | 78181500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Septic tank cleaning - 4N septic tanks. | 78181500
55 | XXXX | To Supply Services to Works Complex Rio Claro | To supply and install fire alarm and dection system for the compound - fire extinguishers with safety signage, smoke detectors and fire alarms. | 72151700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
56 | XXXX | To Supply Services to Highways Drainage Sub Offices Mayaro | Pest control. | 10191700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
57 | XXXX | To Supply Services to Works Complex Matilda Administrative Building | Fencing and retaining wall. | 30152000 | Oct. 2023 | Sept. 2024
Pest control.
58 | XXXX | To Supply Services to Works Complex Siparia | To install camera systems. | 72151700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | To install security gates (2) with motors and electrical . | 72151700
|  |  | Fire alarm and detection system. | 72151700
|  |  | Pest control. | 10191700
59 | XXXX | To Supply Services to Works Complex Maintenance Division, Main Office St. George East | To remodel office with work stations to accommodate monthly and daily paid paid staff. | 72101500 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
60 | XXXX | To Supply Services to Works Complex Maintenance Division, Main Office St. George East | Fire alarm and detection system. | 72151700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | Pest control. | 10191700
|  |  | A/C replacement. | 72151200
61 | XXXX | To Supply Services to Guaico Works Complex | Pest control. | 10191700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
62 | XXXX | Provision of Security Services - Maintenance Regional Office, Farah Street San Fernando. | For one (1) Year - One armed security officer for overnight security of compound and assets. | 72151700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | 6pm - 6am shift, seven (7) days per week. | 72151700
63 | XXXX | Provision of Security Services - Maintenance Regional Office, Eastern Main Road, Laventille | For one (1) Year - One armed security officer and K9 for overnight security of compound and assets. | 72151700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | 6pm - 6am shift, seven (7) days per week. | 72151700
64 | XXXX | Provision of Security Services - Maintenance Air Conditioning and Refrigeration Workshop, Frederick Street, Port of Spain | For one (1) Year - One armed security officer for overnight security of compound and assets. | 72151700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
|  |  | 6pm - 6am shift, seven (7) days per week. | 72151700
65 | XXXX | Medical Services | Medical expenses for daily paid painter and sanitation workers, (plumbers and labourers) | 85121700 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
66 | XXXX | Purchase of Fuels | Purchase of fuels for both eight containers and twenty-one vehicles. | 15000000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
67 | XXXX | Purchase of Vehicles | Purchase of 5 Ton bucket truck, seven seater station wagon, flat tray truck and a double cab pickup. | 25100000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
68 | XXXX | Purchase of Office Equipment | Purchase of Computers, printers, scanners, shredder, external hard drive, microwave, digital camera, gel wrist pads, white board, electronic adding calculator, etc. | 44100000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
69 | XXXX | Purchase of Furniture and Furnishings | Purchase of Computer desk, executive desk, metal desk, lateral filing cabinets, rubbish bins, wall clock swivel chairs, etc. | 56101720 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
70 | XXXX | Purchase of Minor Equipment | Chop saw, electrical jack plane, belt sanders, extension cords, suction pump, leaf blower, rhino cables, table saw, standing fan, etc. | 44100000 | Oct. 2023 | Sept. 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
Emergency Projects
1 | XXXX | Emergency | Supply and installation of fire detection and alarm system for the MOWT Rio Claro Office. | 72151700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 4 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
2 | XXXX | Emergency | Supply and installation of a fire detection and alarm system for the MOWT Matilda Office. | 72151700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 3 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
3 | XXXX | Emergency | Correction of electrical defects in accordance with inspectorate standards for Head Office MOWT - Richmond Street. | 39121700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 4 months | Request for Quotations | Not applicable | Invoice/ Quotation
4 | XXXX | Emergency | Supply and Installation of a card access system for MOWT Maintenance Division, Sackville Street Office. | 72151700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 week | Request for Quotations | Not applicable | Invoice/ Quotation
5 | XXXX | Emergency | Supply and installation of energy efficient A/C mini split units for Laventille MOWT Office - Ground and First Floor. | 72151200 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 3 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
6 | XXXX | Emergency | Electrical materials associated with A/C installation for Laventille MOWT Office - Ground and First Floor. | 72151200 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 3 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
7 | XXXX | Emergency | Supply and installation of energy efficient A/C mini split units for MOWT Maintenance Farm Road Office. | 72151200 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 2 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
8 | XXXX | Emergency | Electrical materials associated with A/C installation for MOWT Maintenance Farm Road Office. | 72151200 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 2 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
9 | XXXX | Emergency | Duct Cleaning of MOWT Head Office | 76111500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 2 months | Request for Quotations | Not applicable | Invoice/ Quotation
10 | XXXX | Emergency | Duct Cleaning of MOWT Caroni Licensing Office | 76111500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 3 months | Request for Quotations | Not applicable | Invoice/ Quotation
11 | XXXX | Emergency | A/C Servicing of Licensing Office P.O.S ( 3 Services) | 72151200 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 3 weekends | Request for Quotations | Not applicable | Invoice/ Quotation
12 | XXXX | Emergency | Correction of electrical defects in accordance with inspectorate standards for Farm Road MOWT Maintenance Office. | 39121700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 month | Request for Quotations | Not applicable | Invoice/ Quotation
13 | XXXX | Emergency | Correction of electrical defects in accordance with inspectorate standards for MOWT Couva Highways and Maintenance Office | 39121700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 month | Request for Quotations | Not applicable | Invoice/ Quotation
14 | XXXX | Emergency | Electrical materials and consumables for the maintenance of St. George West MOWT Offices. | 39121700 | 1st Quarter Fiscal 2024 | Oct. 2023 | Sept. 2024 | Request for Quotations | Not applicable | Invoice/ Quotation
15 | XXXX | Emergency | Air condition material and consumables for the maintenance of St. George West District MOWT Offices | 72151200 | 2nd Quarter Fiscal 2024 | Oct. 2024 | Sept. 2025 | Request for Quotations | Not applicable | Invoice/ Quotation
16 | XXXX | Emergency | Correction of Electrical defects in accordance with inspectorate standards for MOWT Laventille Office. | 39121700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 2 months | Request for Quotations | Not applicable | Invoice/ Quotation
PSIP
1 | XXXX | Renovation Works to Cedros Sub-Office: Repairs to Container. |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Supply and Delivery | Open Bidding | 10 working days | Fixed Term Contract
2 | XXXX | Procurement of Materials for Internal Repairs | Supply and Delivery of materials to replace internal cladding, doors and windows in the container | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
3 | XXXX | Renovation Works to Highways Division /Transport Lengua Compound |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
4 | WT/MD:8/10/3 | Procurement of air conditioning units, electrical fittings and fixtures, where necessary including IT connection. | Supply and Delivery of materials to replace air conditioning units, electrical fittings and fixtures, where necessary including IT connection | 72151200 | 2024-01-31 | 2024-03-31 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
5 | WT/MD:8/10/4 | Procurement of Fire Detection and Alarm System | Supply and Installation of Fire Detection and Alarm System with Extinguishers |  | 2024-03-31 | 2022-05-31 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
6 | XXXX | Renovation Works Highways Sub-Office San Francique Electrical Works |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
7 | XXXX | Procurement of Electrical Materials and Consumables | Supply and Delivery of materials to replace electrical fittings and fixtures | 39121700 | 2023-11-01 | 2024-01-31 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
8 | XXXX | Emergency Repairs to the Drainage Pump Houses and Installation of Perimeter Lighting |  | 39111600 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Request for Quotations | Not applicable | Invoice/ Quotation
9 | WT/MD:14/2/1 Sub I | Procurement of Electrical Cabling & Fittings | Supply and Delivery of Electrical Cabling & Fittings | 39121700 | 2023-11-01 | 2024-01-31 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
10 | XXXX | Renovation Works to St. George West/East District Office, Farm Road, St. Joseph |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
11 | XXXX | Procurement of Service for Termite Treatment | Provision of Service for Treatment of Termite | 10191700 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
12 | XXXX | Procurement of Materials for Internal and External Renovations | Supply and Delivery of materials for Internal and External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
13 | XXXX | Procurement of Plumbing Materials for Repairs | Supply and Delivery of materials to replace Plumbing fittings and fixtures | 72151100 | 2023-10-31 | 2023-12-31 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
14 | XXXX | Procurement of Electrical Cabling, Fixtures & Fittings | Supply and Delivery of materials to replace electrical fittings and fixtures | 39121700 | 2023-10-31 | 2023-12-31 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
15 | XXXX | Renovation Works to Maintenance Sub-Office Electrical Building Chaguanas |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
16 | XXXX | Procurement of Service for Termite Treatment | Provision of Service for Treatment of Termite | 10191700 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
17 | XXXX | Procurement of Materials for Internal and External Renovations | Supply and Delivery of materials for Internal and External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
18 | XXXX | Procurement of Plumbing Materials for Repairs | Supply and Delivery of materials to replace Plumbing fittings and fixtures | 72151100 | 2024-02-29 | 2024-04-30 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
19 | XXXX | Procurement of Electrical Cabling, Fixtures & Fittings | Supply and Delivery of materials to replace electrical fittings and fixtures | 39121700 | 2024-03-31 | 2024-05-31 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
20 | XXXX | Procurement of Mini Split Units | Supply and Installation of Mini Split Units | 72151200 | 2024-04-01 | 2024-06-01 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
21 | XXXX | Procurement of Automated Gate | Supply and Installation of Barrier Gate |  | 2024-04-02 | 2024-06-02 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
22 | XXXX | Renovation Works to Maintenance La Brea Sub-Office |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
23 | XXXX | Procurement of Service for Termite Treatment | Provision of Service for Treatment of Termite | 10191700 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
24 | XXXX | Procurement of Materials for Internal and External Renovations | Supply and Delivery of materials for Internal and External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
25 | XXXX | Procurement of Plumbing Materials for Repairs | Supply and Delivery of materials to replace Plumbing fittings and fixtures | 72151100 | 2024-02-29 | 2024-04-30 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
26 | XXXX | Procurement of Electrical Cabling, Fixtures & Fittings | Supply and Delivery of materials to replace electrical fittings and fixtures | 39121700 | 2024-03-31 | 2024-05-31 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
27 | XXXX | Procurement of Mini Split Units | Supply and Installation of Mini Split Units | 72151200 | 2024-04-01 | 2024-06-01 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
28 | XXXX | Renovation Works to Maintenance Carenage Sub-Office |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
29 | XXXX | Procurement of Materials for Internal and External Renovations | Supply and Delivery of materials for Internal and External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
30 | XXXX | Procurement of Plumbing Materials for Repairs | Supply and Delivery of materials to replace Plumbing fittings and fixtures | 72151100 | 2023-11-01 | 2024-01-31 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
31 | XXXX | Procurement of materials for Fencing and External Works | Supply and Delivery of materials for Fencing and External Works | 72101500 | 2024-01-31 | 2024-03-31 | 28 days | Limited Bidding | 10 working days | Fixed Term Contract
32 | XXXX | Renovation Works to Drainage Pump Houses Bamboo Settlement #3 |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
33 | XXXX | Procurement of Materials for Internal and External Renovations | Supply and Delivery of materials for Internal and External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
34 | XXXX | Renovation Works to Drainage Pump Houses Calco Tulsa Trace, Penal |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
35 | XXXX | Procurement of Materials for Internal and External Renovations | Supply and Delivery of materials for Internal and External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
36 | XXXX | Renovation Works to Drainage Pump Houses Pump Site #5 Trinidad Point, Sluice Gate, Woodland |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
37 | XXXX | Procurement of Materials for Internal Renovations | Supply and Delivery of materials for Internal Renovations | 72101500 | 2024-01-31 | 2024-03-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
38 | XXXX | Procurement of Materials for External Works | Supply and Delivery of materials for External Works | 72101500 | 2024-03-31 | 2024-05-31 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
39 | XXXX | External Works, Agua Santa Batching Plant, Wallerfield |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
40 | XXXX | Procurement of Materials for External Renovations | Supply and Delivery of materials for External Renovations | 72101500 | 2024-04-01 | 2024-06-01 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
41 | XXXX | Mechanical Services Compound - Fencing |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
42 | XXXX | Procurement of Materials for External Renovations | Supply and Delivery of materials for External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
43 | XXXX | Renovation Works to St. George West/East District Office, Farm Road, St. Joseph |  | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 |  | Limited Bidding | 10 working days | Fixed Term Contract
44 | XXXX | Procurement of Materials for Ancillary Service | Supply and Delivery of materials for Ancillary Service | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
45 | XXXX | Procurement of Service for Termite Treatment | Provision of Service for Treatment of Termite | 10191700 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
46 | XXXX | Procurement of Materials for Internal and External Renovations | Supply and Delivery of materials for Internal and External Renovations | 72101500 | 2023-11-01 | 2024-01-31 | 14 days | Request for Quotations | Not applicable | Invoice/ Quotation
47 | XXXX | Procurement of Plumbing Materials for Repairs | Supply and Delivery of materials to replace Plumbing fittings and fixtures | 72151100 | 2023-10-31 | 2023-12-31 | 28 days | Request for Quotations | Not applicable | Invoice/ Quotation
48 | XXXX | Procurement of Electrical Cabling, Fixtures & Fittings | Supply and Delivery of materials to replace electrical fittings and fixtures | 39121700 | 2023-10-31 | 2023-12-31 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation
49 | XXXX | Procurement of Mini Split Units | Supply and Installation of Mini Split Units | 72151200 | 2024-04-01 | 2024-06-01 | 56 days | Request for Quotations | Not applicable | Invoice/ Quotation

## Mechanical Services Division
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Mechanical Services Division
No. | Project Number |  | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 02/006/03 - 001 Monthly Paid Staff | Uniform | To purchase P.P.E., shirt, pants, shoes, helmets, gloves, masks, respirators, goggles, boots. Etc for Mothly Paid Staff | 46180000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 13-15 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
2 | 02/006/03 - 002 DailyPaid Staff | Uniform | To purchase P.P.E., shirt, pants, shoes, helmets, gloves, masks, respirators, goggles, boots. Etc for Daily Paid Staff | 46180000 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 13-15 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
3 | 02/006/03 - 002 Other P.P.E. | Uniform | To purchase any other P.P.E. | 46180000 | Apr. - Jun. 2024 | Apr. - Jun. 2024 | 13-15 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
4 | 02/006/10 | Office Stationery and Supplies | To purchase office consumables, cleaning supplies, garbage bags, hand cleaner, soap, toilet paper, pharmaceuticals, ink toner, imaging unit and bottle water. | 44120000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
5 | 02/006/12 - 001 Machine Shop Tools & Consumables: Welding & Plate Section | Materials and Supplies | To purchase machine shop consumables, welding tools and plate sections, electrical materials and tools, tyre tools and repair material, carpentry tools and materials, equipment bay tools and materials. | 27000000 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
6 | 02/006/12 - 002 Machine Shop Tools & Consumables: Autobody Section | Materials and Supplies | To purchase machine shop consumables, and fittings, welding tools and plate sections, electrical materials and tools, tyre tools and repair material, carpentry tools and materials, equipment bay tools and materials. | 27000000 | Apr. - Jun. 2024 | Apr. - Jun. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
7 | 02/006/12 - 003 Machine Shop Tools & Consumables: Machine and Fitting Sections | Materials and Supplies | To purchase machine shop consumables, and fittings, electrical materials and tools, tyre tools and repair material, carpentry tools and materials, equipment bay tools and materials. | 27000000 | July - Sept. 2024 | July - Sept. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
8 | 02/006/13 - 001 Excavators | Maintenance of Excavators | To purchase all parts for Excavators to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Excavators for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. | 78181500 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 6-8 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
9 | 02/006/13 - 002 Backhoes | Maintenance of Backhoes | To purchase all parts for Backhoes to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Backhoes for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. | 78181500 | Apr. - Jun. 2024 | Apr. - Jun. 2024 | 6-8 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
10 | 02/006/13 - 003 Rollers and Skid Steer | Maintenance of Rollers and Skid Steer | To purchase all parts for Rollers and Skid Steers to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Rollers and Skid Steer for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. | 78181500 | July - Sept. 2024 | July - Sept. 2024 | 6-8 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
11 | 02/006/13 - 004 Light Trucks, SUVs, Trucks, Trailers and other Heavy Equipment | Maintenance of Light Trucks, SUVs, Trucks, Trailers and other Heavy Equipment | To purchase all parts for Light Trucks, SUVs, Trucks, Trailers and other Heavy Equipment to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Light Trucks, SUVs, Trucks, Trailers and other Heavy Equipment for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. | 78181500 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 6-8 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
12 | 02/006/15 - 001 Pumps | Repair and Maintenance of Pumps | To purchase all parts for pumps to conduct preventive maintenance, such as oil and filters. To purchase parts for pumps for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to Pumps. | 40151700 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
13 | 02/006/15 - 002 Copiers | Repair and Maintenance of copiers | To pay charges associated with materials/parts needed to service/repair photocopiers | 81112306 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
14 | 02/006/15 - 003 Scanners | Repair and Maintenance of Scanners | To pay charges associated with materials/parts needed to service/repair scanners. | 81112306 | Apr. - Jun. 2024 | Apr. - Jun. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
15 | 02/006/15 - 004 Communication Radios | Repair and Maintenance of Communication Radios | To pay charges associated with materials/parts needed to service/repaircommunication radios. | 81112306 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
16 | 02/006/21 - 001 Repair and Maintenance | Other Contracted Services | To pay charges associated with building repairs/maintenance/installation of plumbing, AC, lighting, ventilation, washroom, gates, wash stations, extractor fans, lighting (garage, workshop and administration), wash bay, stores etc. | 72152601 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
17 | 02/006/28 - 002 Grounds Staff | Other Contracted Services | To pay charges associated with service, installation and maintenance/repair cost by other contracted services. For example Grounds Staff | 72152601 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
18 | 02/006/37 | Janitorial Services | To pay charges associated with janitorial maintenance and sanitation organizations. | 76110000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
19 | 02/006/96 - 001 Bulk Fuel | Fuel and Lubricants | To purchase diesoline, gasoline (in Bulk) and renew flee cards.. | 15000000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
20 | 02/006/96 - 002 Lubrication and Greases | Fuel and Lubricants | To purchase multiple grades of engine oil, hydraulic fluid, transmission and gearbox fluid, brake fluid, grease and engine coolant. | 15000000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Sole Select | Not applicable | Not applicable
21 | 02/006/96 - 003 Fleet Cards | Fuel and Lubricants | To e renew flee cards. | 15000000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Sole Select | Not applicable | Not applicable
22 | 02/006/96 - 004 Other Fluids | Fuel and Lubricants | To purchase multiple grades of engine oil, hydraulic fluid, transmission and gearbox fluid, brake fluid and engine coolant. | 15000000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
23 | 03/006/01 - 001 Barge | Vehicle Replacement | To purchase replacement vehicles/equipment. For example barges. | 25111507 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 9 Months | Request for Quotations | Not applicable | Invoice/ Quotation
24 | 03/006/01 - 002 SUVs & Pick Ups | Vehicle Replacement | To purchase replacement vehicles/equipment. For example SUVs and CNG Double Cab Pick Ups. | 25101507 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 6-8 weeks | Limited Bidding | 10 Days | Fixed Term Contract
25 | 03/006/01 - 003 Dump Trucks & Trailers | Vehicle Replacement | To purchase replacement vehicles/equipment. For example trailers, trucks etc. | 25101601 | Apr. - Jun. 2024 | Apr. - Jun. 2024 | 6-8 weeks | Open Bidding | 10 Days | Fixed Term Contract
26 | 03/006/01 - 004 Hybrid/Electric Cars | Vehicle Replacement | To purchase replacement vehicles/equipment. For example Hybrid/Electric cars. | 25101509 | July - Sept. 2024 | July - Sept. 2024 | 6-8 weeks | Limited Bidding | 10 Days | Fixed Term Contract
27 | 03/006/01 - 005 - Excavators | Vehicle Replacement | To purchase replacement vehicles/equipment. For example excavators. | 22101500 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 6-8 weeks | Open Bidding | 10 Days | Fixed Term Contract
28 | 03/006/04 - 001 Truck Mounted Crane | Mechanical Equipment | To purchase one new truck mounted, long reach, articulated crane. | 22101900 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 10 months | Open Bidding | 10 Days | Fixed Term Contract
29 | 03/006/02 - 001 Photocopiers | Office Equipment | To purchase office equipment. For example, photocopiers. | 44000000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
30 | 03/006/02 - 002 Cabinets | Furniture and Furnishings | To purchase office furniture and furnishing. For example filing cabinets . | 56000000 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
31 | 03/006/02 - 003 Chairs | Furniture and Furnishings | To purchase office furniture and furnishing. For example office chairs. | 56000000 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
32 | 03/006/04 - 001 Workshop Equipment | Mechanical Equipment | To purchase minor equipment for the division's garage, workshop or administration. For example, trolley jacks, bench vice, pressure washer, grinder and drill. | 44100000 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
33 | 03/006/04 - 002 Wash Pump | Mechanical Equipment | To purchase minor equipment for the division's garage, workshop or administration. For example wash pump.. | 44100000 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
34 | 03/006/04 - 003 Workshop Comsumables | Mechanical Equipment | To rent/ refill acetylene, oxygen and propane cylinders. | 40151500 | Oct. - Dec. 2023 | Oct. - Dec. 2023 | 2-3 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
35 | 03/006/04 - 004 Lighting Tower | Furniture and Furnishings | To purchase minor equipment for the division's garage, workshop or administration For example lighting towers. | 44100000 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 6-8 weeks | Request for Quotations | Not applicable | Invoice/ Quotation

## Procurement
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Procurement Unit
No. | Project Number | Project Name | Brief Description | UNSPEC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 02 Office Equipment | Purchase of Office Equipment -Photocopier for the Procurement Unit | Purchase of new Coloured Photocopier for the Procurement Unit | 44100000 | 2024-02-01 | 2024-04-01 | 90 days | Three Quotation system | Not applicable | Invoice
2 | 02 Office Equipment | Purchase of Office Equipment – Desk top computers | Purchase of Desk top printers for use in the Procurement Unit. | 44100000 | 2024-04-01 | 2024-07-01 | 90 days | Three Quotation system | Not applicable | Invoice
3 | 02 Office Equipment | Purchase of Desktop printers | Purchase of Stationery and Supplies | 44100000 | 2024-02-01 | 2024-06-01 | 90 days | Three Quotation system | Not applicable | Invoice
4 | 04 Furniture and Furnishings | Purchase of Conference Table and Chairs | The purchase of one Conference Table and executive chairs for Conference Room | 56000000 | 2024-04-01 | 2024-07-01 | 90 days | Three Quotation system | Not applicable | Invoice
5 | 04 Furniture and Furnishings | Purchase of Laminated top Steel Desks | The purchase of Laminated top Steel Desks for the Procurement Unit | 56000000 | 2024-04-01 | 2024-07-01 | 90 days | Three Quotation system | Not applicable | Invoice
6 | ITC Department | Upgrade of Computers to facilitate E-Tendering | Upgrade of computers for the Procurement Unit via the ITC Department. The purchase of 6 laptop computers. | 81112202 | 2024-04-01 | 2024-07-01 | 90 days | Request for Proposal | Not applicable | Tender
7 | 10 Stationery and Supplies | Purchase of Stationery and Supplies | Purchase of Standing Desktop computers for use in the Procurement Unit | 44120000 | 2024-02-01 | 2024-03-01 | 31 days | Three Quotation system | Not applicable | Invoice
8 | 10 Office Stationery and Supplies | Purchase of Archival Boxes | Purchase of Chemical Free Archival Boxes for storage of Tender Documents. | 44120000 | 2024-02-01 | 2024-03-01 | 31 days | Three Quotation system | Not applicable | Invoice
9 | 11 Books and Periodicals | Purchase of Law Books | Purchase of New Legislative Acts and regulations governing the rules of Procurement Activities. | 141111800 | 2024-02-01 | 2024-03-01 | 31 days | Three Quotation system | Not applicable | Invoice
10 | 12 Materials and Supplies | Purchase of Wheel Truck | Purchase of Wheel Truck for transporting of Tender boxes and documents for Evaluation exercises. | 24101706 | 2024-03-01 | 2024-03-01 | 21 days | Three Quotation system | Not applicable | Invoice
11 | 28 Other Contracted Services | The Supply and Installation of Blinds for the Procurement Unit | Supply and Installation of Blinds for the Procurement Unit | 52131600 | 2024-01-01 | 2024-03-01 | 90 days | Request for Quotations | Not applicable | Quotations

## PMEU
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Programme Monitoring and Evaluation Unit (PMEU)
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 43/02/011/03 | Supply Safety Wear and Supplies | 46180000 | 2023-11-01 | 2023-11-01 | 1 mth | Open Bidding | Not applicable | Fixed Price
2 | 43/02/011/05 | Telephone Services ftp: 15 Sep 23 - 14 Sep 24 (payment of bills) | 83111501 | Not applicable | Not applicable | Not applicable | Sole Select | Not applicable | Not applicable
3 | 43/02/011/10 | Supply Office Stationery and Supplies | 14111509 | 2023-11-01 | 2023-11-01 | 1 mth | Request for Quotations | Not applicable | Invoice/ Quotation
4 | 43/02/011/11 | Renewal of Newspapers Subscription | 14111800 | 2023-11-01 | 2023-11-01 | 1 mth | Request for Quotations | Not applicable | Invoice/ Quotation
5 | 43/02/011/13 | Service and Repairs of 2 vehicles | 78181500 | 2023-12-01 | 2023-12-01 | 3 mths | Request for Quotations | Not applicable | Invoice/ Quotation
6 | 43/02/011/15 | Maintenance and Repairs of Office Equiment | 81112306 | 2023-12-01 | 2023-12-01 | 3 mths | Request for Quotations | Not applicable | Invoice/ Quotation
7 | 43/02/011/21 | Repairs and Maintenance of Office Building | 72101500 | 2023-11-01 | 2023-11-01 | 1 mth | Request for Quotations | Not applicable | Invoice/ Quotation
| 43/02/011/37 | Provision of sanitary bins | 76110000 | 2023-11-01 | 2023-11-01 | 1 mth | Open Bidding | 10 Days | Fixed Term Contract
8 | 43/02/011/43 | Provision of security services ftp: Oct 23 - Sep 24 (payment of bills) | 92120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
| 43/02/011/96 | Purchase of Lubricants for vehicles | 15000000 | 2023-11-01 | 2023-11-01 | 1 mth | Request for Quotations | Not applicable | Invoice/ Quotation
9 | 43/03/011/02 | Supply of Office Equipment: Laptops, Smart Board, UPS Surge Protectors, Technical Computers, Desktop Printers, Filing Cabinets and other equipment | 44000000 | 2023-11-01 | 2024-02-01 | 3 mths | Request for Quotations | Not applicable | Invoice/ Quotation
10 | 43/03/011/03 | Supply of hand dryer, television, coffee brewer, desks, executive chairs and other office furniture | 44100000 | 2023-11-01 | 2024-02-01 | 3 mths | Request for Quotations | Not applicable | Invoice/ Quotation
11 | 43/03/011/04 | Supply of inks and toners, electric kettle, digital camera with memory card, aerial mappying drone, microwave and other minor equipment and small appliances | 44100000 | 2023-11-01 | 2024-02-01 | 3 mths | Request for Quotations | Not applicable | Invoice/ Quotation
701 -INFRASTRUCTURE DEVELOPMENT FUND
1 | POS East / West Corridor Transportation Project - 701/43/003/15/D/260 | Macoya Interchange, Ramps and Roundabouts (Design/Build)- 1 Package - Design Services | 81101510 | 2024-04-01 | Sep 2024/Aug 2025 | 12mths | Open Bidding | 10 working days | Fixed Price
4 | POS East / West Corridor Transportation Project - 701/43/003/15/D/260 | Macoya Interchange - Frontage Roads (Design/Bid/Build - 3 Packages) | 72141000 | 2024-04-01 | Sep 2024/Aug 2025 | 24 mths | Open Bidding | 10 working days | Fixed Price
5 | POS East / West Corridor Transportation Project - 701/43/003/15/D/260 | NTMS - NATIONAL TRAFFIC MANAGEMENT SYSTEMNTMS - System Expansion CTMS & TSCS from UBH/CRH to Piarco and UBH/CRH to Couva - Consultancy Services for the Design & Integration | 81101510 | 2024-04-01 | Sep 2024/Aug 2025 | 12mths | Open Bidding | 10 working days | Fixed Price
6 | POS East / West Corridor Transportation Project - 701/43/003/15/D/260 | NTMS - NATIONAL TRAFFIC MANAGEMENT SYSTEM-SPOT SPEED ENFORCEMENT SYSTEM - Port-of-Spain Traffic Study Consultancy Services | 81102201 | 2024-04-01 | Sep 2024/Aug 2025 | 12mths | Open Bidding | 10 working days | Fixed Price
6 | POS East / West Corridor Transportation Project - 701/43/003/15/D/260 | Port of Spain Traffic Study - Consultancy Services | 81102201 | 2024-04-01 | Sep 2024/Aug 2025 | 6 mths | Two-Stage Bidding | 10 working days | Fixed price

## PURE 1
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Expenses of the Project Management Unit, Programme for Upgrading Roads Efficiency
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
CAPITAL EXPENDITURE
1 | XXXX | Office Supplies | Supply and Delivery of Stationary and other required supplies | 14111509 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
2 | XXXX | Software Licenses | Supply of Various Software Licenses | 43230000 | 2023-04-01 | 2023-05-01 | 7 days | Subscription Renewal | Not applicable | Fixed Price Contract
3 | XXXX | Books and Periodicals | Supply of Books and Periodicals | 14111800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
4 | XXXX | Training | Training programmes for Staff | 86100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
5 | XXXX | Tools and Equipment | Supply of Required Equipment for Unit | 27000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
6 | XXXX | Personal Protection Equipment | Supply of Personal Protection Equipment | 46180000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
PSIP /CF/IDF
1 | XXXX | Almond Drive [Drainage & Road Works] Off De Norbriga, Morvant | Road Rehabilitation Works | 72141000 | 2023-06-07 | 2024-01-01 | 60 days | Limited Bidding | 10 working days | Unit Price
2 | XXXX | Aranguez Main Road [Road Works] From Delta Glass to Np Gas Station | Road Rehabilitation Works | 72141000 | 2024-05-01 | 2024-06-01 | 10 days | Limited Bidding | 10 working days | Unit Price
3 | XXXX | Arena Road [Concrete, Drainage & Road Works] Brazil | Road Rehabilitation Works | 72141000 | 2023-06-21 | 2024-02-01 | 60 days | Limited Bidding | 10 working days | Unit Price
4 | XXXX | Balata Hill Road [Slope Stabilization & Associated Works] 0km - 2.8km | Slope Stabilization Works | 77111603 | 2024-06-01 | 2024-08-31 | 60 days | Limited Bidding | 10 working days | Unit Price
5 | XXXX | Barataria Ramp and Underpass Upgrade Barataria | Traffic Management Measure | 46161500 | 2024-04-01 | 2024-07-31 | 90 days | Limited Bidding | 10 working days | Unit Price
6 | XXXX | Biche Ortoire [Slope Stabilization & Associated Works] 0.0 - 1.0 km | Slope Stabilization Works | 77111603 | 2024-04-01 | 2024-06-30 | 60 days | Limited Bidding | 10 working days | Unit Price
7 | XXXX | Biljah Road [Road Rehabilitation] Off Caroni Savannah Road | Road Rehabilitation Works | 72141000 | 2023-11-01 | 2023-12-01 | 20 days | Limited Bidding | 10 working days | Unit Price
8 | XXXX | Blanchisseuse Road [Concrete Works - Package 13] Ch 3+000 to 4+500 | Road Rehabilitation Works | 72141000 | 2024-05-01 | 2024-07-01 | 30 days | Limited Bidding | 10 working days | Unit Price
9 | XXXX | Blanchisseuse Road [Roadworks - Package 12] Ch 1+500 to 3+000 | Road Rehabilitation Works | 72141000 | 2024-04-01 | 2024-06-01 | 30 days | Limited Bidding | 10 working days | Unit Price
10 | XXXX | Bon Air Road [Slope Stabilization & Associated Works] 0-3.2km | Slope Stabilization Works | 77111603 | 2024-01-01 | 2024-03-01 | 30 days | Limited Bidding | 10 working days | Unit Price
11 | XXXX | Bosierre Trace (Bridge Reconstruction) Off Gran Couva Main Road | Bridge Works | 72141107 | 2024-02-01 | 2024-08-31 | 181 days | Limited Bidding | 10 working days | Unit Price
12 | XXXX | Bowen Street [Road Rehabilitation] From Eastman Street to Sapodilla Street, Tunapuna | Road Rehabilitation Works | 72141000 | 2023-07-20 | 2023-11-01 | 10 days | Limited Bidding | 10 working days | Unit Price
13 | XXXX | Buen Intento Road [Roadworks] 1.0km - 3.5km Goupal Rd | Road Rehabilitation Works | 72141000 | 2024-06-01 | 2024-07-01 | 20 days | Limited Bidding | 10 working days | Unit Price
14 | XXXX | Cantaro Extension [Road Rehabilitation] From Saddle Road to Maraj Trace | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2023-11-01 | 10 days | Limited Bidding | 10 working days | Unit Price
15 | XXXX | Cap de Ville to Erin [RR - Package 4] To Be Determined | Road Rehabilitation Works | 72141000 | 2024-08-01 | 2024-09-01 | 20 days | Limited Bidding | 10 working days | Unit Price
16 | XXXX | Caparo Brasso Valley Road [Road Rehabilitation] - Phase 2 Depot Road to Ravine Sable Road | Road Rehabilitation Works | 72141000 | 2023-12-01 | 2024-01-01 | 15 days | Limited Bidding | 10 working days | Unit Price
17 | XXXX | Caparo Brasso Valley Road [Road Rehabilitation] - Phase 3 From KFC to Depot Road | Road Rehabilitation Works | 72141000 | 2024-01-01 | 2024-02-01 | 20 days | Limited Bidding | 10 working days | Unit Price
18 | XXXX | Carli Bay Road [Road Works] 0km - 2km Chins Supermarket to Carli Bay Fishing Facility | Road Rehabilitation Works | 72141000 | 2024-06-01 | 2024-07-01 | 15 days | Limited Bidding | 10 working days | Unit Price
19 | XXXX | Cayman Avenue [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
20 | XXXX | Cedar Hill Road (Patching Works) | Road Rehabilitation Works | 72141000 | 2024-02-01 | 2024-03-01 | 5 days | Limited Bidding | 10 working days | Unit Price
21 | XXXX | Chickland Caparo Road [Road Works] 0km - 2km Arena Road to Caparo Valley Brasso Road | Road Rehabilitation Works | 72141000 | 2024-07-01 | 2024-08-01 | 10 days | Limited Bidding | 10 working days | Unit Price
22 | XXXX | Church Hill Extension [Road Rehabilitation] Off Bushe Street, San Juan | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
23 | XXXX | Churchill Roosevelt Highway - Construction of 3rd Lane - Eastbound From Andrew Lane to O'Meara Road | Traffic Management Measure | 46161500 | 2023-11-03 | 2024-07-31 | 240 days | Limited Bidding | 10 working days | Unit Price
24 | XXXX | Cipero Road [Slope Stabilization & Associated Works] 1km - 12km Retrench (connector Junction) to Health centre | Slope Stabilization Works | 77111603 | 2024-05-01 | 2024-07-31 | 60 days | Limited Bidding | 10 working days | Unit Price
25 | XXXX | Cunapo Southern Road [Road Rehabilitation - Patching] Plum Mitan Road to Tabaquite Road | Road Rehabilitation Works | 72141000 | 2024-06-01 | 2024-08-01 | 30 days | Limited Bidding | 10 working days | Unit Price
26 | XXXX | Cunapo Southern/ Charuma Junction Road [Slope Stabilization] 12km length Cushe to Tabaquite Rio | Slope Stabilization Works | 77111603 | 2024-06-01 | 2024-08-31 | 60 days | Limited Bidding | 10 working days | Unit Price
27 | XXXX | Dove Lane [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
28 | XXXX | El Socorro Road [Road Works] From Aranguez-El Socorro Access Road to Railway Road | Road Rehabilitation Works | 72141000 | 2024-05-01 | 2024-06-01 | 10 days | Limited Bidding | 10 working days | Unit Price
29 | XXXX | Finch Drive [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
30 | XXXX | First Street Extension [Drainage & Road Works] Off First Street, Mt Lambert | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-05-01 | 60 days | Limited Bidding | 10 working days | Unit Price
31 | XXXX | Fisher & Moore Avenue [Road Rehabilitation] Off St. Ann's Road | Road Rehabilitation Works | 72141000 | 2023-07-12 | 2023-12-01 | 10 days | Limited Bidding | 10 working days | Unit Price
32 | XXXX | Flamingo Avenue [Road Rehabilitation Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
33 | XXXX | Garth Road (Bridge Reconstruction) Scale Road Junction | Bridge Works | 72141107 | 2024-03-01 | 2024-09-30 | 180 days | Limited Bidding | 10 working days | Unit Price
34 | XXXX | Garth Road [Roadworks] 1.5km - 3.5km Brothers Road Presbterian school to Radicas Roti Shop | Road Rehabilitation Works | 72141000 | 2024-01-01 | 2024-02-01 | 20 days | Limited Bidding | 10 working days | Unit Price
35 | XXXX | Golden Grove Road [Road Works] Off Eastern Main Road, Arouca | Road Rehabilitation Works | 72141000 | 2024-06-01 | 2024-07-01 | 15 days | Limited Bidding | 10 working days | Unit Price
36 | XXXX | Gran Couva Main Road [Roadworks - Package 2] 13km length From Highway to Caparo Valley Road | Road Rehabilitation Works | 72141000 | 2024-03-01 | 2024-05-01 | 30 days | Limited Bidding | 10 working days | Unit Price
37 | XXXX | Grand Curacaye Road [Concrete, Drainage & Road Works] Off Saddle Road, Santa Cruz | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-02-01 | 60 days | Limited Bidding | 10 working days | Unit Price
38 | XXXX | Granville Road [Slope Stabilization] 0km - 4.5km From SMR 106.225 to Granville Beach | Slope Stabilization Works | 77111603 | 2024-04-01 | 2024-06-30 | 60 days | Limited Bidding | 10 working days | Unit Price
39 | XXXX | Grasshopper Lane [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
40 | XXXX | Guapo Cap-de-Ville Road [Roadworks] 0km - 4km From Chunilal Trace | Road Rehabilitation Works | 72141000 | 2024-03-01 | 2024-04-01 | 20 days | Limited Bidding | 10 working days | Unit Price
41 | XXXX | Heights of Guanapo [Slope Stabilization] 0-12km | Slope Stabilization Works | 77111603 | 2024-05-01 | 2024-07-31 | 60 days | Limited Bidding | 10 working days | Unit Price
42 | XXXX | Hermitage Road [Roadworks] 0.0km to 4.8km From KFC St Margrets Junction to Macaulay Flyover | Road Rehabilitation Works | 72141000 | 2024-04-01 | 2024-05-01 | 20 days | Limited Bidding | 10 working days | Unit Price
43 | XXXX | Hermitage Road Union Village (Bridge Reconstruction) Claxton Bay, near Union Presbyterian School | Bridge Works | 72141107 | 2024-02-01 | 2024-08-31 | 180 days | Limited Bidding | 10 working days | Unit Price
44 | XXXX | Hillcrest View [Drainage & Road Works] Off La Canoa Road, Saddle Road, Santa Cruz | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-04-01 | 60 days | Limited Bidding | 10 working days | Unit Price
45 | XXXX | Hillview Road [Drainage & Road Works] Off 6th Avenue, Malick | Road Rehabilitation Works | 72141000 | 2023-07-12 | 2024-02-01 | 60 days | Limited Bidding | 10 working days | Unit Price
46 | XXXX | Hirondelle Street [Drainage & Road Works] Off Lady Young Road, Morvant | Road Rehabilitation Works | 72141000 | 2023-07-12 | 2024-04-01 | 60 days | Limited Bidding | 10 working days | Unit Price
47 | XXXX | Hutchinson Drive [Road Works] La Romaine | Road Rehabilitation Works | 72141000 | 2023-07-19 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
48 | XXXX | Ibis Drive [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
49 | XXXX | Improvement to Endeavour Interchange - Phase 2 (Chaguanas Traffic Alleviation) In the vicinity of Mulchan Seuchan Road | Traffic Management Measure | 46161500 | 2024-02-02 | 2024-08-31 | 180 days | Limited Bidding | 10 working days | Unit Price
50 | XXXX | Jackson Street & Hislop Street [Drainage & Road Works] Off Eastern Main Road & Off Real Street | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-03-01 | 60 days | Limited Bidding | 10 working days | Unit Price
51 | XXXX | KP Lands - La Platta Gardens [Road Rehabilitation] Off Eastern Main Road, Valencia | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
52 | XXXX | La Seiva Road [Road Rehabilitation] From Toco Main Road to Foster Road | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-03-01 | 20 days | Limited Bidding | 10 working days | Unit Price
53 | XXXX | Laventille Extension Road [Road Rehabilitation] From St. Francois Valley Road to Mon Repos | Road Rehabilitation Works | 72141000 | 2023-07-12 | 2024-03-01 | 20 days | Limited Bidding | 10 working days | Unit Price
54 | XXXX | Lemon Drive [Road Works] Off Mendez Drive, Champ Fleurs | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
55 | XXXX | Lopinot Road [Road Rehabilitation] From Dunderhill to Xandu Resort | Road Rehabilitation Works | 72141000 | 2023-08-02 | 2024-02-01 | 20 days | Limited Bidding | 10 working days | Unit Price
56 | XXXX | Lopinot Road [Road Works - Package 2] 0-13km | Road Rehabilitation Works | 72141000 | 2024-06-01 | 2024-07-01 | 20 days | Limited Bidding | 10 working days | Unit Price
57 | XXXX | Lopinot Road [Slope Stabilization - Package 1] LP 26 | Slope Stabilization Works | 77111603 | 2024-05-01 | 2024-08-15 | 75 days | Limited Bidding | 10 working days | Unit Price
58 | XXXX | Lopinot Road [Slope Stabilization - Package 2] LP 29 | Slope Stabilization Works | 77111603 | 2024-05-01 | 2024-08-15 | 75 days | Limited Bidding | 10 working days | Unit Price
59 | XXXX | LP# 154 to LP# 157 Lopinot Road [Road Works] La Pastora | Road Rehabilitation Works | 72141000 | 2023-08-02 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
60 | XXXX | LP# 159 San Francisco Road [Road Works] La Pastora | Road Rehabilitation Works | 72141000 | 2023-08-02 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
61 | XXXX | LP# 180 to LP# 172 Lopinot Road [Drainage & Road Works] La Pastora | Road Rehabilitation Works | 72141000 | 2023-08-02 | 2024-05-01 | 60 days | Limited Bidding | 10 working days | Unit Price
62 | XXXX | LP# 68 Mayo Rd [Slope Stabilization & Associated Works] Mayo Road | Slope Stabilization Works | 77111603 | 2023-07-11 | 2024-06-01 | 90 days | Limited Bidding | 10 working days | Unit Price
63 | XXXX | LP162 to LP168 San Francisco Road [Road Rehabilitation] La Pastora | Road Rehabilitation Works | 72141000 | 2023-08-02 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
64 | XXXX | M2 Ring Road [Slope Stabilization] 8.0 km to 15.39 km Picton Road Junction to Manahambre Road Junction | Slope Stabilization Works | 77111603 | 2024-06-01 | 2024-09-15 | 75 days | Limited Bidding | 10 working days | Unit Price
65 | XXXX | Mahogany Drive [Road Works] Off Samaan Drive, Olton Road | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
66 | XXXX | Maingot Road [Road Rehabilitation] Off Tunapuna Road | Road Rehabilitation Works | 72141000 | 2023-07-20 | 2023-12-01 | 10 days | Limited Bidding | 10 working days | Unit Price
67 | XXXX | Manahambre Road [Road Rehabilitation] - Phase 3 TBD | Road Rehabilitation Works | 72141000 | 2024-02-01 | 2024-03-01 | 15 days | Limited Bidding | 10 working days | Unit Price
68 | XXXX | Maraval Access Road Upgrade [Bridge Reconstruction & Associated Works] Saddle Road, Maraval | Road Rehabilitation Works | 72141000 | 2023-07-20 | 2024-06-01 | 180 days | Limited Bidding | 10 working days | Unit Price
69 | XXXX | Matilda Road [Roadworks] From Matilda Junction to Moruga Rd | Road Rehabilitation Works | 72141000 | 2024-07-01 | 2024-08-01 | 20 days | Limited Bidding | 10 working days | Unit Price
70 | XXXX | Mausica Road South [Roadworks] From CRH to Carapo Road | Road Rehabilitation Works | 72141000 | 2024-01-01 | 2024-02-01 | 15 days | Limited Bidding | 10 working days | Unit Price
71 | XXXX | Mayaro Guayaguayare Road [Slope Stabilization] 9.5km-21km | Slope Stabilization Works | 77111603 | 2024-01-01 | 2024-04-16 | 75 days | Limited Bidding | 10 working days | Unit Price
72 | XXXX | Mayo Road [Roadworks] 0km - 4.6km Juction of Couva Road to Junction of Cedar Hill Road | Road Rehabilitation Works | 72141000 | 2024-06-01 | 2024-08-01 | 30 days | Limited Bidding | 10 working days | Unit Price
73 | XXXX | Mc Carthy Street [Road Rehabilitation] Off Cantaro Extension, Saddle Road, Santa Cruz | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
74 | XXXX | Morne Coco Road Slope Stabilization Pk2 Off Morne Coco Off Pionaire Drive | Slope Stabilization Works | 77111603 | 2024-02-01 | 2024-05-01 | 59 days | Limited Bidding | 10 working days | Unit Price
75 | XXXX | Naggee Road [Slope Stabilization] 1.85km -4.3km Opposite Lp# 42 | Slope Stabilization Works | 77111603 | 2024-07-01 | 2024-09-30 | 60 days | Limited Bidding | 10 working days | Unit Price
76 | XXXX | North Coast Road [Drainage Works] From Pillars to Maracas Bay | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-04-01 | 45 days | Limited Bidding | 10 working days | Unit Price
77 | XXXX | North Coast Road [Road Rehabilitation] From La Fillette to Blanchisseuse | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-01-01 | 20 days | Limited Bidding | 10 working days | Unit Price
78 | XXXX | North Coast Road [Road Works - Phase 1] From Pillars, Chainage 0+000 to 4+900 | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-01-01 | 30 days | Limited Bidding | 10 working days | Unit Price
79 | XXXX | North Coast Road [Road Works - Phase 2] From Chainage 4+900 to 7+400 | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-01-01 | 30 days | Limited Bidding | 10 working days | Unit Price
80 | XXXX | North Coast Road [Road Works - Phase 3] From Chainage 7+550 to 12+850 | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-01-01 | 30 days | Limited Bidding | 10 working days | Unit Price
81 | XXXX | North Manzanilla Road [Slope Stabilization] 0-5km | Slope Stabilization Works | 77111603 | 2024-06-01 | 2024-08-01 | 30 days | Limited Bidding | 10 working days | Unit Price
82 | XXXX | Oasis Gardens [Drainage Works] Off Northpost Road | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-02-01 | 45 days | Limited Bidding | 10 working days | Unit Price
83 | XXXX | Ojoe Road [Road Rehabilitation] Off Brierley Street, Sangre Grande | Road Rehabilitation Works | 72141000 | 2023-07-12 | 2024-01-01 | 15 days | Limited Bidding | 10 working days | Unit Price
84 | XXXX | Oliver Trace Extension [Road Works] Off William Street, Mt D'or | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
85 | XXXX | O'Meara Road North [Road Rehabilitation] Between O'Conner Street and PBR | Road Rehabilitation Works | 72141000 | 2024-03-01 | 2024-04-01 | 15 days | Limited Bidding | 10 working days | Unit Price
86 | XXXX | Parakeet Avenue [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
87 | XXXX | Paria Main Road [Slope Stabilization - Package 1] 0km - 6km, 25km-30km | Slope Stabilization Works | 77111603 | 2024-02-01 | 2024-05-31 | 90 days | Limited Bidding | 10 working days | Unit Price
88 | XXXX | Paria Main Road [Slope Stabilization - Package 2] 69.3 km mark | Slope Stabilization Works | 77111603 | 2024-06-01 | 2024-08-31 | 60 days | Limited Bidding | 10 working days | Unit Price
89 | XXXX | Paria Morne Bleu Road [Slope Stabilization] 0-6.4km | Slope Stabilization Works | 77111603 | 2024-01-01 | 2024-03-31 | 60 days | Limited Bidding | 10 working days | Unit Price
90 | XXXX | Park Street [Road Rehabilitation], Laventille Off Ariapita Avenue, Port of Spain | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2023-12-01 | 5 days | Limited Bidding | 10 working days | Unit Price
91 | XXXX | Park Street [Road Rehabilitation], POS Off Lady Young Road, Morvant | Road Rehabilitation Works | 72141000 | 2023-07-12 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
92 | XXXX | Penal Rock Road [Roadworks] 20km-25km | Road Rehabilitation Works | 72141000 | 2024-02-01 | 2024-03-01 | 20 days | Limited Bidding | 10 working days | Unit Price
93 | XXXX | Penal Rock Road [Slope Stabilization] Lp# 493 23.1km mark | Slope Stabilization Works | 77111603 | 2024-02-01 | 2024-04-30 | 60 days | Limited Bidding | 10 working days | Unit Price
94 | XXXX | Plum Mitan Road [Road Rehabilitation - Patching] From Manzanilla Mayaro Road to Cunapo Southern Main Road | Road Rehabilitation Works | 72141000 | 2024-02-01 | 2024-04-01 | 30 days | Limited Bidding | 10 working days | Unit Price
95 | XXXX | Point Fortin Road [Roadworks] 0km - 4km From Dunlop Roundabout to Atlantic LNG | Road Rehabilitation Works | 72141000 | 2024-06-01 | 2024-07-01 | 20 days | Limited Bidding | 10 working days | Unit Price
96 | XXXX | Ponta Rosa Drive & Good Will Drive [Road Rehabilitation] Off Bushe Street, Opposite Julie Field Road | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2023-11-01 | 10 days | Limited Bidding | 10 working days | Unit Price
97 | XXXX | Primus Street & Delaney Trace [Road Rehabilitation] Off Toco Main Road, Salybia | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
98 | XXXX | Ragoo Street [Road Rehabilitation] Off Meade Street | Road Rehabilitation Works | 72141000 | 2023-07-20 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
99 | XXXX | Rainbow Ridge [Road Works], Off Terracevale Road, Goodwood Avenue, Goodwood Park | Road Rehabilitation Works | 72141000 | 2024-01-01 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
100 | XXXX | Roads 1-5 North Eastern Settlement [Road Rehabilitation] Off Ojoe Road, Sangre Grande | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-11-01 | 10 days | Limited Bidding | 10 working days | Unit Price
101 | XXXX | Rupert Trace (Roadworks) Off Bellevue St James | Road Rehabilitation Works | 72141000 | 2024-01-01 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
102 | XXXX | Saddle Road [Roadworks] Febeau Village to Petit Boug | Road Rehabilitation Works | 72141000 | 2024-01-01 | 2024-02-01 | 15 days | Limited Bidding | 10 working days | Unit Price
103 | XXXX | Samuel Cooper [Slope Stabilization] 1.65km Near to area known as the "Dump" | Slope Stabilization Works | 77111603 | 2024-05-01 | 2024-07-31 | 60 days | Limited Bidding | 10 working days | Unit Price
104 | XXXX | Sangre Grande to Manzanilla [Road Rehabilitation, Road Widening & Culvert Reconstruction - Package 4] Chainage 6+000 to 8+000 | Traffic Management Measure | 46161500 | 2023-10-06 | 2024-09-01 | 300 days | Limited Bidding | 10 working days | Unit Price
105 | XXXX | Sangre Grande to Manzanilla [Road Rehabilitation, Road Widening & Culvert Reconstruction - Package 5] Chainage 8+000 to 10+000 | Traffic Management Measure | 46161500 | 2023-10-06 | 2024-09-01 | 300 days | Limited Bidding | 10 working days | Unit Price
106 | XXXX | Second Trace [Road Rehabilitation] Off Bagatelle Main Road, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
107 | XXXX | Sellier Street [Road Rehabilitation] From Frederick Street, Curepe | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2023-11-01 | 10 days | Limited Bidding | 10 working days | Unit Price
108 | XXXX | Siparia Road [Slope Stabilization] 0km - 11.782km From Oropouche Roundabout to Siparia Road Junction | Slope Stabilization Works | 77111603 | 2024-06-01 | 2024-09-30 | 90 days | Limited Bidding | 10 working days | Unit Price
109 | XXXX | Sir Solomon Hochoy Highway [Construction of Additional Lanes North & South from Chaguanas to Chase Village - Package 1] From Chainage 0+000 to 1+400 | Traffic Management Measure | 46161500 | 2023-08-22 | 2024-09-01 | 365 days | Limited Bidding | 10 working days | Unit Price
110 | XXXX | Sir Solomon Hochoy Highway [Construction of Additional Lanes North & South from Chaguanas to Chase Village - Package 2] From Chainage 1+400 to 3+400 | Traffic Management Measure | 46161500 | 2023-08-22 | 2024-09-01 | 365 days | Limited Bidding | 10 working days | Unit Price
111 | XXXX | Sisters Road [Roadworks] 3.5km-6.2km | Road Rehabilitation Works | 72141000 | 2024-08-01 | 2024-09-01 | 20 days | Limited Bidding | 10 working days | Unit Price
112 | XXXX | Smart Street [Road Rehabilitation] From Warren Street to Fraser Street | Road Rehabilitation Works | 72141000 | 2023-06-29 | 2024-05-01 | 10 days | Limited Bidding | 10 working days | Unit Price
113 | XXXX | Southern Main Road (Concrete Works) Pkg 2 Claxton Bay (Superfoods to TCL) | Road Rehabilitation Works | 72141000 | 2024-05-01 | 2024-07-01 | 45 days | Limited Bidding | 10 working days | Unit Price
114 | XXXX | Southern Main Road [Road Rehabilitation] From Alice Street to Church Street, La Romaine | Road Rehabilitation Works | 72141000 | 2023-07-19 | 2024-02-01 | 20 days | Limited Bidding | 10 working days | Unit Price
115 | XXXX | Southern Main Road [Road Works] 26km - 28km St Marys Junction to Beaucarro Road | Road Rehabilitation Works | 72141000 | 2024-05-01 | 2024-06-01 | 20 days | Limited Bidding | 10 working days | Unit Price
116 | XXXX | Southern Main Road 8km Savonetta to Petrotrin | Road Rehabilitation Works | 72141000 | 2023-11-01 | 2023-12-01 | 20 days | Limited Bidding | 10 working days | Unit Price
117 | XXXX | Southern Main Road Upgrade From HDC Development to Farm Road | Traffic Management Measure | 46161500 | 2024-05-01 | 2024-08-30 | 90 days | Limited Bidding | 10 working days | Unit Price
118 | XXXX | Southern Main Road, Cedros to Icacos [Road Rehabilitation - Package 2] | Road Rehabilitation Works | 72141000 | 2024-08-01 | 2024-09-01 | 20 days | Limited Bidding | 10 working days | Unit Price
119 | XXXX | Southern Main Road/ San Fernando Bye Pass [Roadworks] 3km Tarouba Roundabout to Point a Pierre Roundabout (gas station) | Road Rehabilitation Works | 72141000 | 2024-02-01 | 2024-03-01 | 20 days | Limited Bidding | 10 working days | Unit Price
120 | XXXX | SS Erin Road [Roadworks] 1Km to 5.5 Km Bennet Drive to Dumfries Road Junction | Road Rehabilitation Works | 72141000 | 2024-03-01 | 2024-04-01 | 20 days | Limited Bidding | 10 working days | Unit Price
121 | XXXX | SS Erin Road [Slope Stabilization] 18km Cotton Trace to Los Iros Junction | Slope Stabilization Works | 77111603 | 2024-04-01 | 2024-06-30 | 60 days | Limited Bidding | 10 working days | Unit Price
122 | XXXX | St Julien Road (Slope Stabilization 1) St Julien Road, LP #83 | Slope Stabilization Works | 77111603 | 2024-03-01 | 2024-05-31 | 60 days | Limited Bidding | 10 working days | Unit Price
123 | XXXX | Talparo Mundo Nuevo Road [Slope Stabilization] 0-9km | Slope Stabilization Works | 77111603 | 2024-03-01 | 2024-05-31 | 60 days | Limited Bidding | 10 working days | Unit Price
124 | XXXX | Thunderbird Lane [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
125 | XXXX | Tomato Trace [Road Works] Off Northpost Road, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-08-04 | 2024-02-01 | 10 days | Limited Bidding | 10 working days | Unit Price
126 | XXXX | Torrib Tabaquite Road [Slope Stabilization - Package 1] 0km-10km | Slope Stabilization Works | 77111603 | 2024-04-01 | 2024-06-30 | 60 days | Limited Bidding | 10 working days | Unit Price
127 | XXXX | Toucan Drive [Road Rehabilitation] Off River Estate Circular, Diego Martin | Road Rehabilitation Works | 72141000 | 2023-07-06 | 2024-01-01 | 10 days | Limited Bidding | 10 working days | Unit Price
128 | XXXX | Tumpuna Road (North) [Road Rehabilitation] | Road Rehabilitation Works | 72141000 | 2023-11-01 | 2024-01-01 | 30 days | Limited Bidding | 10 working days | Unit Price
129 | XXXX | Tumpuna Road Upgrade Arima | Traffic Management Measure | 46161500 | 2023-10-05 | 2024-09-30 | 330 days | Limited Bidding | 10 working days | Unit Price
130 | XXXX | Tunapuna Road [Road Rehabilitation] From Hendrickson Street to end of Tunapuna Road | Road Rehabilitation Works | 72141000 | 2023-07-20 | 2023-11-01 | 20 days | Limited Bidding | 10 working days | Unit Price
131 | XXXX | Upper Sea View Hill [Concrete Drainage, Road Works & Slope Stabilization] Off Abbe Pouja Road, Carenage | Slope Stabilization Works | 77111603 | 2024-06-01 | 2024-09-30 | 90 days | Limited Bidding | 10 working days | Unit Price
132 | XXXX | Uriah Butler Highway - Northbound [Road Rehabilitation] Between Chaguanas and Grand Bazaar | Road Rehabilitation Works | 72141000 | 2023-06-30 | 2024-02-01 | 30 days | Limited Bidding | 10 working days | Unit Price
133 | XXXX | Uriah Butler Highway - Southbound [Road Rehabilitation] Between Grand Bazaar and Chaguanas | Road Rehabilitation Works | 72141000 | 2023-06-30 | 2024-02-01 | 30 days | Limited Bidding | 10 working days | Unit Price
134 | XXXX | Waterloo Road [Road Works] 6.5km - 8.5km Waterloo Cremation Site to Orange Valley Bay Road | Road Rehabilitation Works | 72141000 | 2024-08-01 | 2024-09-01 | 15 days | Limited Bidding | 10 working days | Unit Price
135 | XXXX | Yaigual Road [Slope Stabilization] 0-2.4km | Slope Stabilization Works | 77111603 | 2024-07-01 | 2024-09-01 | 30 days | Limited Bidding | 10 working days | Unit Price

## TECU
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
TECU
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | XXXX | Uniforms | Purchase of Uniforms for Division | 53102700 | January, 2024 | March,2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
2 | XXXX | Electricity | Payment of Electricity Bills | 83101800 | October, 2023 | February, 2024 | Not applicable | Sole Select | Not applicable | Fixed Price
3 | XXXX | Telephones | Payment of Telephone Services | 83111501 | October, 2023 | January,2024 | Not applicable | Sole Select | Not applicable | Fixed Price
4 | XXXX | WASA | Payment of water rates | 83101500 | October, 2023 | January,2024 | Not applicable | Sole Select | Not applicable | Fixed Price
5 | XXXX | Office Stationery and Supplies | Purchase of Office Stationary | 44120000 | January, 2024 | March,2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
6 | XXXX | Books and Periodicals | Purchase of Books and Periodicals for the Division | 60102300 | January, 2024 | March,2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation
7 | XXXX | Materials and supplies | Purchase of Materials |  | November,2023 | February, 2024 | Not applicable | Request for Quotations | Not applicable | Invoice/ Quotation

## TMB
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Traffic Management Branch
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 02/003/03 | Uniforms | Purchase of personal protective equipment for daily rated staff (221), safety boots, welding gears, uniforms, safety hats, safety vests, respiratory masks etc, Payment of uniform allowance for monthly paid drivers | 53102700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
2 | 02/003/04 | Electricity | Payment for commercial, street lighting , traffic lights throughout Trinidad | 83101800 | Not applicable | Not applicable | Not applicable | Sole Select | Not applicable | Not applicable
3 | 02/003/05 | Telephone | Payment to Digicel for the Metro Link. Payment to Bmobile on account number 195012901005 and Data Sims. | 83111501 | Not applicable | Not applicable | Not applicable | Sole Select | Not applicable | Not applicable
4 | 02/003/10 | Office Stationery and Supplies | Purchase of cleaning items, toiletries, miscellaneous stationery items such as paper, ink, toners, staplers etc for all TMB Districts | 44120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request for 3 quotes | Not applicable | Invoice/ Quotation
5 | 02/003/06 | WASA | Pyments to WASA Jerningham Junction Cunupia and PBR Macoya | 83101500 | Not applicable | Not applicable | Not applicable | Sole Select | Not applicable | Not applicable
6 | 02/003/12 | Materials and Supplies | Purchase of road marking paint, (white and yellow), thermoplastic materials (blocks and beads), sign making material (aluminum sheets, shapes, pipes, tape), gravel, cement, controllers, mast arms |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
7 | 02/003/12 | Repairs and Maintenance Vehicles | Purchase of spare parts to repair fleet of twenty eight (28) vehicles | 78181500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
8 | 02/003/15 | Repairs and Maintence Equipment | Servicing and repairs to photocopiers, thermoplastic machines, premelter boilers, sign cutting machines, welding and drilling equipment | 81112306 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
9 | 02/003/17 | Training | Training for technical, clerical and administrative staff, daily rated employees, work ethics and conflict resolution | 86100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
10 | 02/003/21 | Repairs and Maintenance Buildings | Building repairs to TMB offices, tiles, plumbing, lighting fixtures, roofing etc | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
11 | 02/003/28 | Other Contracted Services | Payment for services of Traffic Signal Contractors - routine and non-routine maintenance of traffic lights and signals, new traffic signal installation, APS devices, road studs, loop detetectors, street furniture, zebra crossing, UPS | Not applicable | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Fixed term contract
12 | 02/003/62 | Promotions, Publicity and Printing | Publishing of Legal Notices and all road safety awareness initiative measures | 14111800 | Tentative | Tentative | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
13 | 02/003/96 | Fuel and Lubricants | Provision of oil, gasoline and diesel for vehicles and equipment | 15000000 | Not applicable | Not applicable | Not applicable | Ministry of Finance under the fleet card management system | Not applicable | Not applicable
14 | 03/003/01 | Purchase of Vehicles | For the delivery of mail to head office and other areas, transportation of personnel to conduct traffic surveys, transportation of officers to meetings | 25111507 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
15 | 03/003/02 | Office Equipment | Purchase of printers, scanners, computers, tablets, monitors, wall monitors for CCTV monitoring of Highways | 44000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
16 | 03/003/03 | Furniture and Furnishings | Purchase of typist chairs, ergonomic chairs, cabinets, storage cupboards etc | 56000000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
17 | 03/003/04 | Other Minor Equipment | Installation of cameras at the Mon Repos Office, microwave ovens, kettles air condition units etc | 44100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Tentative | Request for 3 quotes | Not applicable | Invoice/ Quotation
18 | 09/003/15G/159 | Provision for backup power supply for traffic signalised intersections | Along with the growing road network within Trinidad and constant increase in vehicular volume, it is very important that full control of signalized intersections must always be maintained. Power outages at traffic signalized areas can result in uncontrolled intersections which hamper the smooth flow of traffic. During these times, a period of confusion is created with undue congestion and a high potential for serious accidents and fatalities. The installation of a reliable backup power supply will eliminate these potential threats. | 46161500 | 2024-01-01 | 2024-03-01 | May 2024 to August 2024 | Limited Bidding | 10 working days | Fixed Term Contract
19 | 09/003/15G/164 | Provision to upgrade obsolete traffic signal control equipment | To improve road safety on Trinidad and Tobago’s primary road network. The focus is to reduce journey times caused by increased congestion due to obsolete traffic signal control equipment. | 46161500 | 2024-01-01 | 2024-03-01 | May 2024 to August 2024 | Limited Bidding | 10 working days | Fixed Term Contract
20 | 09/003/15G/170 | Provision for data collection | Road safety measures provision for data collection to assist with management of traffic congestion/accidents | 46161500 | 2024-01-01 | 2024-03-01 | May 2024 to August 2024 | Limited Bidding | 10 working days | Fixed Term Contract
21 | 09/003/15G/171 | Provision of road safety audit on the roadways of Trinidad | Conduct road assessment program on road ways, to enhance the efficiency and effectiveness of National Transportation system | 46161500 | 2024-01-01 | 2024-03-01 | May 2024 to August 2024 | Limited Bidding | 10 working days | Fixed Term Contract
22 | 09/003/15G/172 | Provision of equipment for road marking purposes | To purchase equipment for road marking purposes on the nation's roadways | 22101624 | 2024-01-01 | 2024-03-01 | May 2024 to August 2024 | Limited Bidding | 10 working days | Fixed Term Contract

## Transport Division (Licensing)
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Transport Division (Licensing)
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | XXXX | Electricity | Supply of electricity to all Licensing Offices (Princes Town, Sangre Grande, Caroni, Point Fortin, Wrightson Road, St James, Arima, San Fernando) | 83101800 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
2 | XXXX | WASA | Pyments to WASA Jerningham Junction Cunupia and PBR Macoya | 83101500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
3 | XXXX | Uniform | Supply uniform for Motor Vehicle Officers, Motor Vehicles Drivers Messenagers , Estate Constables and Chauffeur | 53102700 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
4 | XXXX | Telephone | Supply of Telephone Servies, Internetand Communication and Wireless Broadban to all Licensing Offices (Princes Town, Caroni, Point Fortin, Wrightson Road, St James, Arima, San Fernando) | 83111501 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
5 | XXXX | Rental | Rental of office space to Licensing Offices (Princes Townand Point Fortin.) | 80131500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable
6 | XXXX | Equipment | Rental of Linx machine | 44100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
7 | XXXX | Office stationary and supplies | Purchase of cleaning, toiletries, office stationary, household cleaning items etc | 44120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
8 | XXXX | Books and periodicals | Supply of newspaper and transport related journals | 55101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable
9 | XXXX | Material and supplies | Supply of items for core functions within Transport Division (Ink, Toners, Security registration cards, Consumables for cash register, bonding paper, printery items) |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
10 | XXXX | Vehicles | Purchase of Oil, filter, batteries, tyres, wipers, parts for repairs. | 78181500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
11 | XXXX | Repairs and Maintenance of equipment | Repairs and service to photocopying machines, printers, cash registers, lift, money counters, weigh bridge, water pumps.* | 811120306 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
12 | XXXX | Training | Training for customer service, law enforcement | 86100000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
13 | XXXX | Repairs and Maintenance of buildings | Repairs and maintenance to buildings, bulbs, elevators, generator, air-condition, fire alarm, windows, doors, rolling gates | 72101500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
14 | XXXX | Other Contracted Services | Air refresheners, soap dispensers, urinal flush, landscaping |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
15 | XXXX | Janitorial Services | Provision of services; Cleaning of washrooms, windows, sanitizing, shampoo floors for Caroni Licensing | 76110000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
16 | XXXX | Security services | Provision of armed and unarmed sercurity service as well as courrier. | 92120000 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
17 | XXXX | Security services | Provision of cash InTransit service for all Transport Divisions | 92120000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Working Days | Fixed Term Contract
18 | XXXX | Postage | Purchase of stamps | 44121500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable
19 | XXXX | Promotion, publicity and printing | Informative advertising- Licensing procedures (in respect to closure of offices) | 14111800 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
20 | XXXX | Hosting of conferences, seminars and other functions | Hosting of conferences, seminars and other functions | 80141902 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable
21 | XXXX | Fuels & Lubricants | Gas, fuels and oils for all Licensing offices. | 15000000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable
22 | XXXX | Minor Equipment | Vehicles: Purchase of new vehicles. Office Equipment: Printers, Registers, Ultra-Violet lights, Photocopier, Money Counter. Furniture: Dexion, Cabinets, Filing Cabinets, Carpet, Shelving units, Steep cupboards, Blinds, Six seater chairs. | 25100000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
23 | XXXX | Other minor equipment | Air condition, trolleys, hand trucks, ladders, fridge, kettles, tri-pod stands, microphone systems. | 44100000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Request of quotations | Not applicable | Invoice/ Quotation
24 | XXXX | Traffic Enforcement Centre Unit | Thermal paper, ticket books, water resistance affix envelopes, citation notice paper | 14110000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Tenders | Not applicable | Not applicable
25 | XXXX | Traffic Enforcement Centre Unit | Envelopes, consumable letter printers, toners | 44120000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Quotation | Not applicable | Not applicable
26 | XXXX | Traffic Enforcement Centre Unit | Delivery citation notices, couriering of motor vehicles and road traffic act, payment collection for citation notices and fixed penalty notices | 78102205 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Contract Agreement | Not applicable | Not applicable
27 | XXXX | Traffic Enforcement Centre Unit | Newspaper advertisement, data centre fees, software license | 55101500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Permanent Secretary Approval |  | Not applicable
Capital Expenditure/DP
1 | XXXX | Procurement of Red Light Camera and Spot spped Camera System | Procurement and Implementation of a Red Light Camera Enforcement and Spot Speed Camera Enforcement Hardward and Software management Sytsem for the Ministry of Works and Transport | 46161500 | 1st Quarter Fiscal 2024 | 2nd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
2 | XXXX | Upgrade Electronic Vehicle Registration System | Complete mapping of relevant business processes and requirements Deployment of EVR software and Require Software Implement a new data centralized model to improve data security. Ensure affected employees are fully trained on new business processes Adjust and simplify fee structure - Recommend new fees to Minister Reinvent Web offerings and format - Deploy Online Transfer System Review and enhance service delivery methods - Dissemination of Information | 43232400 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
3 | XXXX | Data Migration Validation | Improve data quality to support new data capture methods Digitization of Maxi Taxi Records Digitization of Taxi Badge Records (ongoing) Digitization of Registration documents (ongoing) Digitization and Validation of Vehicle Registration Records Validation of Drivers Permit Records Adjust and simplify fee structure Embrace innovation and continuous improvement as the engine of transformation Review and enhance service delivery methods Digitiazation of HR, GA, TC and TECU Operational Files | 43223100 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
4 | XXXX | Expand Debit Card Acceptance | Expansion of electronic payments systems (Credit Card) Introduction of Counter Service Paymen - Via Payment Vouchers (Hardware and Software) Reinvent Web offerings and format | 64101700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
5 | XXXX | Modernization of the Drivers Permit and Taxi Badge Issuance System | Deployment of Online scheduling for Regulations and Driving Tests Pilot - Computerized exams with secure access (pin/biometric) - 2 sites GPS plotting of vehicles used for Driving Test (Extension of Pilot) Online renewal processing for Drivers Permit (Public Tender for Software) Strengthen links and coordination with data-sharing partners | 81102500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
6 | XXXX | Assess and evaluate the needs of records customers | Review and redesign data collections forms Implementation an Interactive Chat Room with IGovtTT Thoroughly survey and identify customers’ record needs to clarify business requirements for future system and process improvements Introduce Web Survey Performance and Statistical Systems (Vehicle Registration Data and Drivers Permit) | 43232300 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
7 | XXXX | Proactively monitor and respond to laws and their impact on the Division’s Services and work processes | The Division will partner with stakeholders to design and develop approaches for implementing a comprehensive program for drivers’ rehabilitation - Expansion Data Integration with Law enforcement agencies Disclosure of Offence Reporting | 85122100 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
8 | XXXX | Modernization of the Vehicle Inspection System | system upgraded | 78141600 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
9 | XXXX | Speedier Certified Copy Request and Delivery | Develop Fulfilment Software Implement Online Payment for Certified Copies Develop and Finalise MOU | 64101700 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
10 | XXXX | Modernization of the number plate system | Implement Bidding Software See Cabinet approval for new revenue stream Modify Legislation where necessary |  | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
11 | XXXX | Facilities Maintenance and Enhancements | Painting of all Licensing Sites where needed Commence work on the Princes Town Licensing Office Complete Construction of Guaico Office Ensure appropriate lighting at all Licensing Offices Complete Inspection Area Wrightson, Completer upgrade of at Wrightson road to to accommodate St. James Office Improve facilities at all remaining sites. Acquisition of two vehicles for Enforcement Unit | 81141800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
12 | XXXX | Introduction of Mobile Services | 100% Completed | 83111600 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
13 | XXXX | Training | Customer Service Basic Tactical Self Defense Evidence Gathering Case Management New Fixed Penalty System – Enforcement Tint Enforcement Leadership Management - People, culture and leadership Chassis Forensics Chassis Impressing First Aid Firearm | 86101800 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
14 | XXXX | Human Resource (HR) Enhancement | Seek PMCD Approval Seek Cabinet Approval Recruitment/Implementation | 80111500 | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract

## Traffic Warden
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Traffic Warden Division
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
RECURRENT EXPENDITURE
1 | 5/10/6. | Office Equipment | Purchase of 10 computers,1 laptop and projector ( Road Safety Committee) , 15 Telephones, 1 Heavy Duty shredders, 6 Adding Machines ,200 FPN Devices | 44000000 | 2023-11-01 | 2024-01-01 | 90 Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
2 | 05/9/1. | Furniture & Furnishings | Purchase of various furniture and furnishings such as Chairs, Desks and Cabinets for 4 Traffic Warden Offices | 56000000 | 2023-11-01 | 2023-12-01 | 60Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
3 | 5/10/5. | Other Minor Equipment | Purchase of 6 Refrigerators, Air Condition Units, Binding machine,2 Guillotine and 6 Microwaves | 44000000 | 2023-11-01 | 2024-01-01 | 60 Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
4 | 5/3/11. | Vehicle | Purchase of One (1) 25 seater Bus and one (1) 18 Seater Bus | 25100000 | 2023-11-01 | 2024-04-01 | 180 Days | Limited Bidding | 10 working days | Fixed Term Contract
5 | 3/1/4 | Uniforms | Purchase of Uniforms and Ceremonial wear for Traffic Wardens | 53102700 | 2024-01-01 | 2024-03-01 | 90Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
6 | 5/5/1 | Electricity | Payment of Electricity Invoices for Traffic Warden Division | 83101800 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
7 | 5/4/1 | Telephones | Payment of telephone Invoice for Traffic Warden Division | 83111501 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
8 | 5/7/1 | Wasa and Sewerage Rates | Payment of Water Invoices for Traffic Warden Division | 83101500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Sole Select | Not applicable | Not applicable
9 | 5/11/1 | Rent/Lease | Payment of rent Invoice for Traffic Warden Division for Penal, Point Fortin and Port of Spain | 80131500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Limited Bidding | 10 working days | Fixed Term Contract
10 | 5/2/1 | Office Stationery and Supplies | Purchase of Office Stationery and Supplies for the Traffic Warden Division such as; Pens, ink, paper, cleaning supplies, toner, and other items | 44120000 | 2024-01-01 | 2024-02-01 | 30 Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
11 |  | Books and Periodicals | Purchase of Training Manuel for recruitment | 55101500 | 2023-11-01 | 2023-12-01 | 30 Days | Not applicable | Not applicable | Not applicable
12 | 5/2/7 | Materials and Supplies | Purchase of Station diaries, patrol registers, bulbs, electrical materials and other items |  | 2024-01-01 | 2024-02-01 | 30 Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
13 | 5/3/1 | Maintenance of Vehicles | Purchase of all items necessary for the upkeep and maintenance of Traffic Warden Vehicles | 78181500 | 2023-11-01 | 2023-12-01 | 30 Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
14 | 5/10/2 | Repairs and Maintenance of Equipment | Servicing of Water Coolers and photocopying machines | 811120306 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Selective Tendering | Not applicable | Not applicable
15 | 3/1/6 | Training | Recruitment of Traffic Warden, First Aid and CPR Training | 86100000 | 2023-10-01 | 2023-12-01 | 60 days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
16 | 5/12/4 | Other Contracted Services | Payment of Sanitary Bins | 47121500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Limited Bidding | 10 working days | Fixed Term Contract
17 | 5/13/1 | Janitorial Services | Payment for janitorial services for Port of Spain, Chaguans, Point Fortin, Penal | 47121500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
18 | 5/14/1 | Security Services | Payment for Security services for Port of Spain and Point Fortin | 92120000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Open Bidding | 10 Days | Fixed Term Contract
19 | 5/2/7 | Postage | Payment for register mail | 44121500 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable
20 | 5/2/5 | Promotion, Publicity and Printing | Printing of items for road safety campaigns and other functions | 14111800 | 2024-01-01 | 2024-02-01 | 30 Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
21 | 5/2/6 | Hosting of Conferences, Seminars and Other Functions | Hosting of graduation for new recruits, Anniversary function and Independence Day function. | 80141902 | 2024-01-01 | 2024-02-01 | 30 Days | 3 Quote System and Permanent Secretary Approval | Not applicable | Invoice/ Quotation
22 | XXXX | Fuel and Lubricants | Non Cash Tranaction for fuel and Lubricants | 15000000 | 1st Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | Not applicable | Not applicable | Not applicable | Not applicable

## URP (hidden)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
URP
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
Note on H16: Akido Ford
Note on H17: Akido For

## URP
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2023/2024
Unemployment Relief Programme (URP)
No. | Project Number | Project Name | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
Recurrent Expenditure
1 | URPN0001/2023-2024 | Purchasing or Leasing of Vehicles | Purchasing or Lease Agreement for the Supply, Delivery and Maintenance of 20 4x4 Diesel Double Cab Vans | 25100000 | 2023-10-01 | 2023-11-01 | 2 months | Open Bidding | 10 Days | Fixed Term Contract
3 | URP 60/4/21 | Supply, Delivery and Furniture and Furnishings | Supply and Delivery of Chairs, Desk and Filing Cabinets | 56000000 | 2023-10-01 | 2023-12-31 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
4 | URP 60/4/16 | Supply, Delivery and Maintenance of Bushcutters | Approx. 100 Bushcutters for Wackercrews | 44100000 | 2023-10-01 | 2023-11-02 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation
5 | URP 60/4/16 | Supply, Delivery and Buschcutters Accessories | Buschcutter string, two stroke oil, auto cut head etc | 78181500 | 2023-10-01 | 2023-11-02 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation
6 | URP 60/4/65 | Additional Modules re: DAILY PAID PAYROLL (Inventory Module) | Creation of an additional module to capsulate the materials procured and purchase for construction projects | 81111500 | 2023-10-01 | 2024-05-01 | 6 months | Single Source | Not applicable | Fixed Term Contract
7 | URP 60/4/65 | Additional Modules re:NID SCANNING | Creation of an additional module to scan National Identification Cards to attached to profile and the required equipment for Payroll processing | 81111500 | 2023-10-01 | 2024-05-01 | 6 months | Single Source | Not applicable | Fixed Term Contract
8 | URP 60/4/2 | Supply and Delivery of Office Supplies - PAPER | STATIONERY SUPPLIES - Copy paper and Book Binding Material | 44120000 | 2023-10-01 | 2023-12-01 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
9 | URP 60/4/3 | Supply and Delivery of Office Supplies - TONERS | STATIONERY SUPPLIES - Toners for photocopiers and printers | 44120000 | 2023-10-01 | 2023-12-01 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
10 | URP 60/4/2 | Supply and Delivery of Office Stationery and Supplies | STATIONERY SUPPLIES (Envelopes,pens,writing pads, Staples, Storage Boxes, etc. | 44120000 | 2023-10-01 | 2023-12-01 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
11 | URP 60/4/4 | Supply and Delivery of Office Stationery and Supplies - GROCERS | Refreshments for meetings | 90101700 | 2023-10-01 | 2024-01-01 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation
12 | URP 60/4/4 | Supply and Delivery of Office Stationery and Supplies - TOILETRIES | TOILETRIES (Toilet Paper, Hand Paper Towel, Hand Liquid Soap, Han Sanitizer) | 47131700 | 2023-10-01 | 2023-12-01 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
13 | URP 60/4/33 | Supply and Delivery of HEALTH & SAFTEY EQUIPMENT AND SUPPLIES | Gloves, chemicals for sanitization, cones, traffic signage, safety signs, safety garments, googles, clear glasses | 46181500 | 2023-10-01 | 2023-12-01 | 4 months | Request for Quotation | Not applicable | Invoice/ Quotation
14 | URP 60/4/63 | Consultation for Digitized System of LEGACY NIS DOCUMENTS | Consultants to be engaged to develop a system process for phase one (1) for the DIGITIZATION OF LEGACY NIS DOCUMENTS including implementation | 81111500 | 2023-10-01 | 2024-05-01 | 6 months | Request for Proposal | Not applicable | Invoice/ Quotation
15 | URP 60/4/62 | Procurement of PAYROLL AND HR APPLICATION | Supply, Installation and Implementation of a Monthly paid payroll and Human Resource Application | 81111500 | 2023-10-01 | 2024-08-01 | 8 months | Request for Proposal | Not applicable | Invoice/ Quotation
16 | URP 60/4/60 | Supply and Delivery of Office Equipment - DESKTOPS | Supply and Delivery of 50 Desktops | 43211500 | 2023-10-01 | 2023-12-01 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
17 | URP 60/4/60 | Supply and Delivery of Office Equipment - Power Supply | Supply and Delivery of 1500V Uninterrupted Power Supply Units | 26111600 | 2023-10-01 | 2023-11-01 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation
18 | URP 60/4/60 | Service and Repairs of Office Equipment | Servicing and supply and installation replacement parts for photocopies and printers | 44100000 | 2023-10-01 | 2023-12-01 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation
19 | URP 60/4/4 | Supply and Delivery of Office Stationery and supplies - Janitorial Supplies | JANITORIAL SUPPLIES (All Cleaning Supplies) | 76110000 | 2023-10-01 | 2023-11-01 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation
20 | URP 60/4/60 | Procurement of Additional Modules re: Daily Paid Payroll (NIS Module) Phase I | Conversion of the Daily Paid Payroll from 2002-2016 | 81111500 | 2023-10-01 | 2024-02-01 | 4 months | Request for Quotation | Not applicable | Invoice/ Quotation
21 | URP 60/4/12 | Refurbishing of the Chaguanas Conference Room -Part 1 | Procurement of doors, fitting and fixtures, blinds and repainting of walls | 56000000 | 2023-11-01 | 2023-12-01 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation
22 | URP 60/4/60 | Supply and Delivery of Licenses for Draughting Software | Supply and Delivery of AUTOCAD (upgrade) LICENSES FOR ENGINEERING DEPT | 81111500 | 2023-11-01 | 2024-04-01 | 4 months | Sole Source | Not applicable | Fixed Term Contract
23 | URP 60/4/12 | Refurbishing of the Chaguanas Conference Room -Part 2 | Procurement of furniture, Audio/Visual and Wireless Equipment | 56000000 | 2023-11-01 | 2024-02-01 | 4 months | Request of Quotations | Not applicable | Invoice/ Quotation
24 | URP 60/4/60 | Supply and Delivery of Office Equipment - IT Peripherals | Supply and Delivery of mouse, keyboards, hardrives, memory sticks, compress air, CMOS Batteries, networking cables, etc. | 44000000 | 2023-11-01 | 2024-03-01 | 4 months | Request of Quotations | Not applicable | Invoice/ Quotation
25 | URP 60/4/60 | Supply and Delivery of Office Equipment - Photocopiers | PHOTOCOPIERS for HO | 44000000 | 2023-11-01 | 2024-03-01 | 4 months | Request for Quotation | Not applicable | Invoice/ Quotation
26 | URP 60/4/63 | Supply and Delivery of Office Equipment - Software Application Licenses | Supply and Delivery of MS Office Licenses | 81111500 | 2023-11-01 | 2024-01-01 | 2 months | Sole Source | Not applicable | Invoice/ Quotation
27 | URP 60/4/12 | Supply and Delivery of Material - BUILDING MATERIAL (maintenance) | Electrical fixture and fittings, Plumbing fixture and fittings , door locks and handles, toilet seats, toilet sets, taps etc. | 72101500 | 2023-11-01 | 2023-12-01 | 1 month | Request for Quotation | Not applicable | Invoice/ Quotation
28 | URP 60/4/62 | Consultation, Supply and Delivery of Information Management Security Systems | SECURITY SYSTEM UPGRADE CHAGUANAS AND HEAD OFFICE | 92121700 | 2023-12-01 | 2024-04-01 | 4 months | Request for Proposal | Not applicable | Invoice/ Quotation
29 | URP 60/4/60 | Supply and Delivery of Office Equipment - Laptops | Supply and Delivery of 7 Laptops | 44000000 | 2023-12-01 | 2024-03-01 | 4 months | Request for Quotation | Not applicable | Invoice/ Quotation
30 | URPN0030/2023-2024 | Procurement of Materials, supplies and transport for approximately 105 projects | CONSTRUCTION PROJECTS | 72141100 | 2024-01-01 | 2024-05-01 | 5 months | Request for Quotation | Not applicable | Invoice/ Quotation
31 | URP 60/4/12 | Supply and Delivery of Office Equipment - Calculators | Procurement of 24 Calculators | 44000000 | 2024-01-01 | 2024-03-01 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
32 | URP 60/4/60 | Procurement of Additional Modules Re: DAILY PAID PAYROLL (NIS MODULE) Phase 2 | Creation of an additional module for migration of the end product form the digitization of legacy NIS documents project | 81111500 | 2024-01-01 | 2024-05-01 | 3 months | Single Source | Not applicable | Fixed Term Contract
33 | URP 60/4/64 | Upgrade of Telephony System | Upgrade of IP TELEPHONY SYSTEM | 81111500 | 2024-01-01 | 2024-07-01 | 6 months | Request for Proposal | Not applicable | Invoice/ Quotation
34 | URP 60/4/61 | Disposal of Unserviceable Articles | Disposal of obsolete/defective computer hardware, photocopiers, furniture and filing cabinets, fax machines, printers etc. | 76121500 | 2024-01-01 | 2024-05-01 | 5 months | Request for Quotation | Not applicable | Invoice/ Quotation
35 | URP 60/4/60 | Supply and Delivery of Office Equipment - DESKTOPS | Supply and Delivery of 50 Desktops | 44000000 | 2024-01-03 | 2024-03-01 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
36 | URP 60/4/62 | Consultation, Supply and Delivery of Information Management Security Systems | SECURITY SYSTEM UPGRADE - 3 REGIONS | 92121700 | 2024-02-01 | 2024-04-01 | 4 months | Request for Proposal | Not applicable | Invoice/ Quotation
37 | URP 60/4/4 | Supply and Delivery of Office Stationery and supplies - Janitorial Supplies | JANITORIAL SUPPLIES (All Cleaning Supplies) | 76110000 | 2024-02-01 | 2024-03-01 | 2 months | Request for Proposal | Not applicable | Invoice/ Quotation
38 | URP 60/4/2 | Supply and Delivery of Office Supplies - Paper | STATIONERY SUPPLIES - Copy paper and Book Binding Material | 44120000 | 2024-03-01 | 2024-06-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
39 | URP 60/4/12 | Supply and Delivery of Tent Carvas | Canvas for 2 (20*20) Tents. | 95131700 | 2024-03-01 | 2024-05-01 | 2 months | Request for Proposal | Not applicable | Invoice/ Quotation
40 | URP 60/4/3 | Supply and Delivery of Office Stationery and supplies - Toners | STATIONERY SUPPLIES - Toners for photocopiers and printers | 44000000 | 2024-04-01 | 2024-05-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
41 | URP 60/4/2 | Supply and Delivery of Office Stationery and Supplies | STATIONERY SUPPLIES (Envelopes,pens,writing pads, Staples, Storage Boxes, etc. | 44120000 | 2024-04-01 | 2024-05-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
42 | URP 60/4/4 | Supply and Delivery of Office Stationery Supplies - Grocers | Refreshments for meetings | 90101700 | 2024-04-01 | 2024-05-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
43 | URP 60/4/33 | Supply and Delivery of HEALTH & SAFTEY EQUIPMENT AND SUPPLIES | Safety Jackets, gloves, chemicals for sanitization, cones, traffic signage, safety signs, safety garments, etc. | 46180000 | 2024-04-01 | 2024-05-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
44 | URP 60/4/60 | Supply and Delivery of Office Equipment - DESKTOPS | Supply and Delivery of 100 Desktops | 44000000 | 2024-04-01 | 2024-05-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
45 | URP 60/4/4 | Supply and Delivery of Office Stationery and supplies - Janitorial Supplies | JANITORIAL SUPPLIES (All Cleaning Supplies) | 76110000 | 2024-04-01 | 2024-05-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
46 | URP 60/4/65 | Contract Renewal for the URP Registration and Payroll Application | Maintenance, Technical support, Additional Modules and SSL Security | 81111500 | 2024-05-01 | 2024-06-01 | 1 month | Sole Source | Not applicable | Invoice/ Quotation
47 | URP 60/4/21 | Supply and Delivery of Furniture and Furnishing | Supply and Delivery of Chairs, Desks and Filing Cabinets | 44120000 | 2024-06-01 | 2024-08-31 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
48 | URP 60/4/61 | Disposal of Unserviceable Articles | Disposal of obsolete/defective computer hardware, photocopiers, furniture and filing cabinets, fax machines, printers etc. | 76121500 | 2024-06-01 | 2024-09-01 | 4 months | Request for Quotation | Not applicable | Invoice/ Quotation
49 | URP 60/4/62 | Consultation, Supply and Delivery of Information Management Security Systems | SECURITY SYSTEM UPGRADE - 3 REGIONS | 72151700 | 2024-06-01 | 2024-09-01 | 4 months | Request for Proposal | Not applicable | Invoice/ Quotation
50 | URP 60/4/12 | Supply and Delivery of Powerwashers | (3) Powerwasher for HO, Northern Regions and Southern Regions | 47121800 | 2024-07-01 | 2024-08-01 | 1 month | Request for Proposal | Not applicable | Invoice/ Quotation
51 | URP 60/4/2 | Supply and Delivery of Office Stationery and Supplies | STATIONERY SUPPLIES (Envelopes,pens,writing pads, Staples, Storage Boxes, etc. | 44120000 | 2024-07-01 | 2024-09-01 | 3 months | Request for Proposal | Not applicable | Invoice/ Quotation
52 | URP 60/4/25 | Supply, Delivery and Maintenance of Automatic Sanitary Bins | Lease Agreement for 69 Automatic Sanitary Bins for HO and Regions | 47131700 | 2024-07-01 | 2024-08-02 | 2 months | Request for Quotation | Not applicable | Invoice/ Quotation