## BLT
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Bridges, Landslips and Traffic Management (BLT-PIU)
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
701 - Infrastructure Development Fund
Bridges Reconstruction Programme
1 | xxxx | 8111000 | Phase 3B - Designs | Procurement of 2 Consultants for the Design Services and Construction Supervision for 12 Bridges | 2024-11-01 | Mar 2025/Dec 2025 | 10mths | Open Bidding | Fixed Price
Landslip Repairs Programme
1 | xxxx | 77111603 | L02 - North Coast Road 7.7km | Landslip rehabilitation | 2025-01-01 | Sep 2025/Jun 2026 | 10mths | Open Bidding | Fixed Price
2 | xxxx | 77111603 | L05 - Paria Morne Bleu Rd (5.6km) | Landslip rehabilitation | 2025-01-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
3 | xxxx | 77111603 | L06 -Paria Main Rd (69.3km) | Landslip rehabilitation | 2025-01-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
4 | xxxx | 77111603 | L10- Bonair Road (Lp 177-178) | Landslip rehabilitation | 2025-01-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
5 | xxxx | 77111603 | L12 - Cumoto Road (Lp 301-303) | Landslip rehabilitation | 2025-01-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
6 | xxxx | 77111603 | L15- Sisters Road 5.50km | Landslip rehabilitation | 2025-01-01 | Jun 2025/Jan 2026 | 8mths | Open Bidding | Fixed Price
7 | xxxx | 77111603 | L16-Sisters Road 5.1km | Landslip rehabilitation | 2025-01-01 | Jun 2025/Jan 2026 | 8mths | Open Bidding | Fixed Price
8 | xxxx | 77111603 | L32 Sixth Company Circular Road 3.5km LP#15-16 | Landslip rehabilitation | 2025-01-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
9 | xxxx | 77111603 | L33 Sixth Company Circular Road 1.8km LP#73 | Landslip rehabilitation | 2025-01-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
10 | xxxx | 77111603 | L 34 - Moreau Rd #1(LP226), Marac | Landslip rehabilitation | 2025-01-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
11 | xxxx | 8111000 | Phase 2B - Designs | Procurement of 3 Consultants for the Design Sevices and Construction Supervision for 35 Landslips | 2025-03-01 | Sep 2025/Aug 2026 | 12mths | Open Bidding | Fixed Price
Traffic Management Programme
1 | xxxx | 46161500 | CP13 – Supply and Installation of AASHTO W-Type Metal Beam Guardrails CRH – Antigua Road to Pinto Road (St. George East) | Installation of traffic management and safety systems | 2025-01-01 | Jun 2025/Aug 2025 | 3mths | Open Bidding | Fixed Price
2 | xxxx | 46161500 | (ii) CP17 – Supply and Installation of AASHTO W-Type Metal Beam Guardrails (11000m) SSHH/UBH(Caroni) from Guaymare River to Seereeram Bros Walkover | Installation of traffic management and safety systems | 2025-01-01 | Jun 2025/Sep 2025 | 4mths | Open Bidding | Fixed Price
3 | xxxx | 46161500 | (iii) CP18 – Supply and Installation of AASHTO W-Type Metal Beam Guardrails (10100m) UBH(Caroni) from Divali Nagar to Chaguanas Overpass | Installation of traffic management and safety systems | 2025-01-01 | Jun 2025/Sep 2025 | 4mths | Open Bidding | Fixed Price
DP
1 | xxxx | 81100000 | Information Technology Dep't | Renewal of Design Software Licenses | 2023-11-01 | 2023-12-01 | 1 mth | Sole Select | Fixed Price
2 | xxxx | 44000000 | Information Technology Dep't | Purchase of Printers, computers and other office equipment | 2023-11-01 | 2024-01-01 | 3 mths | Open Bidding | Fixed Price

## Coastal Protection
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Coastal Protection Unit
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
701 - Infrastructure Development Fund
1 | 701/43/003/11/P/024 | 72141200 | Repair Works | Vistabella Seawall Repair Works | 2024-12-01 | Jun 2025/Nov 2025 | 6mths | Open Bidding | Fixed Price
2 | 701/43/003/11/P/027 | 72141200 | Stabilization Works | Granville Shoreline Stabilization Works | 2024-12-01 | Jun 2025/Mar 2026 | 10mths | Open Bidding | Fixed Price
3 | 701/43/003/11/P/028 | 72141200 | Coastal Works | Otaheite Coastal Restoration Project | 2025-03-01 | Sep 2025/Jun 2026 | 10mths | Open Bidding | Fixed Price
4 | 701/43/003/11/P/030 | 72141200 | Coastal Works | Paria Main Road Coastal Protection - Design Services for Rampanalgas and Construction Works for San Souci | 2024-12-01 | Apr 2025/Mar 2027 | 24mths | Open Bidding | Fixed Price
5 | 701/43/003/11/P/031 | 72141200 | Stabilization Works | Cap De Ville Shoreline Stabilisation Works Phase II | 2024-12-01 | Apr 2025/Sep 2026 | 18mths | Open Bidding | Fixed Price
6 | 701/43/003/11/P/032 | 72141200 | Improvement Works | Manzanilla Beach Facility Improvement Works - Environmental Impact Assessment (EIA) | 2024-12-01 | Apr 2025/Mar 2027 | 24mths | Open Bidding | Fixed Price
7 | 701/43/003/11/P/033 | 72141200 | Coastal Works | Comprehensive National Coastal Monitoring Programme Phase II | 2024-12-01 | Apr 2025/Mar 2027 | 24mths | Open Bidding | Fixed Price
8 | 701/43/003/11/P/036 | 72141200 | Coastal Works | Mayaro/Guayaguayare Coastal Management Programme (West Guayaguayare) | 2025-03-01 | Sep 2025/Nov 2026 | 15mths | Open Bidding | Fixed Price
9 | 701/43/003/11/P/NEW | 81102100 | Coastal Works | Green Engineering Pilot Study - Artificial Reef Project | 2024-12-01 | Apr 2025/Mar 2027 | 24mths | Open Bidding | Fixed Price

## CPU (hidden)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
Central Planning Unit (CPU)
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## Construction
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Construction
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
1 | 4/5/6 Sub II | 30152000 | Construction of perimeter fencing | 311 - Sangre Grande Works Office , Guaico: Construction of Wirewall and Blockwall security fencing | 2024-09-01 | 2025-01-01 | 90 days | Open Bidding | Measured Works Contract
2 | 4/5/3 Sub I | 30161700 | Constuction of a mezzanine floor | 318 - Mechanical Services Department, Caroni - The Construction of Mezzanine Floor in Workshop | 2024-10-01 | 2025-02-01 | 90 days | Open Bidding | Fixed Term Contract
3 | 4/5/31 | 81101500 | Geotechnical investigations | 240 - Geotechnical Proposal New Office Building: Southern Main Road, Curepe | 2024-09-01 | 2024-11-01 | 60 days | Selective | Fixed Term Contract
4 | 4/5/11 Sub VI | 72102104 | Pest control | 240 - Service Contract for Pest control at D'Abadie Furniture Branch and Stores | 2024-12-01 | 2025-01-01 | 30 days | Selective | Fixed Term Contract
5 | 4/5/3 Sub I | 30152000 | Construction of perimeter fencing | 318 - Construction of wire wall fencng at Mechanical Services Division, Caroni | 2025-01-01 | 2025-05-01 | 90 days | Open Bidding | Measured Works Contract
6 | 4/5/11 Sub VI | 30152000 | Construction of perimeter fencing | 240 - Construction of wire wall fencng at D'D'Abadie Furniture Branch and Stores | 2024-11-01 | 2025-03-01 | 90 days | Open Bidding | Measured Works Contract
7 | 4/5/32 | 72102300 | Plumbing and electrical upgrades and general refurbishment to buildings | 240 - D'Abadie Compound and District Ofices Repairs | 2024-11-01 | 2025-04-01 | 120 days | Open Bidding | Measured Works Contract
8 | 4/5/11 Sub VIIII | 40101604 | Supply and install of expeller fans | 240 - D'Abadie Furniture Branch and Stores - Expeller fans | 2024-11-01 | 2025-02-01 | 45 days | Selective | Fixed Term Contract
9 | xxxx | 81101500 | Geotechnical investigations | 240 - Geotechnical Proposal New Office Building: Frederick Street, POS | 2025-03-01 | 2025-05-01 | 60 days | Selective | Fixed Term Contract
10 | xxxx | 72102104 | Pest control | 240 - Service Contract for Pest control at Beetham Stockpile for a period of 1yr | 2025-03-01 | 2025-04-01 | 30 days | Selective | Fixed Term Contract
11 | xxxx | 81101500 | Geotechnical investigations | 240 - Geotechnical Proposal South Regional Head Office, San Fernando | 2025-03-01 | 2025-05-01 | 60 days | Selective | Fixed Term Contract

## CTO (hidden)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
CTO
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## Drainage Division
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Drainage Division
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
Recurrent Expenditure
1 | 1/4/24 | 53102700 | Uniforms | Purchase of Personal Protective Equipment | 2025-01-01 | 2025-06-01 | Not applicable | Request for Quotations | Fixed Price / Lumpsum
2 | 4/3/75 | 43221700 | Minor Equipment | Network Hardware Upgrades to Systems for Head Office, District Offices and Sub Offices (Mayaro and Rio Claro) | 2025-03-01 | 2025-06-01 | Not applicable | Request for Quotations | Fixed Price / Lumpsum
3 | 4/3/76 | 41114200 | Minor Equipment | 2 Total Stations | 2025-03-01 | 2025-06-01 | Not applicable | Single Source | Fixed Price / Lumpsum
4 | 4/3/77 | 43232600 | Other Minor Equipment | ARCGIS Pro Lisence (Lamps) | 2025-01-01 | 2025-06-01 | Not applicable | Single Source | Fixed Price / Lumpsum
| 4/3/78 | 43211500 | Minor Equipment | Server for Processing Drone Imagery | 2025-01-01 | 2025-06-01 | Not applicable | Request for Quotations | Fixed Price / Lumpsum
1 | 4/3/79 | 41114300 | Minor Equipment | Baythmetric Drone | 2025-01-01 | 2025-08-01 | Not applicable | Single Source | Fixed Price / Lumpsum
2 | 4/3/80 | 43211500 | Minor Equipment | 20 Computers | 2025-01-01 | 2025-06-01 | Not applicable | Request for Quotations | Fixed Price / Lumpsum
3 | 1/7/33 | 25101600 | Vehicles | 1 New Vehicle | 2025-01-01 | 2025-06-01 | Not applicable | Request for Quotations | Fixed Price / Lumpsum
Recurrent 09
1 | 02/005/09 | 70171800 | Lengua | D/S of Cunjal Road (4000m) (Naparima) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
2 | 02/005/09 | 70171800 | Erin River | D/S of Johnson Trace (3000m) (La Brea) | 2025-01-01 | 2025-09-30 | 1,100 hours | Invoice Order | N/A
3 | 02/005/09 | 70171800 | Fraits Drain | U/S of Fullerton Beach (1000m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
4 | 02/005/09 | 70171800 | Kanjack Drain | D/S of Southern Main Road (2500m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 450 hours | Invoice Order | N/A
5 | 02/005/09 | 70171800 | Alleys Creek | D/S of Renn Avenue to Bamboo Junction (1000m) (San Fernando West) | 2025-01-01 | 2025-09-30 | 1,100 hours | Invoice Order | N/A
6 | 02/005/09 | 70171800 | Chirripan River | U/S of Gooljar Trace (3000m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
7 | 02/005/09 | 70171800 | Tributary to Oropouche River | D/S of Douglas Trace, Barrackpore (1500m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
8 | 02/005/09 | 70171800 | Oropouche River | D/S of Cowen Hamilton School Moruga (3000m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
9 | 02/005/09 | 70171800 | Congo River and Tributaries | D/S of Ribero Trace to Oropouche River (3000m) (Siparia) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
10 | 02/005/09 | 70171800 | Montique Drain | U/S of Guaracara River near Ali Trace (1000m) (Tabaquite) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A | `
11 | 02/005/09 | 70171800 | Tributary to Mitchell River | D/S from Assiah Trace / Mussarap Trace Barrackpore (1500m) (Naparima) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
12 | 02/005/09 | 70171800 | Fairfield River | D/S from Fairfield Road Princes Town (1500m) (Princes Town) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
13 | 02/005/09 | 70171800 | Mungal Channel | U/S and D/S of Pluck Road Woodland (1200m) (Oropuche West) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
14 | 02/005/09 | 70171800 | Blackwater Polder | U/S and D/S of Gopie Trace Debe (600m) (Oropuche West) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
15 | 02/005/09 | 70171800 | Tributary to Gucharon River | D/S of S.S Erin Road Debe (300m) (Oropuche East) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
16 | 02/005/09 | 70171800 | Tributary to John Lewis River | U/S and D/S of Rochard Road Penal (1400m) (Siparia) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
17 | 02/005/09 | 70171800 | Parforce River | U/S and D/S of Bedeau Street Gasparillo (2500m) (Tabaquite) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
18 | 02/005/09 | 70171800 | Tributary to Oropouche River | D/S from Rest House Trace St. Mary's (1100m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
19 | 02/005/09 | 70171800 | Laza Drain | D/S from Moruga Main Road, Basse Terre (800m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
20 | 02/005/09 | 70171800 | Cipero River | D/S of Solomon Hochoy Highway (1000m) (San Fernando East) | 2025-01-01 | 2025-09-30 | 500 hours | Invoice Order | N/A
21 | 02/005/09 | 70171800 | Guaracara River (Removal of Tree) |  | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
22 | 02/005/09 | 70171800 | Reform Drain |  | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
23 | 02/005/09 | 70171800 | St Louis River and Tributaries |  | 2025-01-01 | 2025-09-30 | 450 hours | Invoice Order | N/A
24 | 02/005/09 | 70171800 | Vessigny River Mouth |  | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
25 | 02/005/09 | 70171800 | Guapo River Mouth |  | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
26 | 02/005/09 | 70171800 | Oropouche River | U/S and D/S of Mussarap Trace (1500m) (Moruga/ Tableland) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
27 | 02/005/09 | 70171800 | Coora River | U/S and D/S of Gallai Trace, San Francique (2000m)(Siparia) | 2025-01-01 | 2025-09-30 | 500 hours | Invoice Order | N/A
28 | 02/005/09 | 70171800 | Coromata River | U/S of South Oropuche River (1000 m) (Oropuche West) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
29 | 02/005/09 | 70171800 | New Cut Channel | U/S and D/S of Pluck Road, Woodland (2500m) (Oropuche West) | 2025-01-01 | 2025-09-30 | 1,700 hours | Invoice Order | N/A
30 | 02/005/09 | 70171800 | Ramkhalia 1and2 Drain | U/S and D/S of Southern Main Road, Rousillac (3000m) (La Brea) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
31 | 02/005/09 | 70171800 | Mc Cullock Drain | D/S of S.S Erin Road, San Francique (1100m) Siparia | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
32 | 02/005/09 | 70171800 | Tarouba River | D/S of Berridge Trace to Highway (2500m) (Fyzabad) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
33 | 02/005/09 | 70171800 | Tributaries to Rookmin Drain | U/S of Douglas Trace, Moruga (2100m) (Moruga/ Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
34 | 02/005/09 | 70171800 | Oropouche River | U/S and D/S of Rochard Douglas Road, Barrackpore (4000m) (Naparima) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
35 | 02/005/09 | 70171800 | Erin River and Trib. | D/S of SS Erin Road, Palo Seco (4000m) (La Brea) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
36 | 02/005/09 | 70171800 | Oropouche River | U/S and D/S of S.S. Erin Road, Debe (2500m) (Oropouche East) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
37 | 02/005/09 | 70171800 | Fairfield River | D/S of Perry Young Road (2500m) ( Princes Town) | 2025-01-01 | 2025-09-30 | 700 hours | Invoice Order | N/A
38 | 02/005/09 | 70171800 | Cap-de-Ville River | D/S of South Central Road, Point Fortin to Guapo/Cap-de-Ville Main Road (3500m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
39 | 02/005/09 | 70171800 | Austin North and South Drain | U/S and D/S of S.M.R. Cedros (600m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
40 | 02/005/09 | 70171800 | Chimming Drain | U/S and D/S of Austin Ext. South Cedros (400m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
41 | 02/005/09 | 70171800 | Panchorie Drain | U/S and D/S of S.M.R. Coromandel. (500m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
42 | 02/005/09 | 70171800 | Poonah Main Drain | D/S of Poonah Road (1800m) (Tabaquite) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
43 | 02/005/09 | 70171800 | Marie Doulay and Tributaries | U/S and D/S of Bonne Aventure Main Road, Gasparillo (1800m) (Tabaquite) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
44 | 02/005/09 | 70171800 | John Lewis and Tributaries | D/S of Clarke Road (4100m) (Siparia) | 2025-01-01 | 2025-09-30 | 350 hours | Invoice Order | N/A
45 | 02/005/09 | 70171800 | Chester River | D/S of Dil Mohammed Road (2000m) (Siparia) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
46 | 02/005/09 | 70171800 | Coromata River | U/S and D/S of Penal Rock Road (4500m)(Siparia) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
47 | 02/005/09 | 70171800 | Beharry Drain and Tributaries | D/S of Mon Desir Road to Silverstream River (2000m) (Fyzabad) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
48 | 02/005/09 | 70171800 | Mc Lean Drain | D/S of Bois Jean Jean, Moruga (1000m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
49 | 02/005/09 | 70171800 | Coryal Drain | D/S of S.S Erin Road, Buenos Ayres (1800m) (La Brea) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
50 | 02/005/09 | 70171800 | Nagessar Channel | D/S of Penal Rock Road Hindu School, (2500m) (Siparia) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
51 | 02/005/09 | 70171800 | Rio Negro River | U/S of Siparia Old Road, Avocat (2000m) (Fyzabad) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
52 | 02/005/09 | 70171800 | Maingot River | U/S and D/S of St. George's Road, St Julien (2000m) (Princes Town) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
53 | 02/005/09 | 70171800 | Cipero River | U/S of Solomon Hochoy Highway, San Fernando (3000 m) (San Fernando East) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
54 | 02/005/09 | 70171800 | Ramkissoon Drain | U/S and D/S of Laltoo Trace, Debe (1000 m) (Oropuche West) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
55 | 02/005/09 | 70171800 | Amarsingh Drain | U/S and D/S of Penal Rock Road (1500 m) (Siparia) | 2025-01-01 | 2025-09-30 | 220 hours | Invoice Order | N/A
56 | 02/005/09 | 70171800 | Chinnebass River | D/S of Lalbeharry Trace, Debe (2500m) (Oropuche West) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
57 | 02/005/09 | 70171800 | Chinnebass River | D/S of Ramai Trace, Debe (1000m) (Oropouche West) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
58 | 02/005/09 | 70171800 | Lal Mahabir and Boojoon Drain | D/S Battan Trace to Ramlal Trace, Cunjal Road Barrackpore (2500 m) (Naparima) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
59 | 02/005/09 | 70171800 | Bedeau Drain | D/S Johnson Trace, Gasparillo (1500 m) (Tabaquite) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
60 | 02/005/09 | 70171800 | Cunapo River | U/S of Duck Pond (2500m) (Fyzabad) | 2025-01-01 | 2025-09-30 | 340 hours | Invoice Order | N/A
61 | 02/005/09 | 70171800 | Dunlop River and Tributaries | D/S of South Central Road to Filtration Plant Road (3500m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
62 | 02/005/09 | 70171800 | Blackwater Channel | U/S of Calco Pump Site (2000m) (Oropouche West) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
63 | 02/005/09 | 70171800 | Alligator Channel | D/S of Suchit Trace, Debe (1500m) (Oropouche West) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
64 | 02/005/09 | 70171800 | Trinidad River | U/S and D/S of Pluck Road, Woodland (6500m) (Oropouche West) | 2025-01-01 | 2025-09-30 | 550 hours | Invoice Order | N/A
65 | 02/005/09 | 70171800 | Carapal River | U/S and D/S of S.S Erin Road, Erin (3500m) (La Brea) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
66 | 02/005/09 | 70171800 | Cumuto River | U/S and D/S of Rochard Douglas Road, Barrackpore (4000 m) (Naparima) | 2025-01-01 | 2025-09-30 | 350 hours | Invoice Order | N/A
67 | 02/005/09 | 70171800 | Harrypile Drain | D/S of Sahadath Trace to Lengua River (1000m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
68 | 02/005/09 | 70171800 | Subrattee Drain | D/S of Paynter Trace - Cunjal Road Barrackpore to Oropouche River (1800m) (Naparima) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
69 | 02/005/09 | 70171800 | Ali Khan Drain | U/S and D/S of Ali Khan Trace ( 1500m)(Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
70 | 02/005/09 | 70171800 | Tributary to Oropouche River | D/S of Cumuto Road, #7 Barrackpore (1400m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
71 | 02/005/09 | 70171800 | Blackwell Drain | D/S of Taylor Trace, St Mary's (400m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
72 | 02/005/09 | 70171800 | Rest House Trace Drain | D/S and U/S of Rest House Trace, St Mary's (450m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
73 | 02/005/09 | 70171800 | White Trace Drain | U/S and D/S of White Trace, St. May's, Moruga (500m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
74 | 02/005/09 | 70171800 | Tributary to Jokhan River | U/S of Poui Trace (500m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
75 | 02/005/09 | 70171800 | Sielto Drain | D/S of St Mary's, Moruga (500m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
76 | 02/005/09 | 70171800 | Salick Drain | U/S and D/S of La Rufin Moruga (1200 m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
77 | 02/005/09 | 70171800 | Ramadhar Drain | U/S and D/S of La Rufin Moruga (1000 m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
78 | 02/005/09 | 70171800 | Marabella River | U/S and D/S of Union Park, Marabella (2500m)(Pointe a Pierre) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
79 | 02/005/09 | 70171800 | Marabella River | D/S of Southern Main Road, Marabella (1500m) (Pointe a Pierre) | 2025-01-01 | 2025-09-30 | 750 hours | Invoice Order | N/A
80 | 02/005/09 | 70171800 | Teemul Channel | U/S and D/S of Jokhan Branch Trace (1800m) (Oropouche West) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
81 | 02/005/09 | 70171800 | Blackwater River | U/S and D/S of New Colonial Road, Barrackpore (3200m) (Oropouche East) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
82 | 02/005/09 | 70171800 | Cipero River (PAVED SECTION ONLY) | U/S and D/S of South Trunk Road (2000m) (San Fernando West) | 2025-01-01 | 2025-09-30 | 1,050 hours | Invoice Order | N/A
83 | 02/005/09 | 70171800 | Techier 1and2 | D/S of S.M.R to Dunlop River, (2000m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
84 | 02/005/09 | 70171800 | Maitland Trace Drain | D/S of Maitland Trace, Moruga (500m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 180 hours | Invoice Order | N/A
85 | 02/005/09 | 70171800 | Ramadhar Drain | D/S of Lance Mitan, Moruga (500m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 100 hours | Invoice Order | N/A
86 | 02/005/09 | 70171800 | Jokhan River | D/S of Poui Trace (2500m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
87 | 02/005/09 | 70171800 | Jokhan River | D/S of Hamilton Trace to Cumuto South Trace (2500 m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
88 | 02/005/09 | 70171800 | Tennent Channel | D/S of Doorbassa Trace, San Francique (2000 m) (Siparia) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
89 | 02/005/09 | 70171800 | Seedial Channel | D/S of Jhulai Branch Trace, Penal (2000 m) (Siparia) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
90 | 02/005/09 | 70171800 | Columbia River | D/S of Southern Main Road, Cedros (1500m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
91 | 02/005/09 | 70171800 | Guapo River and Tributaries | D/S of Highway to Filtration Plant Road, Point Fortin (2500 m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
92 | 02/005/09 | 70171800 | Duck Pond River | U/S and D/S of Pluck Road (5700m) (Oropouche West) | 2025-01-01 | 2025-09-30 | 550 hours | Invoice Order | N/A
93 | 02/005/09 | 70171800 | Scotts 1 and 2 | U/S and D/S of Mendez Trace, Penal (3000 m) (Siparia) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
94 | 02/005/09 | 70171800 | Rampersad Drain | U/S and D/S SMR, Coromandel, Cedros (1800m) (Point Fortin) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
95 | 02/005/09 | 70171800 | Seebalack Drain | U/S Rochard Road, Penal (2000 m) (Siparia) | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
96 | 02/005/09 | 70171800 | Curampo River | D/S of SS Erin Road (3000m) (Siparia) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
97 | 02/005/09 | 70171800 | Saunders Trace Drain | U/S Saunders Trace St. Mary's, Moruga (2000 m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
98 | 02/005/09 | 70171800 | Oropouche River | D/S of Douglas Trace St. Mary's, Moruga (3000 m) (Moruga/Tableland) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
99 | 02/005/09 | 70171800 | Cupie River | D/S from Morne Diable to Mendez (2500 m) (Siparia) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
100 | 02/005/09 | 70171800 | Cunapo River | D/S of Standard Road, Fyzabad (2000 m) (Fyzabad) | 2025-01-01 | 2025-09-30 | 350 hours | Invoice Order | N/A
101 | 02/005/09 | 70171800 | Tributaries to Sangre Chiquito River | LP.#120 Oropouche Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
102 | 02/005/09 | 70171800 | Blackwater River | LP.#214 Cunapo Southern Main Road, Charuma Village, Biche | 2025-01-01 | 2025-09-30 | 700 hours | Invoice Order | N/A
103 | 02/005/09 | 70171800 | Tributary to Killdeer River | 3km Killdeer Trace River (off Tabaquite Rd) Rio Claro | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
104 | 02/005/09 | 70171800 | La Savanne River (Upstream and Downstream) | 15.5km Newlands Village, Guayaguayare Mayaro | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
105 | 02/005/09 | 70171800 | Melajo River and Tributaries | Vega De Oropouche Sangre Grande | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
106 | 02/005/09 | 70171800 | Tributaries to Blackwater River | LP.#224 Charuma Village, Biche | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
107 | 02/005/09 | 70171800 | Nariva River | Mahabalsingh 1st Branch Rd | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
108 | 02/005/09 | 70171800 | Tributary to Ortoire River | Balata East Road, Naparima Mayaro Road, Bristol Village, | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
109 | 02/005/09 | 70171800 | Cunapo River | Lp#116 Oropouche Road | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
110 | 02/005/09 | 70171800 | Redwater River | Off Martin Saza Road, Lassalle Road, Biche | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
111 | 02/005/09 | 70171800 | Clearwater River | 42-42.5km Naparima Mayaro Rd Rio Claro | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
112 | 02/005/09 | 70171800 | Sea Spray Drain | LP.#38 Resthouse Village, Manzanilla Road, Mayaro | 2025-01-01 | 2025-09-30 | 100 hours | Invoice Order | N/A
113 | 02/005/09 | 70171800 | Bamboo River and Tributaries | Lp#16 Vega De Oropouche | 2025-01-01 | 2025-09-30 | 350 hours | Invoice Order | N/A
114 | 02/005/09 | 70171800 | Tambolatay River | Martin Saza Road, Lassalle, Biche | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
115 | 02/005/09 | 70171800 | Mantacool River | Warwell 2nd Road ,Warwell | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
116 | 02/005/09 | 70171800 | Rabita Drain | LP.#32 Resthouse Village, Manzanilla Road, Mayaro | 2025-01-01 | 2025-09-30 | 100 hours | Invoice Order | N/A
117 | 02/005/09 | 70171800 | Tributary to Cunapo River | Jarasingh Junction Guaico Tamana Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
118 | 02/005/09 | 70171800 | Biche River | Corner Lassalle Road and CSMR, Biche | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
119 | 02/005/09 | 70171800 | Wynappie River | 1.5km Guayaguayare Rd Rio Claro | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
120 | 02/005/09 | 70171800 | Cato Main Drain-upstream and downstream | B1/1 Old Guayaguayare Road, Calmapas Village, Guayaguayare | 2025-01-01 | 2025-09-30 | 140 hours | Invoice Order | N/A
121 | 02/005/09 | 70171800 | Valencia River | Valencia Old Road | 2025-01-01 | 2025-09-30 | 120 hours | Invoice Order | N/A
122 | 02/005/09 | 70171800 | Tributary To Biche River | LP.#14 Lassalle Road, Cunapo Southern Main Road, Biche | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
123 | 02/005/09 | 70171800 | Wynappie River | 41km Naparima Mayaro Road Rio Claro | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
124 | 02/005/09 | 70171800 | Cemetery River and Tributaries | LP.#3 Edghill Road, Radix Village, Guayaguayare Road, Mayaro | 2025-01-01 | 2025-09-30 | 100 hours | Invoice Order | N/A
125 | 02/005/09 | 70171800 | Cunapo River | Upstream Cunapo Southern Road (by Swaha) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
126 | 02/005/09 | 70171800 | Samuel River and Tributaries | LP.#14 Martin Saza Road, Lassalle, Biche Biche/Tamana | 2025-01-01 | 2025-09-30 | 350 hours | Invoice Order | N/A
127 | 02/005/09 | 70171800 | Roach River and Tributaries | 34.5km Cunapo Southern Main Road Cushe Rio Claro/ Tableland Sub District (Mayaro Constituency) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
128 | 02/005/09 | 70171800 | Kernaham River and Tributaries | LP#74, off 79.5km Kernaham Village, Manzanilla Road, Mayaro | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
129 | 02/005/09 | 70171800 | Tributary to Oropouche River | Kissoon Trace off Toco Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
130 | 02/005/09 | 70171800 | Canque River | Somrah Trace, off Wade Road, Cunapo Southern Main Road, Biche | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
131 | 02/005/09 | 70171800 | Killdeer River | Sackeer Trace Navet | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
132 | 02/005/09 | 70171800 | Lagoon Mouths and Sea Outlets | Between Ortoire Vilage and Guayaguayare Village | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
133 | 02/005/09 | 70171800 | Tributary to Oropouche River | River Road off Toco Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
134 | 02/005/09 | 70171800 | Cuchee River | LP.#455 CSMR, Biche | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
135 | 02/005/09 | 70171800 | Tributary To Mantacool River | Harriot Trace,Robert Village | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
136 | 02/005/09 | 70171800 | Tributary to Mahaut River | LP.#1097 Naparima Mayaro Road, Union Vilage, Mayaro | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
137 | 02/005/09 | 70171800 | Quare River and Tributaries | Lp#79 Valencia Old Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
138 | 02/005/09 | 70171800 | Tributary to Cuchee River | Corner CSMR and Plum Mitan Road, Plum Mitan | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
139 | 02/005/09 | 70171800 | Tributary to Nariva River | 4km Legendre Rd Ecclesville (cricket Ground) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
140 | 02/005/09 | 70171800 | Cumaca River and Tributaries | Lp#86 Valencia Old Road | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
141 | 02/005/09 | 70171800 | Crossline River | Road 24, off Road 3, Caltoo Road, Plum Mitan Road | 2025-01-01 | 2025-09-30 | 500 hours | Invoice Order | N/A
142 | 02/005/09 | 70171800 | Tributary to Poole River | LP.#24 Glod Road, Poole Village | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
143 | 02/005/09 | 70171800 | Tributary to Arena River | 3mm Vega De Oropouche | 2025-01-01 | 2025-09-30 | 150 hours | Invoice Order | N/A
144 | 02/005/09 | 70171800 | Tributaries To Crossline River | Road 23, off Road 3, Caltoo Road, Plum Mitan Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
145 | 02/005/09 | 70171800 | Tributary to Poole River | Perry Road off Nohar Road, Poole Villlage | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
146 | 02/005/09 | 70171800 | Tributary to New Bolt River | Leemond Road off Oropouche Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
147 | 02/005/09 | 70171800 | Mainline River | Corner Somrah Road and RD 3 off Caltoo Road, Plum Mitan Road | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
148 | 02/005/09 | 70171800 | Tributary to Poole River | Pascual Road off Brothers Road | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
149 | 02/005/09 | 70171800 | Tributary to New Bolt River | Seecharan Trace Fishing Pond | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
150 | 02/005/09 | 70171800 | Trbutaries To Mainline River | LP.#77A Caltoo Road, Plum Mitan | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
151 | 02/005/09 | 70171800 | Tributary to Nariva River | LP.#59 Colondso Trace, Navet Village | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
152 | 02/005/09 | 70171800 | Tributary to Le Branche River | LP.#1100 Off Eastern Main Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
153 | 02/005/09 | 70171800 | Petite Poole River and Tributaries | LP.#89 Plum Mitan Road, Plum Mitan | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
154 | 02/005/09 | 70171800 | Nariva River | LP.#120 Cunapo Southern Main Road | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
155 | 02/005/09 | 70171800 | Tributary to Cunapo River | Regiment Corner Toco Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
156 | 02/005/09 | 70171800 | Cunapo River | LP.#268 Guaico Tamana Road, Tamana Village, Tamana | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
157 | 02/005/09 | 70171800 | Tributary To Nariva River | LP.#8 Location Road, Navet Village | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
158 | 02/005/09 | 70171800 | Tributary to Cunapo River | LP.#95 Oropouche Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
159 | 02/005/09 | 70171800 | Cunapo River | Ganteuma Trace, Nestor Village, Tamana | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
160 | 02/005/09 | 70171800 | Tributary to Poole River | 35.5km Naparima Mayaro Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
161 | 02/005/09 | 70171800 | Tributary to Bamboo River | Members Road Vega De Oropouche | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
162 | 02/005/09 | 70171800 | Tributary to Poole River | LP.#75A Lazarri Road,Poole | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
163 | 02/005/09 | 70171800 | Tributaries to Bamboo River | Lp#30 Vega De Oropouche | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
164 | 02/005/09 | 70171800 | Tributary to Clear Water River | 1km Old Rio Claro Mayaro Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
165 | 02/005/09 | 70171800 | Tributaries to Caigual River | Flemming Junction Fising Pond | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
166 | 02/005/09 | 70171800 | Caigual River Downstream | Genda Road Fishing Pond | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
167 | 02/005/09 | 70171800 | Hunter River | Turure Road off the Eastern Main Road | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
168 | 02/005/09 | 70171800 | Tributary to Guaico River | Railway Road, Guaico, Sangre Grande | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
169 | 02/005/09 | 70171800 | Tributary to Sangre Grande River | Loversville Village Coalmine | 2025-01-01 | 2025-09-30 | 180 hours | Invoice Order | N/A
170 | 02/005/09 | 70171800 | Tributary to Cunapo River | Shepherd Lane off Cunapo Southern | 2025-01-01 | 2025-09-30 | 150 hours | Invoice Order | N/A
171 | 02/005/09 | 70171800 | Tributaries to Swaha Main Drain | Barker Trace (next to double man) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
172 | 02/005/09 | 70171800 | Tributary to Cunapo River | 1 1/2 MM Cunapo Southern Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
173 | 02/005/09 | 70171800 | Tributary to Guaico River | Marchak Trace off Foster Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
174 | 02/005/09 | 70171800 | Blackwater River and Tributaries | Sahadeen Trace Toco Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
175 | 02/005/09 | 70171800 | Manning Ravine | Logan Drive off Toco Road | 2025-01-01 | 2025-09-30 | 80 hours | Invoice Order | N/A
176 | 02/005/09 | 70171800 | Guaico River and Tributaries | La Seiva Road off Toco Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
177 | 02/005/09 | 70171800 | Guaico River and Tributaries | Henderson Street | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
178 | 02/005/09 | 70171800 | Sangre Chiquito River and Tributaries | Boodoo Highway off Oropouche Road | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
179 | 02/005/09 | 70171800 | Sangre Chiquito River and Tributaries | LP.#118 Oropouche Road Sangre Grande | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
180 | 02/005/09 | 70171800 | Timital River and Tributaries | Vega De Oropouche | 2025-01-01 | 2025-09-30 | 500 hours | Invoice Order | N/A
181 | 02/005/09 | 70171800 | Bamboo River and Tributaries Downstream | 2MM Vega De Oropouche Road | 2025-01-01 | 2025-09-30 | 500 hours | Invoice Order | N/A
182 | 02/005/09 | 70171800 | James Smart River | Sangre Chiquito opposite Warden Road | 2025-01-01 | 2025-09-30 | 500 hours | Invoice Order | N/A
183 | 02/005/09 | 70171800 | Tributary to Cunaripo River | Guaico Tamana Road next to De Gannes and Jawahir | 2025-01-01 | 2025-09-30 | 150 hours | Invoice Order | N/A
184 | 02/005/09 | 70171800 | Cunaripo River | LP.#A60 Guaico Tamana Road | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
185 | 02/005/09 | 70171800 | Salazar River | LP.#8 Roop Trace Off Little Coora Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
186 | 02/005/09 | 70171800 | Tributaries to Salazar River | Lp#116 Little Coora Road | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
187 | 02/005/09 | 70171800 | Tributary to Cunapo River | Lot#699 Guaico Tamana Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
188 | 02/005/09 | 70171800 | Tributary to Le Branche River | Eastern Main Road Manzanilla next to Jehovah Witness Church | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
189 | 02/005/09 | 70171800 | Dubloon River | Eastern Main Road Manzanilla by Beach Resort | 2025-01-01 | 2025-09-30 | 150 hours | Invoice Order | N/A
190 | 02/005/09 | 70171800 | Sangre Chiquito River and Tributaries | Warden Road off Eastern Main Road Sangre Chiquito Sangre Grande /Toco Sub District (Cumuto/Manzanilla Constituency) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
191 | 02/005/09 | 70171800 | Tributary to Sangre Chiquito River | LP.#34 Boodoo Highway | 2025-01-01 | 2025-09-30 | 180 hours | Invoice Order | N/A
192 | 02/005/09 | 70171800 | Tributary to Oropouche River | Emamdie Trace Leemond | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
193 | 02/005/09 | 70171800 | Tributary to Cunapo River | Veronica Boulevard | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
194 | 02/005/09 | 70171800 | Le Branche River and Tributaries | Eastern main road Manzanilla | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
195 | 02/005/09 | 70171800 | Tributaries to Caigual River | Elijah Road 1st Caigual | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
196 | 02/005/09 | 70171800 | Tributary to Le Branche River | Logan Road North Manzanilla | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
197 | 02/005/09 | 70171800 | Tributary to Le Branche River | LP.#1090 Eastern Main Road Manzanila | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
198 | 02/005/09 | 70171800 | Tributary to Caigual River | Lp#61 Yaigual Road | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
199 | 02/005/09 | 70171800 | Tributary to Quare River | LP.#64 Redhead Trace,Turure | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
200 | 02/005/09 | 70171800 | Tributary to Sangre Chiquito River | 1st Caigual Road off Eastern Main Road | 2025-01-01 | 2025-09-30 | 250 hours | Invoice Order | N/A
201 | 02/005/09 | 70171800 | Guaico River and Tributaries | LP.#56 La Seiva Road | 2025-01-01 | 2025-09-30 | 440 hours | Invoice Order | N/A
202 | 02/005/09 | 70171800 | Diego Martin River | Upstream Western Main Rd to Morne Coco Rd. Upstream Jasper Avenue, Upstream Crystal Stream | 2025-01-01 | 2025-09-30 | 7,250 hours | Invoice Order | N/A
203 | 02/005/09 | 70171800 | Caroni River | Greenvale 0km-1km d/s Tumpuna Bridge, 1km-2km Greenvale d/s Tumpuna Bridge, Greenvale 2km-3km d/s Tumpuna Bridge | 2025-01-01 | 2025-09-30 | 6,000 hours | Invoice Order | N/A
204 | 02/005/09 | 70171800 | Centeno River | Upstream and Downstream Centeno rd (La Horquetta/Talparo) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
205 | 02/005/09 | 70171800 | Caroni River | Upstream Tumpuna bridge (La Horquetta/Talparo) | 2025-01-01 | 2025-09-30 | 1,500 hours | Invoice Order | N/A
206 | 02/005/09 | 70171800 | Caroni River | Cumuto Santa Marie Emmanuelle (La Horquetta/ Talparo) | 2025-01-01 | 2025-09-30 | 1,500 hours | Invoice Order | N/A
207 | 02/005/09 | 70171800 | San Juan River | Downstream Johnny King Weir.Downstream weir #2 and Downstream Concord road to EMR | 2025-01-01 | 2025-09-30 | 2,800 hours | Invoice Order | N/A
208 | 02/005/09 | 70171800 | Guanapo River | Upstream and Downstream Guanapo Treatment Facility Arima,Downstream Readymix road to Manuel Congo Road, | 2025-01-01 | 2025-09-30 | 4,500 hours | Invoice Order | N/A
209 | 02/005/09 | 70171800 | San Juan River Weir | Johnny King Road Bridge to weir Aranguez (St Joseph ) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
210 | 02/005/09 | 70171800 | Morne Coco Silt Trap and downstream Morne Coco Ravine | Coco View Terrace | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
211 | 02/005/09 | 70171800 | Trainline Ravine | Upstream trainline (La Horquetta/Talparo) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
212 | 02/005/09 | 70171800 | Thomas Trace Main Drain | Downstream EMR (Arouca/ Maloney) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
213 | 02/005/09 | 70171800 | Arima River | Upstream EMR (Arima), Downstream EMR Pinto | 2025-01-01 | 2025-09-30 | 6,700 hours | Invoice Order | N/A
214 | 02/005/09 | 70171800 | Mora Ravine | Downstream Arima Old Road (Arouca/ Maloney) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
215 | 02/005/09 | 70171800 | Niherst Science Centre Drain and Interlots Tributaries | Downstream CRH/WAY (Arouca Maloney) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
216 | 02/005/09 | 70171800 | Salegam Ravine | Cumuto Santa Marie Emmanuelle (Cumuto / Manzanilla) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
217 | 02/005/09 | 70171800 | Hawkins Main Drain | Downstream Highway & Downstream Garden Road (St. Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
218 | 02/005/09 | 70171800 | Mausica River | Up and Downstream Centeno Road & Downstream CRH/way (D'abadie/Omeara) | 2025-01-01 | 2025-09-30 | 1,600 hours | Invoice Order | N/A
219 | 02/005/09 | 70171800 | Mausica River | Up and Downstream Centeno Road, Downstream CRH/way(D'abadie/Omeara) | 2025-01-01 | 2025-09-30 | 2,800 hours | Invoice Order | N/A
220 | 02/005/09 | 70171800 | Mausica River | Upstream EMR (D'abadie/Omeara) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
221 | 02/005/09 | 70171800 | Runway Drain | Downstream Mausica Road (Dabadie/ Omeara) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
222 | 02/005/09 | 70171800 | Arena Ravine | Talparo Cumuto Road, (La Horquetta/ Talparo) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
223 | 02/005/09 | 70171800 | Trainline Ravine | Downstream Trainline (La Horquetta /Talparo) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
224 | 02/005/09 | 70171800 | Arouca River | Downstream PBR / Bon Air Gardens (Lopinot/ Bon Air) | 2025-01-01 | 2025-09-30 | 2,000 hours | Invoice Order | N/A
225 | 02/005/09 | 70171800 | Arouca River | Up and Downstream Golden Grove Road (Arouca/ Maloney) | 2025-01-01 | 2025-09-30 | 1,500 hours | Invoice Order | N/A
226 | 02/005/09 | 70171800 | Arouca River | Downstream CR Hway Left Bank of watercourse in vicinity Oropune housing development. (St Augustine) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
227 | 02/005/09 | 70171800 | Lopinot River | Upstream and downstream Recreation Area (Lopinot/ Bon Air West) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
228 | 02/005/09 | 70171800 | Carapo River | Carapo Road (Dabadie Omeara ) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
229 | 02/005/09 | 70171800 | Jokhan Trace Carapo Ravine | Carapo Road (Dabadie Omeara ) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
230 | 02/005/09 | 70171800 | Jamba Ravine | upstream PBR to Pine Ridge Heights Lopinot Bon Air (Lopinot Bon Air West) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
231 | 02/005/09 | 70171800 | Dunderhill Main Drain | Downstream Dunderhill road (Lopinot Bon Air West) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
232 | 02/005/09 | 70171800 | Rainbow Crest Silt Trap and Ravine downstream | Downstream Rainbow Crest Park 1st Street (Lopinot Bon Air West) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
233 | 02/005/09 | 70171800 | Blackwater Ravine | Downstream Dunderhill Road to outfall (Lopinot/ Bon Air West) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
234 | 02/005/09 | 70171800 | Blackman Ravine and Tributary | Downstream Bassie Street to Outfall (St Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
235 | 02/005/09 | 70171800 | Guayabal Ravine | Downstream Freeman Rd. to Outfall Caroni River (St Augustine) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
236 | 02/005/09 | 70171800 | Macoya Main Drain | Down stream CRH to Outfall (St Augustine ) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
237 | 02/005/09 | 70171800 | Wilkinson Main Drain | Downstream Wilkinson Street P.B.R (St Augustine) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
238 | 02/005/09 | 70171800 | Ansa Drain | Down stream CRH (St Augustine) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
239 | 02/005/09 | 70171800 | College Main Drain and Tributaries | Downstream CRH (St Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
240 | 02/005/09 | 70171800 | Cannings Main Drain | Downstream CRH Tunapuna (St Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
241 | 02/005/09 | 70171800 | Oropune River | Downstream Piarco Old Road (TT Post Head Quarters) To Outfall (St Augustine) | 2025-01-01 | 2025-09-30 | 3,600 hours | Invoice Order | N/A
242 | 02/005/09 | 70171800 | Valsayn Main Drain | Bamboo #2 (St. Augustine) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
243 | 02/005/09 | 70171800 | N.U.G.F.W Drain and Tributaries | Downstream S.M.R (St Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
244 | 02/005/09 | 70171800 | Mexico River | Downstream Eastern Main Road to CR H/way (Arima) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
245 | 02/005/09 | 70171800 | Mexico River | Downstream CRHway (Arima) | 2025-01-01 | 2025-09-30 | 1,000 hours | Invoice Order | N/A
246 | 02/005/09 | 70171800 | Sunrise Park Silt Trap and Drain | Trincity, College Road (Arouca Maloney) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
247 | 02/005/09 | 70171800 | Tunapuna River | Upstream CRH/WAY To PBR (St. Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
248 | 02/005/09 | 70171800 | Cane Farm Main Drain | Opposite Trincity Mall St. Augustine (Arouca/ Maloney) | 2025-01-01 | 2025-09-30 | 3,200 hours | Invoice Order | N/A
249 | 02/005/09 | 70171800 | Tacarigua River | Upstream and Downstream E.M.R (St.Augustine | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
250 | 02/005/09 | 70171800 | Miss Gutter Ravine | Up stream Davis Street (Lopinot/ Bon Air West) | 2025-01-01 | 2025-09-30 | 4,200 hours | Invoice Order | N/A
251 | 02/005/09 | 70171800 | New Blue Waters Drain | Downstream CRH (St Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
252 | 02/005/09 | 70171800 | Agua Santa River | Downstream Eastern Main Road to CR Hway (Arima) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
253 | 02/005/09 | 70171800 | Dunderhill Main Drain | Arouca (Lopinot/ Bon Air West) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
254 | 02/005/09 | 70171800 | Mausica River | Upstream CR Highway (D'abadie/O'meara) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
255 | 02/005/09 | 70171800 | La Horquetta Main Drain | La Horquetta (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
256 | 02/005/09 | 70171800 | Talparo River | San Rapheal (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
257 | 02/005/09 | 70171800 | Pinto Ravine | Trainline Road Pinto (Arima) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
258 | 02/005/09 | 70171800 | Repost Ravine | Brazil Village( La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
259 | 02/005/09 | 70171800 | Skimming Drain | D/s CRH Tunapuna (St Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
260 | 02/005/09 | 70171800 | Mt Dor Silt Trap | Mt. Dor (St. Joseph) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
261 | 02/005/09 | 70171800 | San Juan River | Downstream P.B.R. (St. Joseph) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
262 | 02/005/09 | 70171800 | Mt Lambert Main Drain | Mt Lambert (St. Joseph) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
263 | 02/005/09 | 70171800 | St Joseph River | Upstream CRH Hway to Farm Road (St Joseph) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
264 | 02/005/09 | 70171800 | La Horquette River | Downstream Western Main Road, Glenco (Diego Martin West) | 2025-01-01 | 2025-09-30 | 750 hours | Invoice Order | N/A
265 | 02/005/09 | 70171800 | Blue Range Silt Trap | Blue Range Avenue (Diego Martin North East) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
266 | 02/005/09 | 70171800 | St Joseph River | Upstream Farm Rd. to Maracas St Joseph Bridge (St. Joseph) | 2025-01-01 | 2025-09-30 | 1,600 hours | Invoice Order | N/A
267 | 02/005/09 | 70171800 | Carib Main Drain | St. Joseph (St. Joseph) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
268 | 02/005/09 | 70171800 | Tributary to Arthur Lok Jack Drain | Behind Authur Lok Jack IOB (St. Joseph) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
269 | 02/005/09 | 70171800 | Martin Main Drain and Trib | UWI Field station and T & TEC (St. Joseph) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
270 | 02/005/09 | 70171800 | St. Anns / East Dry River | Downstream old St. Joseph Road to CRH/way | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
271 | 02/005/09 | 70171800 | St Ann's Silt Trap | St Ann's Roundabout Port of Spain North (St Anns East) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
272 | 02/005/09 | 70171800 | Capriatta Ravine | The settlement Santa Cruz (St. Ann's East) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
273 | 02/005/09 | 70171800 | La Pastora River | Upstream Saddle Road (St. Anns East) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
274 | 02/005/09 | 70171800 | Santa Cruz River | D/s Hololo Bridge to Saddle road (St. Anns East) | 2025-01-01 | 2025-09-30 | 3,200 hours | Invoice Order | N/A
275 | 02/005/09 | 70171800 | Maracas Bay River | From Village to outfall (St. Anns East) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
276 | 02/005/09 | 70171800 | Granford River | From Village to outfall (St. Anns East) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
277 | 02/005/09 | 70171800 | Rincon River and Tributaries | Upstream and Downstream North Coast Road (St. Anns East) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
278 | 02/005/09 | 70171800 | Gasparillo River | El Perico Road, off Gasparillo Road, Santa Cruz. (St. Anns East) | 2025-01-01 | 2025-09-30 | 1,600 hours | Invoice Order | N/A
279 | 02/005/09 | 70171800 | Sam Boucaud Ravine | From Undercover Nurseries to Police Station Santa Cruz (St Anns East) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
280 | 02/005/09 | 70171800 | Barataria Main Drain | Downstream Highway (Barataria/San Juan) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
281 | 02/005/09 | 70171800 | Corbeau Drain | Downstream CR Hway (Barataria/San Juan) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
282 | 02/005/09 | 70171800 | Malick River | Downstream Barataria (Barataria/San Juan) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
283 | 02/005/09 | 70171800 | Malick Silt Trap and Desilting Upstream | Barataria (Barataria San Juan) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
284 | 02/005/09 | 70171800 | Sadhoo Trace Outfall Drain | From Sadhoo Trace to outfall at Barataria Main Drain Downstream CRH (Barataria/San Juan) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
285 | 02/005/09 | 70171800 | Detention Pond | Abbatoir Road Port of Spain (Port of Spain South) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
286 | 02/005/09 | 70171800 | Mc Alister Drain | Beetham Gardens (Port Of Spain South) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
287 | 02/005/09 | 70171800 | VMCOTT | Beetham Gardens (Port of Spain South) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
288 | 02/005/09 | 70171800 | John John Silt traps | Foster Road, Laventille (Port of Spain South) | 2025-01-01 | 2025-09-30 | 700 hours | Invoice Order | N/A
289 | 02/005/09 | 70171800 | Beetham Drain Parallel to PBR | Beetham Gardens Morvant, (Laventille West / Laventille East) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
290 | 02/005/09 | 70171800 | PBR Crossing Beetham Gardens | Beetham Gardens (Port of Spain South) | 2025-01-01 | 2025-09-30 | 500 hours | Invoice Order | N/A
291 | 02/005/09 | 70171800 | Collector Drain | South of Beetham Highway (Port of Spain South) | 2025-01-01 | 2025-09-30 | 2,000 hours | Invoice Order | N/A
292 | 02/005/09 | 70171800 | NP Drain | Beetham Gardens (Port of Spain South) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
293 | 02/005/09 | 70171800 | CGA Drain | Beetham Gardens (Port of Spain South) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
294 | 02/005/09 | 70171800 | Hell Yard Drain (TELCO) | Beetham Gardens (Port of Spain South) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
295 | 02/005/09 | 70171800 | Wharton Street (Servol) | Beetham Gardens (Port of Spain South) | 2025-01-01 | 2025-09-30 | 1,600 hours | Invoice Order | N/A
296 | 02/005/09 | 70171800 | Feeder Drain to the Lighthouse Pump Station | Downstream Wrightson Road, (Port of Spain South) | 2025-01-01 | 2025-09-30 | 1,200 hours | Invoice Order | N/A
297 | 02/005/09 | 70171800 | Cascade River | Upstream and Downstream Cascadia Hotel ( Port of Spain North/ St. Anns West) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
298 | 02/005/09 | 70171800 | Perseverance Silt Trap | Maraval Haleland Park (Diego Martin North East) | 2025-01-01 | 2025-09-30 | 900 hours | Invoice Order | N/A
299 | 02/005/09 | 70171800 | Camacho & Cocorite Silt Traps | Upper Broome Street Diego Martin and Waterhole Cocorite (Diego Martin West) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
300 | 02/005/09 | 70171800 | La Seiva Ravine & Silt Trap | From Upstream La Seiva Terrace to outfall (Diego Martin North East ) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
301 | 02/005/09 | 70171800 | Bournes Road Ravine and Tributaries | Downstream Mucurapo Road to the outfall (Port of Spain South) | 2025-01-01 | 2025-09-30 | 900 hours | Invoice Order | N/A
302 | 02/005/09 | 70171800 | Honda River & Bi-Furcation System | from Bi-Furcation System, Edinburgh 500 to UBH Southbound (Caroni Central) | 2025-01-01 | 2025-09-30 | 1,600 hours | Invoice Order | N/A
303 | 02/005/09 | 70171800 | Clarke River and Tributaries | Ragoonanan Rd, Cunupia to Ghandiah River (Chaguanas East) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
304 | 02/005/09 | 70171800 | Aranguez Road East and West | Aranguez Access Road South (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
305 | 02/005/09 | 70171800 | Muller Canal West | Aranguez Access Road South to William St. pumpsite (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 120 hours | Invoice Order | N/A
306 | 02/005/09 | 70171800 | Bamboo #1 Collector and Tributaries | Bamboo Settlement #1 to Pumpsite (St. Joseph) | 2025-01-01 | 2025-09-30 | 560 hours | Invoice Order | N/A
307 | 02/005/09 | 70171800 | Drain #5 & #10 | Sadhu Trace, El Socorro (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 160 hours | Invoice Order | N/A
308 | 02/005/09 | 70171800 | Guayamare Compound and Irrigation drains | Guayamare, Charlieville (Chaguanas West) | 2025-01-01 | 2025-09-30 | 1200 hours | Invoice Order | N/A
309 | 02/005/09 | 70171800 | Melvin Canal and Tributaries | Ramsarran Trace to Guayamare New Cut River (Chaguanas West) | 2025-01-01 | 2025-09-30 | 320 hours | Invoice Order | N/A
310 | 02/005/09 | 70171800 | G.S.B Canal & D1 Irrigation Drain | Guayamare River to Bejucal Road, Warren (Chaguanas West) | 2025-01-01 | 2025-09-30 | 640 hours | Invoice Order | N/A
311 | 02/005/09 | 70171800 | Mc Lellan Drain | Endeavour Road, Chaguanas to Marchine River (Chaguanas West) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
312 | 02/005/09 | 70171800 | Lallan River | from Dass Trace, Enterprise to Marchine River. (Chaguanas East) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
313 | 02/005/09 | 70171800 | Felicity Pumpsite Collector Drains | Abidh Road to Cunupia River South Bank (Chaguanas West) | 2025-01-01 | 2025-09-30 | 320 hours | Invoice Order | N/A
314 | 02/005/09 | 70171800 | Cunupia River | UBH S/B to Jerningham Railway Road, Cunupia (Chaguanas East) | 2025-01-01 | 2025-09-30 | 1,280 hours | Invoice Order | N/A
315 | 02/005/09 | 70171800 | Coolie Canal | Sumaria Trace West, Charlieville to Guayamare River Old Cut (Chaguanas West) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
316 | 02/005/09 | 70171800 | Tributary to Caroni River | Ministry of Agriculture Field Station Centeno, Cocoa Genebank , San Raphael (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
317 | 02/005/09 | 70171800 | Palm Drive Outfall Drain | Las Lomas Road #1 going downstream (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 160 hours | Invoice Order | N/A
318 | 02/005/09 | 70171800 | Governer Trace Drain | Governor Trace to Las Lomas Road #1 (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 160 hours | Invoice Order | N/A
319 | 02/005/09 | 70171800 | Pandora Ravine | Mc Clean Trace, Las Lomas #1 to Caroni South Bank Road Las Lomas #2 (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 220 hours | Invoice Order | N/A
320 | 02/005/09 | 70171800 | Cascabelle Ravine | Las Lomas Road #1 to Guayamare River (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
321 | 02/005/09 | 70171800 | Cunupia River (U/S) & Tribs | Savary Road Extention Las Lomas #1 to Oakmount Gardens, Chin Chin Rd (Caroni East) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
322 | 02/005/09 | 70171800 | Cunupia River (D/S) & Tributaries | Oakmount Gardens, Chin Chin Rd to Lallo Trace, Cunupia (Caroni East) | 2025-01-01 | 2025-09-30 | 360 hours | Invoice Order | N/A
323 | 02/005/09 | 70171800 | Cunupia River (D/S) | Lallo Trace to Mc Nair Road Cunupia (Caroni East) | 2025-01-01 | 2025-09-30 | 360 hours | Invoice Order | N/A
324 | 02/005/09 | 70171800 | Cunupia River (D/S) | Mc Nair Road to Chin Chin Rd. (Caroni East) | 2025-01-01 | 2025-09-30 | 640 hours | Invoice Order | N/A
325 | 02/005/09 | 70171800 | Diana River | Bagna Trace Ext to Perseverance Rd, Chase Village (Couva North) | 2025-01-01 | 2025-09-30 | 180 hours | Invoice Order | N/A
326 | 02/005/09 | 70171800 | Diana River | Perserverance Rd, Chase Village to Roopsingh Rd, Carapichaima (Couva North) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
327 | 02/005/09 | 70171800 | Diana River | Roopsingh Rd to Brick Field Road (Mangrove), Carapichaima (Couva North) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
328 | 02/005/09 | 70171800 | Esparanza Main Drain | Diamond Road to Pheonix Park, Esperanza (Couva South) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
329 | 02/005/09 | 70171800 | Calcutta #2 Main Drain | UBH N/B to La Cuesa River (Couva South) | 2025-01-01 | 2025-09-30 | 280 hours | Invoice Order | N/A
330 | 02/005/09 | 70171800 | Perseverance Main Drain | Waterloo Rd to Gulf of Paria (Couva North) | 2025-01-01 | 2025-09-30 | 120 hours | Invoice Order | N/A
331 | 02/005/09 | 70171800 | Orange Valley Main Drain | Upstream & Downstream, Waterloo Road (Couva North) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
332 | 02/005/09 | 70171800 | Preysal River | Gran Couva Main Road, Preysal to Gran Couva River (Caroni Central) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
333 | 02/005/09 | 70171800 | Diana River | SSHH upstream to Arena River Outfall (Caroni Central) | 2025-01-01 | 2025-09-30 | 160 hours | Invoice Order | N/A
334 | 02/005/09 | 70171800 | Arena River | Tewarie South to Diana River (Caroni Central) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
335 | 02/005/09 | 70171800 | Beaucarro Main Drain and Tributaries | U/S & D/S Beaucarro Road, Mc Bean Couva (Couva South) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
336 | 02/005/09 | 70171800 | Tacarigua River | from Corner of Freeman Road & Trantrill Rd, St. Augustine to Caroni River (St. Augustine) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
337 | 02/005/09 | 70171800 | Sadoo Trace Ext Outfall Drain | Sadoo Trace Ext to Barataria Main Drain (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
338 | 02/005/09 | 70171800 | Marchine River | Rodney Road to Endeavour Road, Chagauanas (Caroni Central) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
339 | 02/005/09 | 70171800 | Marchine River and Detention Pond | Endeavour Road to Jerningham Junction Road (Caroni Central) | 2025-01-01 | 2025-09-30 | 1,920 hours | Invoice Order | N/A
340 | 02/005/09 | 70171800 | Guru Persad Drain and Detention Ponds #1 & #2, | Caroni Savannah Road, Charlieville to Borough Drain (Chaguanas West) | 2025-01-01 | 2025-09-30 | 480 hours | Invoice Order | N/A
341 | 02/005/09 | 70171800 | Warren Main Drain and Trib. | From Complex to Guayamare River (Chaguanas West) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
342 | 02/005/09 | 70171800 | Felicity Outfall Drains | Bet. Bernard Rd and Peters Field Rd (Chaguanas West) | 2025-01-01 | 2025-09-30 | 560 hours | Invoice Order | N/A
343 | 02/005/09 | 70171800 | Bovel Canal | UBH N/B to Guayamare River Old Cut (Chaguanas West) | 2025-01-01 | 2025-09-30 | 720 hours | Invoice Order | N/A
344 | 02/005/09 | 70171800 | Ghandiah River & Tributaries | Ravine Sable Road to Jagessar Street, Longdenville (Caroni Central) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
345 | 02/005/09 | 70171800 | Muller Canal East | Global Avenue to Aranguez Access Road South, El Socorro (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 180 hours | Invoice Order | N/A
346 | 02/005/09 | 70171800 | Collector Drain & Tibutary | William St. El Socorro to pumpsite (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 180 hours | Invoice Order | N/A
347 | 02/005/09 | 70171800 | Collector Drain | betw. William St & Sadhu Tr. El Socorro South (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
348 | 02/005/09 | 70171800 | Endeavour Main Drain | Jerningham Junction Road to Marchine River (Chaguanas West) | 2025-01-01 | 2025-09-30 | 880 hours | Invoice Order | N/A
349 | 02/005/09 | 70171800 | Borough Drain & Tributaries and Detention Pond #3 | Nandram Road to Pierre Road Connector, Charlieville (Chaguanas West) | 2025-01-01 | 2025-09-30 | 560 hours | Invoice Order | N/A
350 | 02/005/09 | 70171800 | Guayamare River New Cut | UBH N/B to Mangrove (Chaguanas West) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
351 | 02/005/09 | 70171800 | Chandanagore River & Tributary | SSHH Northbound to Diana River (Couva North) | 2025-01-01 | 2025-09-30 | 260 hours | Invoice Order | N/A
352 | 02/005/09 | 70171800 | Spring Vale Main Drain | Spring Vale Road to Indian Trail Road (near Milton Cricket Ground) (Couva South) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
353 | 02/005/09 | 70171800 | Munroe Road Outfall Drains | Munroe Road to Bejucal Road, Warren (Chaguanas West) | 2025-01-01 | 2025-09-30 | 380 hours | Invoice Order | N/A
354 | 02/005/09 | 70171800 | Bovel Canal | Warren Munroe Road to Ajodha Road, Warren (Chaguanas West) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
355 | 02/005/09 | 70171800 | Guayamare River Old Cut | Guayamare Link Road to Cunupia River (Chaguanas West) | 2025-01-01 | 2025-09-30 | 320 hours | Invoice Order | N/A
356 | 02/005/09 | 70171800 | Guayamare River New Cut (Upstream) | UBH S/B to Guayamare Headworks, Caroni Village (Chaguanas West) | 2025-01-01 | 2025-09-30 | 1,280 hours | Invoice Order | N/A
357 | 02/005/09 | 70171800 | Guayamare River (Upstream) | Guayamare Headworks to S.M.R Caroni Village Chaguanas. (Chaguanas West) | 2025-01-01 | 2025-09-30 | 720 hours | Invoice Order | N/A
358 | 02/005/09 | 70171800 | Genspec Drain | Warren Road, Cunupia to Guayamare River (Chaguanas West) | 2025-01-01 | 2025-09-30 | 400 hours | Invoice Order | N/A
359 | 02/005/09 | 70171800 | Caparo River downstream | From Woodford Lodge, Perseverance Road to Cacandee Road Ext., Petersfield Village (Chaguanas West) | 2025-01-01 | 2025-09-30 | 1,120 hours | Invoice Order | N/A
360 | 02/005/09 | 70171800 | Guayamare River (U/S) | Southern Main Road to Kelly Irrigation (Caroni Caroni East) | 2025-01-01 | 2025-09-30 | 440 hours | Invoice Order | N/A
361 | 02/005/09 | 70171800 | Guayamare River (U/S) | Kelly Irrigation Channel to Hererra Trace (Caroni East) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
362 | 02/005/09 | 70171800 | Guayamare River (U/S) | Hererra Trace to Madras Road (Caroni East) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
363 | 02/005/09 | 70171800 | Guayamare River (U/S) | Madras Road to Ministry of Agriculture Livestock Station, El Carmen (Caroni East) | 2025-01-01 | 2025-09-30 | 600 hours | Invoice Order | N/A
364 | 02/005/09 | 70171800 | St Helena Main Drain, Downstream and Tribs. | Madras Road to Seunarine Trace, St. Helena (Caroni East) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
365 | 02/005/09 | 70171800 | Caroni River Airport 1,2,3,4 and Tributary | St Augustine. | 2025-01-01 | 2025-09-30 | 320 hours | Invoice Order | N/A
366 | 02/005/09 | 70171800 | Balata Ravine | Caroni South Bank Road El Carmen #2 to Madras Road. (Caroni East) | 2025-01-01 | 2025-09-30 | 210 hours | Invoice Order | N/A
367 | 02/005/09 | 70171800 | China Man Ravine | Seunarine Trace, Kelly to Guayamare River (Caroni East) | 2025-01-01 | 2025-09-30 | 180 hours | Invoice Order | N/A
368 | 02/005/09 | 70171800 | Cunupia River (D/S) | Chin Chin Rd,Cunupia to SMR (Caroni East) | 2025-01-01 | 2025-09-30 | 480 hours | Invoice Order | N/A
369 | 02/005/09 | 70171800 | Macaulay Main Drain | U/S & D/S Macaulay Trace, Claxton Bay (Couva South) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
370 | 02/005/09 | 70171800 | Sonny Ladoo Main Drain & Tributaries | Sonny Ladoo Traxe to SMR, Mc Bean Couva (Couva North) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
371 | 02/005/09 | 70171800 | Honda River | SSHH Northbound to Caparo River (Couva North) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
372 | 02/005/09 | 70171800 | Factory Road Drain | Factory Road to Honda River (Couva North) | 2025-01-01 | 2025-09-30 | 140 hours | Invoice Order | N/A
373 | 02/005/09 | 70171800 | T&TEC Substation Outfall Drains | T&TEC Substation Road (along UBH N/B) to Mangrove (Chaguanas West) | 2025-01-01 | 2025-09-30 | 120 hours | Invoice Order | N/A
374 | 02/005/09 | 70171800 | UBH Southbound Bamboo #3 Outfall Drain | UBH Southbound Bamboo #3 Boulevard to Bamboo #3 Pumpsite (St. Augustine) | 2025-01-01 | 2025-09-30 | 1,280 hours | Invoice Order | N/A
375 | 02/005/09 | 70171800 | Bovel Canal | Ajodha Road, Warren to UBH S/B (Chaguanas West) | 2025-01-01 | 2025-09-30 | 880 hours | Invoice Order | N/A
376 | 02/005/09 | 70171800 | Caparo River downstream | From Cacandee Road Ext., Petersfield Village to Mangrove (Chaguanas West) | 2025-01-01 | 2025-09-30 | 1,140 hours | Invoice Order | N/A
377 | 02/005/09 | 70171800 | Bridal Road Outfall Drain | Endeavour Insect Vector to Cunupia River. (Chaguanas West) | 2025-01-01 | 2025-09-30 | 320 hours | Invoice Order | N/A
378 | 02/005/09 | 70171800 | Pranz Garden Main Drain | Main St.,Pranz Garden to SMR, Claxton Bay (Point-A-Pierre) | 2025-01-01 | 2025-09-30 | 160 hours | Invoice Order | N/A
379 | 02/005/09 | 70171800 | U.T.T Drain | Rivulet Road to S.M.R, Couva (Couva South) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
380 | 02/005/09 | 70171800 | San Juan River | Churchill Roosevelt Highway (Westbound) to Caroni River (St. Joseph) | 2025-01-01 | 2025-09-30 | 640 hours | Invoice Order | N/A
381 | 02/005/09 | 70171800 | Diana River | SMR to Bagna Trace Ext, Chase Village (Couva North) | 2025-01-01 | 2025-09-30 | 780 hours | Invoice Order | N/A
382 | 02/005/09 | 70171800 | Lurkhur Drain | Phillip Road to Pierre Road (Chaguanas West) | 2025-01-01 | 2025-09-30 | 160 hours | Invoice Order | N/A
383 | 02/005/09 | 70171800 | Tributary to Pranz Gardens | SMR to Pranz Garden Main Drain, Claxton Bay (Point-A-Pierre) | 2025-01-01 | 2025-09-30 | 140 hours | Invoice Order | N/A
384 | 02/005/09 | 70171800 | Latchu Main Drain & Tributaries | SMR to Jerningham Railway Road, Cunupia (Chaguanas East) | 2025-01-01 | 2025-09-30 | 680 hours | Invoice Order | N/A
385 | 02/005/09 | 70171800 | Exchange Main Drain, McBean to Perseverance Road | Mc Bean to Waterloo Road (Couva North) | 2025-01-01 | 2025-09-30 | 280 hours | Invoice Order | N/A
386 | 02/005/09 | 70171800 | Powdharie River | S.S.H. to Powdharie Road (upstream) (Caroni Central) | 2025-01-01 | 2025-09-30 | 160 hours | Invoice Order | N/A
387 | 02/005/09 | 70171800 | Cunupia River | UBH N/B to Felicity Pumpsite (Chaguanas West) | 2025-01-01 | 2025-09-30 | 960 hours | Invoice Order | N/A
388 | 02/005/09 | 70171800 | Warrenville Main Outfall Drain | Robert Trace Warrenville to Guayamare River (Caroni East) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
389 | 02/005/09 | 70171800 | Econo Main Drain | Caroni Southbank Road to Guayamare River. | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
390 | 02/005/09 | 70171800 | Skimming Drain and Tribs | Southern Main Road Fredrick Settlement Caroni to UBH Southbound (Chaguanas West) | 2025-01-01 | 2025-09-30 | 800 hours | Invoice Order | N/A
391 | 02/005/09 | 70171800 | La Paille Outfall Drain | Southern Main road La Paille Gardens to Skimming Drain (Chaguanas West) | 2025-01-01 | 2025-09-30 | 320 hours | Invoice Order | N/A
392 | 02/005/09 | 70171800 | Ibis Gardens Outfall drain | Washington Round-a-bout Caroni to Skimming Drain (Chaguanas West) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
393 | 02/005/09 | 70171800 | Vishnu Boys Outfall | Southern Main road to Ibis Gardens Outfall drain (Chaguanas West) | 2025-01-01 | 2025-09-30 | 120 hours | Invoice Order | N/A
394 | 02/005/09 | 70171800 | Maraj Outfall Drain | Southern Main road to Skimming Drain (Chaguanas West) | 2025-01-01 | 2025-09-30 | 200 hours | Invoice Order | N/A
395 | 02/005/09 | 70171800 | Chootoo Drain | William St. El Socorro to Caroni River (Barataria / San Juan) | 2025-01-01 | 2025-09-30 | 1,60 hours | Invoice Order | N/A
396 | 02/005/09 | 70171800 | Chin Johnson Oufall Drain | Chin Johnson Road, Caparo to Caparo River (Caroni Central) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
397 | 02/005/09 | 70171800 | Welcome North Main Drain | from Ramcharitar Road to Welcome Road North (Chaguanas East) | 2025-01-01 | 2025-09-30 | 300 hours | Invoice Order | N/A
398 | 02/005/09 | 70171800 | Seeraj Outfall and Tributaries | Seeraj Trace, Chin Chin Road Cunupia to Guayamare River (Caroni East) | 2025-01-01 | 2025-09-30 | 720 hours | Invoice Order | N/A
399 | 02/005/09 | 70171800 | Boycato Outfall Drain | Boycato Road, Madras Cunupia (Caroni East) | 2025-01-01 | 2025-09-30 | 240 hours | Invoice Order | N/A
400 | 02/005/09 | 70171800 | Madoo Singh Ravine | Madras Road to Guayamare River (Caroni East) | 2025-01-01 | 2025-09-30 | 560 hours | Invoice Order | N/A
401 | 02/005/09 | 70171800 | Esparanza Outfall and Tributaries | Caroni Arena Road to Esparanza Trace, San Raphael (La Horquetta Talparo) | 2025-01-01 | 2025-09-30 | 395 hours | Invoice Order | N/A
IDF
1 | MOWT/DD/8/9/246 | 72141205 | St. Ann’s River proceeding upstream from bridge on lady young to bridge of cascade road - 0.00 to 516m (Phase I) | Reinforced Concrete Invert Rehabilitation | Fiscal 2023/2024 (Ongoing) | 2025-10-01 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
2 | MOWT/DD/8/9/248 | 72141205 | Rehabilitation Works Cascade and St. Anns River (Cascade - 919m, St Anns -79) Phase II | Reinforced Concrete Invert Rehabilitation | Fiscal 2023/2024 (Completed) | 2025-04-24 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
3 | MOWT/DD/8/9/243 | 72152707 | Maraval River. Pinhurst Park to Fens Furniture. Ch. 804m to 1291m (Phase I) | Construction of Reinforced Concrete Wall 2.4m (H) x 5m (L), Revetment Wall Repair, Rubble Masonry Wall Underpinning & Invert Rehabilitation | Fiscal 2023/2024 (Completed) | 2024-05-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
4 | MOWT/DD/8/9/247 | 72141205 | Diego Martin River from bridge on Wendy Fitzwilliam Blvd. proceeding upstream - 528.5m | Reinforced Concrete Invert Rehabilitation | Fiscal 2023/2024 (Completed) | 2024-06-23 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
5 | MOWT/DD/8/9/244 | 72152707 | Rehabilitation Works to Maraval River. Bridge at Simpson Drive to Pinehurst Park. Ch. 0.00m to 804m (Phase II) | Construction of Reinforced Concrete Wall 2.4m (H) x 18m (L), Reinforced Concrete Cross Wall 1m (W) x 1.5m (H) x 1.5m (L), Rubble Masonry Wall 2.4m (H) x 16m (L) & Invert Rehabilitation | Fiscal 2023/2024 (Completed) | 2024-05-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
6 | MOWT/DD/8/3/49 | 70171800 | Desilting & Clearing Cunapo River | Desilting and clearing Cunapo River, Cumuto Mnazanilla | Fiscal 2024/2025 | 2024-08-01 | 420 days (240 days for project duration & 180 days for defect liability period) | Limited Bidding | FIDIC Red Book
7 | MOWT/DD/NIPDEC/8/14/01 | 72152707 | Construction of a R.C Wall at LP#41 Santa Cruz Old Road, San Juan. | Works will include Construction of R.C. Wall 100m x 4m high | Fiscal 2023/2024 (Completed) | 2024-10-01 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
8 | MOWT/DD/NIPDEC/8/14/02 | 72152707 | Construction of a R.C Wall along Laventille Road, San Juan. | Works will include the Construction of a R.C. Wall 35m (L) x 4.7m (H), RC Wall 35m (L) x 3.65m (H). Riprap 4m wide x 0.5m depth x 6m length | Fiscal 2023/2024 (Completed) | 2024-08-17 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
9 | MOWT/DD/NIPDEC/8/14/03 | 72152707 | Construction of a R.C Wall along the San Juan River at Hidden Orchards, Santa Cruz. | Works will include the construction of a R.C. Wall 120m long x 4.7m high. | Fiscal 2023/2024 (Completed) | 2024-08-20 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
10 | MOWT/DD/NIPDEC/8/14/04 | 72141205 | Construction of a U-Section along Dyette Main -Jerningham Railway Rd, Cunupia Rd to Jerningham Railway Rd | Works will include the Construction of RC Open Box Drain 180m (L) x 3m (W) x 3m (H) | Fiscal 2023/2024 (Completed) | 2025-01-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
11 | MOWT/DD/NIPDEC/8/14/05 | 72152707 | Rehabilitation Works Along Malick River, Eastern Main Road, Barataria | Works will include the Construction of a R.C. Wall 70m long x 4m high and Invert Paving 155m long x 7m wide. Underpinning 310m | Fiscal 2023/2024 (Completed) | 2025-07-04 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
12 | MOWT/DD/NIPDEC/8/14/06 | 70171800 | Rehabilitation Works Along La Horquette River, Carenage | Walling and Paving | Fiscal 2023/2024 (Completed) | 2024-07-23 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
13 | MOWT/DD/NIPDEC/8/14/07 | 72152707 | Construction of a R.C Wall along Maraval River, Simpson Drive | R.C. Retaining Wall 4.7m (H) x 48m (L) | Fiscal 2023/2024 (Completed) | 2024-07-23 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
14 | MOWT/DD/NIPDEC/8/14/08 | 72152707 | Construction of Gabion Basket Walls Along Maraval River, St. Andrews Golf Course | Construction of Gabion Basket Wall 2.4m (H) x 220m (L) and Grad control Structures | Fiscal 2023/2024 (Completed) | 2024-08-20 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
15 | MOWT/DD/NIPDEC/8/14/09 | 72152707 | Construction of a R.C Wall at La Pastora Gardens, Santa Cruz | Works will include construction of R.C Wall at 3.7m High x 120m Length. | Fiscal 2023/2024 (Completed) | 2024-08-30 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
16 | MOWT/DD/NIPDEC/8/14/10 | 70171803 | Bank Rehabilitation along Powdharie River, Balmain, Couva | Bank Rehabilitation | Fiscal 2023/2024 (Completed) | 2024-10-05 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
17 | MOWT/DD/NIPDEC/8/14/11 | 72152707 | Construction of Gabion Basket Walls along the Matelot River, Matelot Community College, Paria Main Road | Construction of Maccaferri Branded Gabion Basket Retaining Structure - 140m (L) x 3m (H). | Fiscal 2023/2024 (Completed) | 2025-01-04 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
18 | MOWT/DD/NIPDEC/8/14/12 | 72152707 | Rehabilitation to Petit Valley Ravine adjacent to La Burnham Villas, Petit Valley | Works will include the Construction of a R.C. Wall 100m long x 3.65m high | Fiscal 2023/2024 (Completed) | 2024-10-05 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
19 | MOWT/DD/NIPDEC/8/14/13 | 72152707 | Rehabilitation Works to Cunupia River at #263 Southern Main Road, Cunupia | Construction of Reinforced Concrete Wall 4.7m (H) x 140m (L) | Fiscal 2023/2024 (Ongoing) | 2026-06-01 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
20 | MOWT/DD/NIPDEC/8/14/14 | 72141205 | Rehabilitation Works to San Juan River, Sundarsingh Drive, Aranguez, San Juan | Construction of 400m Long x 1.4m High x1.6m Wide Reinforced Concrete Box drain | Fiscal 2023/2024 (Completed) | 2025-02-08 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
21 | MOWT/DD/NIPDEC/8/14/15 | 72141205 | Construction of a R.C U-Section at #1 St. Michael Village, Las Cuevas | Works include construction of a R.C U-Section 3m wide x 3.65 high x 80m length. | Fiscal 2023/2024 (Completed) | 2024-11-02 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
22 | MOWT/DD/NIPDEC/8/14/16 | 72152707 | Construction of Reinforced Concrete Wall along Arima River in the vicinity of Buena Vista | Construction of Reinforced Concrete Wall 4.5m (H) x 100m (L) | Fiscal 2023/2024 (Completed) | 2025-05-15 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
23 | MOWT/DD/NIPDEC/8/14/17 | 72152707 | Rehabilitation Works Along the Tunapuna River., in the vicinity of Jorden, Terrace Tunapuna | Works will include the Construction of a R.C. Walls, 60m long x 3.65m high, 60m long x 2.4m high | Fiscal 2023/2024 (Completed) | 2024-12-19 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
24 | MOWT/DD/NIPDEC/8/14/18 | 72152707 | Rehabilitation Works along the St. Joseph River - in the vicinity of La Joya Administrative Complex | Construction of R.C Revetment Wall 7m (H) x 20m (L), R.C Wall 4.7m (H) x 20 m (L), Gabion Basket Wall 5m (H) x 30m (L), Rip Rap 30m (L) x 11m (W) 4 R.C Cross Walls 16m L, R.C Box Drain 6m (L) x 0.6m (H) x 0.6m (W) | Fiscal 2023/2024 (Completed) | 2025-01-18 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
25 | MOWT/DD/NIPDEC/8/14/19 | 72141205 | Construction of Reinforced Concrete Section at Bamboo #3 Pumpsite | R.C Section 400m (L) x 3 m (H) (Eastern Side) & 4.5m (S.D)Revetment (Western Side) Invert Paving 4m (W) | Fiscal 2023/2024 (Completed) | 2025-01-18 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
26 | MOWT/DD/NIPDEC/8/14/21 | 72141205 | Construction of a Reinforced Concrete U-Section at LP#52 Queen Drive, Bagatelle Road, Diego Martin | Reinforced Concrete U-Section, 3m (H) x 16m (L) | Fiscal 2023/2024 (Completed) | 2025-05-22 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
27 | MOWT/DD/NIPDEC/8/14/22 | 72152707 | Tributary to Lagoon Mahout River - B 1/1 Mayaro Guayaguayare Road | Works will include the Construction of RC Wall 225m (L) x 3.65m (H). | Fiscal 2023/2024 (Completed) | 2025-02-20 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
28 | MOWT/DD/NIPDEC/8/14/23 | 72152707 | Oropouche River, New Colonial Road Barrackpore | Works will include the Construction of RC Retaining Wall - 95m (L) x 4.7m (H) | Fiscal 2023/2024 (Ongoing) | 2025-02-04 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
29 | MOWT/DD/NIPDEC/8/14/24 | 70171800 | Redefinition of the Caroni River from the Uriah Butler Highway to the Gulf of Paria | Desilting of the river and its mouth | Fiscal 2023/2024 (Ongoing) | 2026-05-01 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
30 | MOWT/DD/NIPDEC/8/14/25 | 70171800 | Clearing and Desilting of the Diego Martin River Mouth | Desilting of the river and its mouth | Fiscal 2023/2024 (Ongoing) | 2026-05-01 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
31 | MOWT/DD/NIPDEC/8/14/26 | 72152707 | Wattley Circular, Mt, Pleasant | Construction of R.C Wall 4.7m H x 129m L and Gabion Basket Wall 4m H x 150m L | Fiscal 2023/2024 (Ongoing) | 2025-12-01 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
32 | MOWT/DD/NIPDEC/8/14/27 | 70171800 | Rehabilitation Works on the Diego Martin River from the bridge on Diego Martin Main Road | Rehabilitation Works along the Diego Martin River for 1397m | Fiscal 2023/2024 (Completed) | 2024-09-05 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
33 | MOWT/DD/NIPDEC/8/14/28 | 72152707 | Rehabilitation Works, Arima River In The Vicinity Of The Crossings, Arima. | Construction of Reinforced Concrete Wall 4.5m (H) x 100m (L) | Fiscal 2023/2024 (Completed) | 2025-08-15 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
34 | MOWT/DD/NIPDEC/8/14/29 | 72152707 | Construction of R.C Wall Downstream Cipero River from Gulf View Link Road Bridge To WASA Treatment Plant | Works will include the Construction of R.C. Wall 300m (L) x 5.6m (H) | Fiscal 2023/2024 (Completed) | 2025-08-09 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
35 | MOWT/DD/NIPDEC/8/14/30 | 72152707 | Construction of Reinforced Concrete Wall along Simeon Ravine, Sparrow Drive Ext. Petit Valley. | (a) Reinforced Concrete Wall 3.60m (H) x 52m (L). (b) Reinforced Concrete Box Drain 1.2m (W) x 2.0m (H) x 6.0m (L) | Fiscal 2023/2024 (Completed) | 2025-01-09 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
36 | MOWT/DD/NIPDEC/8/14/31 | 72152707 | Construction of Reinforced Concrete Wall along Cunupia River, Manzana Drive | (a) Reinforced Concrete Wall 4.7m (H) x 80m (L). (b) Reinforced Concrete Box Drain 0.6m (W) x 0.8m (H) x 6m (L). (c) Reinforced Concrete Box Drain 0.6m (W) x 0.8m (H) x 10m (L) | Fiscal 2023/2024 (Completed) | 2025-02-11 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
37 | MOWT/DD/NIPDEC/8/14/34 | 70171800 | Rehabilitation works along the St. Ann’s River behind Pizza Boys for a distance of 358m long between Chainage 595 to Chainage 953 | Desilting and degrassing works along the St. Ann’s River for a distance of 358m long behind Pizza Boys St Ann’s. It also entails the construction any outfall drains that needs to be constructed or repaired. | Fiscal 2023/2024 (Completed) | 2025-02-22 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
38 | MOWT/DD/NIPDEC/8/14/35 | 72152707 | Construction of Reinforced Concrete Wall along Guapo River/ Guapo River Road, at Guapo Village, Point Fortin | Construction of Reinforced Concrete Wall 4m (H) x 170m (L) (With Piles) | Fiscal 2023/2024 (Ongoing) | 2025-12-01 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
39 | MOWT/DD/NIPDEC/8/14/36 | 72152707 | Construction of a Reinforced Concrete Wall along the Arima River off Trisha Avenue, Mandalay Gardens, Arima. | Construction of a 185 m long x 4.7m high Reinforced Concrete Wall in total. Which consists of Forty Five (45) meters of piled retaining wall inclusive of two 3m wing walls upstream and downstream on the left bank and the other One Hundred and Forty 140 m long x 4.7m high Reinforced Concrete Wall inclusive of wing walls upstream and downstream along with outfall drains where necessary. | Fiscal 2023/2024 (Completed) | 2025-03-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
40 | MOWT/DD/NIPDEC/8/14/37 | 72152707 | Construction of a Reinforced Concrete Wall along Maraval River, Opposite Chaconia Home Away from Home | Construction of a Reinforced Concrete Wall 4.0m (H) x 80m (L) and a Reinforced Concrete Invert Paving | Fiscal 2023/2024 (Completed) | 2025-04-12 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
41 | MOWT/DD/NIPDEC/8/14/41 | 70171800 | Clearing and Desilting of the Guaico River & Embankment from bridge on Eastern Main Road to Bridge on Foster Road, Sangre Grande. | Clearing, Desilting & Embankment Works | Fiscal 2023/2024 (Completed) | 2025-07-13 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
42 | MOWT/DD/NIPDEC/8/14/42 | 72152707 | Construction of a Reinforced Concrete Wall along the San Juan River, Saddle Road, Lower Santa Cruz | Construction of Reinforced Concrete Wall 3.6m (H) x 180m (L) | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
43 | MOWT/DD/NIPDEC/8/14/44 | 72152707 | Construction of a Reinforced Concrete Wall along Petit Valley Ravine, D/S Morne Coco Road, Petit Valley | Works will include the Construction of a R.C. Wall 4m (H) x 145m (L) | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
44 | MOWT/DD/NIPDEC/8/14/47 | 72152707 | Construction of a Reinforced Concrete Wall along Cunapo River, Eastern Main Road, Sangre Grande | Works will include the Construction of a RC Wall 150m x 4 m. | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
45 | MOWT/DD/NIPDEC/8/14/43 | 72152707 | Construction of a Reinforced Concrete Wall along Aripo River, LP#58, Carib Circular, La Platta Gardens | Works will include the Construction of RC Retaining Wall 150m (L) x 4.7m (H) | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
46 | MOWT/DD/NIPDEC/8/14/45 | 72152707 | Construction of Reinforced Concrete Wall along Mausica River in the Vicinity of the Basketball Court on Mendez Trace, Arima | Construction of Reinforced Concrete Wall 4.7m (H) x 90m (L) | Fiscal 2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
47 | MOWT/DD/NIPDEC/8/14/46 | 72152707 | Rehabilitation Works along the Arima River Downstream of the Churchill Roosevelt Highway | Construction of Reinforced Concrete Wall 4.5m (H) x 150m (L) | Fiscal 2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
48 | MOWT/DD/NIPDEC/8/14/51 | 72152707 | Construction of a Reinforced Concrete Wall along Valencia River, Eastern Main Road, Valencia | Reinforced Concrete Wall 4.7m (H) x 165m (L) Reinforced Concrete Wall 4.0m (H) x 60m (L) | Fiscal 2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
49 | MOWT/DD/NIPDEC/8/14/56 | 72141205 | Construction of a Reinforced Concrete U-Section along Lallan River, from Egypt Trace to Jerningham Railway Road, Endeavour | Construction of Reinforced Concrete Box Drain, 415m Long x 2.6m high x 3.5m wide, and two (2) RC outfall drains 20m Long x 2.6m high x 3.0m wide & 25m Long x 1.7m high x 1.2m wide | Fiscal 2024 (Awarded) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
50 | MOWT/DD/NIPDEC/8/14/58 | 72141205 | Construction of a Reinforced Concrete Wall along La Cuesa River, Alongside Northbound Ramp, Freeport Overpass | Construction of Reinforced Concrete open Box Drain, 100m Long x 3.0m high x 6.0m wide, and a RC block outfall drain 15m Long x 1.2m high x 1.5m wide | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
51 | MOWT/DD/NIPDEC/8/14/52 | 72141205 | Construction of a Reinforced Concrete U-Section along Tributary to Arouca River, Trincity Central Road, Trincity | Reinforced Concrete U- Section 5.5m (W) x 2m (H) x 460m (L) | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
52 | MOWT/DD/NIPDEC/8/14/50 | 72152707 | Rehabilitation Works along Vistabella River off San Fernando By Pass, Marabella | Works will include the Construction of R.C. Walls, 60m long x 5.6m high, 100m long x 3.65m high, and 65m long x 4.7 high | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
53 | MOWT/DD/NIPDEC/8/14/49 | 72152707 | Construction of a Reinforced Concrete Retaining Wall on Nagessar Channel, Penal Rock Road, Penal | R.C. Wall 3m (H) x 65m (L) (Right Bank) R.C. Wall 3m (H) x 35m (L) (Left Bank) | Fiscal 2024 (Completed) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
54 | MOWT/DD/NIPDEC/8/14/48 | 72152707 | Construction of a Reinforced Concrete Wall along Guaracara River, Guaracara Tabaquite Road., Williamsville | Reinforced Concrete Wall 4.7m (H) x 80m (L) | Fiscal 2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
55 | MOWT/DD/NIPDEC/8/14/55 | 72152707 | Construction of a Reinforced Concrete Wall, Off Ramdularie Lane, Southern Main Road, Cunupia | Construction of Reinforced Concrete Wall 4.5m (H) x 140m (L) | Fiscal 2023/2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
56 | MOWT/DD/NIPDEC/8/14/53 | 72152707 | Construction of a Reinforced Concrete Wall along Cap-de-Ville River, #1 Cemetary Block Road, Cap-de-Ville | Reinforced Concrete Retaining Wall - 75 m (L) x 4.7m (H) | Fiscal 2024 (Awarded) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
57 | MOWT/DD/NIPDEC/8/14/54 | 72141205 | Rehabilitation works along Ramkhalia Drain, Southern Main Road, Rousillac | Reinforced Concrete U-Section - 50 m (L) x 3.5 m (W) x 2.0 m (H) with 4.0 m wingwall Reinforced Concrete U-Section - 60 m (L) x 3.5 m (W) x 2.0 m (H) with 4.0 m wingwall | Fiscal 2024 (Awarded) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
58 | MOWT/DD/NIPDEC/8/14/59 | 70171800 | Desilting & Clearing Couva River Mouth | Desilting and Clearing of Watercourse | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
59 | MOWT/DD/NIPDEC/8/14/57 | 72141205 | Construction Of A Reinforced Concrete Wall Along San Juan River, E.P. #53 Saddle Road, San Juan | Construction of Reinforced Concrete U- Section 30.0m Long x 3.6m Wide x 2.0m, Reinforced Concrete U- Section 6.0m Long x 5.6m Wide x 2.4m High, Construction of Two (2) Reinforced Concrete Box Drain 6.0m Long x 0.6m Wide x 0.5m High 1 x 0.7m High 2. and Construction of Rip Rap. | Fiscal 2024 (Ongoing) | 2026-01-31 | 485 days(120 days for project duration & 365 days for defect liability period) | Open Bidding | FIDIC Red Book
60 | MOWT/DD/NIPDEC/8/14/58 | 72152707 | Emergency Works - Construction of RC U-Section along Trib to La Cuesa RIver at Lp#5 Cemetery Road Freeport | Construction of a Gabion Basket Wall 4m (H) x 62m (L) (Left Bank) and Gabion Basket Wall 4m (H) x 18m (L) (Right Bank). | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
61 | MOWT/DD/NIPDEC/8/14/60 | 72152707 | Emergency Works - Rehabilitation Works along Santa Cruz River, Guerra Road, Santa Cruz | Reinforced Concrete Wall 3.65m(H) x 18m(L), Reinforced Concrete Wall 3m(H) x 33m(L), Reinforced Concrete Invert Paving w/Cascade Drops 6.7m(W) x 0.3m(H) x 12m(L) and Rip Rap Invert Protection 6.7m(W) x 0.4m(H) x 3m(L). | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
62 | MOWT/DD/NIPDEC/8/14/61 | 72152707 | Emergency Works - Construction of a Reinforced Concrete Wall along Petit Valley Ravine US Morne Coco Road | Reinforced concrete invert paving and underpinning. Construction of a rubble masonry wall 2.0m high x 5.0m long. | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
63 | MOWT/DD/NIPDEC/8/14/62 | 72141205 | Emergency Works - Rehabilitation Works along Maraval River in the Vicinity of Adam's Bagels | Construction of Reinforced Concrete U- Section 65.0m Long x 3.6m Wide x 3.0m High, Reinforced Concrete Box Drain 15.0m Long x 1.2m High x 1.5m Wide. Reconstruction of Reinforced Concrete Invert 4.0m Wide x 15.0m Long. | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
64 | MOWT/DD/NIPDEC/8/14/64 | 72152707 | Emergency Works - Rehab Works to the Santa Anna Ravine off Elizabeth Parkway St Joseph | Construction of a reinforced concrete pile wall 4.7m high x 65.0m long inclusive of 3.0m wingwall upstream and downstream, reinforced concrete pile wall 3.0m high x 20.0m long inclusive of 3.0m wingwall upstream and downstream. Construction of reinforced concrete box drain 0.5m wide x 0.6m high x 6.0m long | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
65 | MOWT/DD/NIPDEC/8/14/66 | 72152707 | Emergency Works - RC Pile Walls on Rio Negro River at #225 Siparia Old Road Fyzabad | Construction of reinforced concrete wall 1.6m H x 25.0m L and 1.6m H x 20.0m L | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
66 | MOWT/DD/NIPDEC/8/14/67 | 72141205 | Rehabilitation Works on Tributary to San Juan River | Construction of a reinforced concrete invert 9.0m Wide x 65.0m Long. Construction of rubble masonry wall 3.1m high x 16m long | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
67 | MOWT/DD/NIPDEC/8/14/68 | 72152707 | Rehabilitation Works Along Malik River US EMR CRH Link Road Morvant | construction of 4 gabion walls 5m (H) x 34m (L), 5m (H) x 15m (L), 1m (H) x 40m (L) and 6m (H) x 70m (L). Construction of Reno Mattress Erosion Protection 12m (W) x 0.3m (H) x 6m (L). Construction of Three (3) Cross Walls 16m (L) | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
68 | MOWT/DD/NIPDEC/8/14/63 | 70171800 | Rehabilitation Works along St. Joseph River, Narine Trace, Curepe | Pre, interim and post desilting surveys of the project area and approved offshore dump site. Desilting of the river and its mouth as determined from pre-survey and proposed cut areas.Removal and disposal of non-biodegradable material to an approved dump site. | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
69 | MOWT/DD/NIPDEC/8/14/69 | 70171800 | FW: Emergency Works - Clearing and Desilting of the Confluences of the Guayabal, St. Joseph and the San Juan Rivers and the Caroni River Between Locations | Clearing and Desilting | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
70 | MOWT/DD/NIPDEC/8/14/70 | 72141205 | Rehabilitation Works along Champs Fleur Main Drain | Construction of a reinforced concrete U-Section 4.0m Wide x 3.0m High x 50m long and reinforced concrete invert 50m long x 4.0m wide x 0.3m thick. | Fiscal 2024 (Procuring) | 2026-02-25 | 485 days(120 days for project duration & 365 days for defect liability period) | Selective Bidding | FIDIC Red Book
PSIP /CF/IDF
1 | 43/09/003/11A/001 | 70171800 | Caroni River Rehabilitation and Improvement Works Project - Phase II – Package A | Caroni River Rehabilitation and Improvement Works Project - Phase II - Construction Works at New Street | Awarded - 6/07/2023 | 2024-12-31 | 1 year | Open Tendering through internal procurement unit | FIDIC Red Book
2 | 43/09/003/11A/003 | 70171803 | MARIE DULAY AND GUARACARA RIVER FLOOD REDUCTION WORKS FOURTH STREET, HUNGER MARCH AND GUARACARA RIVER | Flood Reduction Works at Marie Dulay and Guaracara River - Construction and Rehabilitation Works to prevent erosion and flooding and health hazards in the Gasparillo area | Awarded - 7/11/2023 | 2025-07-31 | 18 Months | Open Tendering through procurement agency (NIDCO) | FIDIC Red Book
3 | 43/09/003/11A/003 | 70171700 | Irrigation & Drainage Structures in Caroni Irrigation Area (Phase III) – Bamboo #1: Mobile Pumps | Purchase of three (3) mobile pumps | Awarded - 27/09/2023 | 2024-10-31 | 4 Months | Open Tendering through internal procurement unit | N/A
4 | 701/43/001/11A/ 003 701/43/003/11A/ 011 | 72141205 | Structural works | The execution of Structural Measures inclusive of works in the following areas: Caroni, North Oropouche and South Oropouche. These projects were designed in Component 2 of the Technical Grant from CAF. Also the land acquisition component of this programme would be initiated. This project will be undertaken utilizing funds from the US $40 Mn. CAF Loan. Funding will be used for the execution of Non-Structural Measures, inclusive of Drainage Feasibility Studies and Development of Plans.Funds will also be used for the creation of the Project Execution Unit which was delayed due to the finalization of the Programme Operations Manual. | 2nd Quarter Fiscal 2024 (pending Hiring of PEU) |  | 3 years | Open Tendering through procurement agency or internal procurement unit | FIDIC Suite
1 | 43/09/003/11/A/009/01 | 70171700 | Upgrade of Tulsa Trace Pump House and Gates | Upgrade of Tulsa Trace Pump House and Gates - Installation of one (1) new pump and two (2) new sluice gates | Ongoing Award - Aug 2019 Status - Period of Maintenance ongoing | Completion date - 24/01/2023 | 6 Years | Open Tender through CTB | FIDIC Red Book
2 | 43/09/003/11/A/009/07 | 70171700 | Upgrade of Gate Structures, at Trinidad Point Gate Site, Penal | Upgrade of Gate Structures, at Trinidad Point Gate Site , Penal - Refurbish of the existing fourteen (14) sluice gate system | Ongoing Award - Sep 2019 Status - Period of Maintenance ongoing | Completion date - 20/01/2022 | 5 Years | Open Tender through procurement agency (NIDCO) | FIDIC Green Book
3 | 43/09/003/11/A/009/04 | 70171700 | Reconstruction of Sadhoo Trace Pump House | Reconstruction of Sadhoo Trace Pump House - Installation of one (1) pump | Ongoing Award - Sep 2019 Status - 90% To enter period of Maintenance | 2025-01-24 | 6 Years | Open Tender through CTB | FIDIC Red Book
4 | 43/09/003/11/A/009/03 | 70171700 | Upgrade of Gate Structures in the St. Augustine Area, Trantrill Road | Upgrade of Gate Structures in the St, Augustine Area, Trantrill Road - Refurbish of three (3) sluice gate system and installation of (2) new sluice gates | Ongoing Award - May 2020 Status - 40%, | N/A | N/A | Open Tender through PSTC | FIDIC Green Book
5 | 43/09/003/11/A/009/02 | 70171700 | Upgrade of Bamboo No.2 Pump House and Gate | Upgrade of Bamboo No.2 Pump House and Gates | Ongoing Award - Mar 2022 Status - 42%, To enter period of Maintenance | 2025-01-30 | 3 Years | Open Tender through procurement agency (NIDCO) | FIDIC Green Book
6 | 43/09/003/11/A/009/05 | 70171700 | Upgrade of Bamboo No.1 Storm Water Pump Station | Upgrade of Bamboo No.1 Pump House - Installation of one (1) new pump | Tendered Awarded - 19 October 2023 Status - 30% | 2026-01-30 | 3 Years | Open Tender through procurement agency (NIDCO) | FIDIC Red Book
7 | 43/09/003/11/A/009/08 | 70171700 | Upgrade of Gate Structures in the St. Helena Area | Upgrade of Gate Structures in the St. Helena Area - Installation of one (1) new flap gate structure | 2025-01-30 | 2027-01-30 | 2 Years | Open Tendering through procurement agency or internal procurement unit | FIDIC Red Book
8 | 43/09/003/11/A/009/10 | 70171700 | Upgrade of Sea Lots Pump House and Gate structures | Upgrade of Sea Lots Pump House and Gate structures - Installation of one (1) new pump and one (1) new flap gate | 2025-01-30 | 2028-01-30 | 3 Years | Open Tendering through procurement agency or internal procurement unit | FIDIC Red Book
9 | 43/09/003/11/A/009/11 | 70171700 | Construction of Moruga Pump House and Installation of Gate | Construction of Moruga Pump House and Installation of Gate - Installation of one (1) new pump and one (1) new sluice gate | 2025-04-28 | 2028-04-28 | 3 Years | Open Tendering through procurement agency or internal procurement unit | FIDIC Red Book
10 | 43/09/003/11/A/009/12 | 70171700 | Reconstruction of Williams Street Pump House | Reconstruction of Williams Street Pump House - Installation of two (2) new gates, construction of sump. | 2024-11-30 | 2026-12-31 | 2 Years | Open Tendering through procurement agency or internal procurement unit | FIDIC Red Book

## General Admini (GA)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
General Administration G.A. ( Accounts, I.T., Facilities Management, Legal, H.R., Communications, Transport Board, CTO, Internal Audit, Estate police, D.P.S. & P.S. Secretariat)
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
General Administration G.A.
1 | XXXX | 25100000 | Purchase of Vehicles | New vehicles needed to replace non-operating vehicles which were used to transport, Permament Secretary, Deputy Permanent Secretary, Comptroller Administrative Services and Messengers. Fuel and Lubricants required for vehicles to function, reapairs and maintenance to service vehicles |  | 2025-01-01 | 1 yr | RFQ | Fixed Price
2 | XXXX | 80131500 | Contracted Services | Rent/Lease of Buildings |  | 2025-06-01 | Bi Annual | Sole Select | Fixed Price
3 | XXXX | 76110000 | Contracted Services | Janitorial Services, Security Services, |  | 2025-07-01 | Monthly | Sole Select | Fixed Price
4 | XXXX | 14111509 | Small /Minor Equipment and Stationery | Paper, Toners, Treasury Tags, Staplers, Pencils, Pens, Paperclips, Manila Files, Clear tape, Glue Sticks, Highlighters, Rubber Bands, Markers, Liquid paper, erasers, file jackets, pens, Post its, Calculators, standing fans, filing cabinets, Ergonomic Chairs, Staples, Desktop Computers, Paper punches, notebooks, first aid Kits |  | 2025-07-01 | Per Year | RFQ | No Contract
5 | XXXX | 56101700 | Furniture | Furniture and Furnishings for the District Offices |  | 2025-07-01 | Per Year | RFQ | No Contract
Information Technology Unit
1 | Ref# 2/7/2 | 43230000 | Renewal of Forticlient EMS Subscription | Anti-Virus software used to access the corporate network at Head Office, Maritime Services, Licensing Division and TSTT Datacentre. | 2024-10-01 | 2025-09-01 | 1 yr | Selective Tendering | Fixed Price
2 | Ref# 2/7/2 | 43230000 | Renewal of Wireless Access Points at Head Office | Upgrades to the firewall is necessary to avoid security risk to the corporate network. | 2024-10-01 | 2025-09-01 | 1 yr | Selective Tendering | No Contract
3 | Ref# 2/7/2 | 43200000 | Acquisition of 2 Forticlient 600E Firewall Redundant Power supply |  | 2024-10-01 | 2025-09-01 |  | Selective Tendering | No Contract
4 | Ref# 2/7/2 | 43200000 | Upgrade of digitisation Hyper-Converged Infrastructure at Head Office |  | 2024-10-01 | 2025-09-01 | 1 yr | Selective Tendering | No Contract
5 | Ref# 2/7/2 | 43200000 | Acquisition of Datacentre Resources for MOWT Services to the Public | Acquisition of modern ICT to enable the digitisation projects. | 2024-10-01 | 2025-09-01 | 1 yr | Selective Tendering | No Contract
6 | Ref# 2/7/2 | 81112308 | Acquisition of computer systems and hardware for | This project is aimed at transforming physical files into digital records. | 2024-10-01 | 2025-09-01 | 1 yr | Selective Tendering | No Contract
7 | Ref# 2/7/2 | 81110000 | UTURN Change Request |  | 2024-10-01 | 2025-09-01 | 1yr | Sole Tendering
8 | Ref# 2/7/2 | 81110000 | UTURN Software SLA | Preventative Maintenance - on-site support, corrective maintenance license. | 2024-06-01 | 2025-05-01 | 1yr | Sole Tendering | SLA
9 | Ref# 2/7/2 | 81110000 | Upgrade Electronic Vehicle Inspection System (EVIS) | To facilitate Examiner Renewal and Enforcement, Examiner Suspension, Proprietor Renewal Enforcement, Proprietor Suspensions, Improve Audit Reporting, Improve Dashboard, Display List of Proprietors conducting Inspections and Printable Digitally Signed Examiner and Proprietor Certificates and voiding of stickers | 2024-11-01 | 2025-11-01 | 1yr | Sole Tendering | SLA
10 | Ref# 2/2/6 | 81110000 | Online Appointment and Queue Management System |  | 2024-10-01 | 2025-09-01 | 1yr | Sole Tendering | SLA
11 | Ref# 2/2/6 | 81110000 | Online Provisional Permit System (OPPS) | To provide Online Appointment System, Form redirect, OPPS Reviewer Unlock option, OPPS Approval screen, OPPS Archival feature and allow for OAS Validation ID settings for the Licensing Division | 2024-10-01 | 2025-09-01 | 1yr | Sole Tendering | SLA
12 | Ref# 3/1/2 | 81110000 | Vehicle Transfer |  | 2024-10-01 | 2025-09-01 | 1yr |  | SLA
13 | Ref# 3/1/2 | 81110000 | Enterprise Content Document Management System |  | 2024-10-01 | 2025-09-01 | 1yr | Sole Tendering | SLA/Upgrade
14 | Ref# 2/7/2 | 81110000 | Network Equipment |  | 2024-10-01 | 2025-09-01 | 1yr | Selective Tendering | No contract
15 | Ref# 2/2/5 | 43230000 | Software Purchases |  | 2024-10-01 | 2025-09-01 | 1yr | Selective Tendering | No Contract
Facilities Management Unit
1 | 9/4/8. | 76111501 | Provision of Janitorial Services | Supply of Janitorial Services for Head Office, DAO's, Traffic Warden & Licensing |  | 2025-09-25 | 12 months | RFQ | Fixed Price
2 | 9/4/2. | 92121504 | Provision of Security Services | Supply of Security Services for Head Office & Other Ministry Buildings |  | 2025-09-25 | 12 months | RFQ | Fixed Price
3 | 9/4/13. | 72101506 | Lift Maintenance | Maintenance & Repairs of Elevators to Main Office. Specialist service company required. |  | 2025-09-25 | 12 months | RFQ | No Contract
4 | 9/4/9. |  | Technical Services - Electrical & Plumbing | Maintenance & Repairs of any electrical and plumbing works to Main Office |  | 2025-09-25 | 12 months | RFQ | No Contract
5 | 9/4/11. | 72151207 | Maintenance of Chill Water System | Works include for daily inspections of the system, quarterly servicing of Air Handler Units, semi annual servicing of Cooling Towers and annual servicing of the Chillers |  | 2025-09-25 | 12 months | Single Source | No Contract
6 | 9/4/11. | 40101601 | Head Office- HVAC System - Maintenance Works- Blower Wheel Assembly Replacement | Replacement of Blower Wheel Assemby in Air Handler Rooms (AHR). There are presently 14 Blower Wheels (1 per AHR) and these have reached there serviceable life cycle. In fiscal year 2023-2024, 1 Blower Wheel was replaced, therefore 13 more have to be replaced. This project will be phased and it is planned to complete at least 4 per year. |  | 2025-03-25 | 3 months | Single Source | No Contract
7 | 9/4/11. | 40151600 | Head Office- HVAC System - Maintenance Works- Replacement of Two (2) Compressors | There are five compressors powering Head Office's HVAC System, three of them have been replaced and the next two have reached the end of their serviceable life cycle. |  | 2025-01-01 | 2 months | Single Source | No Contract
8 | 9/4/13. | 72101506 | Head Office- Maintenance of Lifts | Caribbean Lifts Ltd have identified several parts in the various lifts that require repairing or replacing. |  | 2025-03-01 | 3 months | RFQ | No Contract
9 | 9/4/9. | 39111544 | Head Office- Supply of LED Bulbs - 4ft & 8ft | Replacement of fluorescent bulbs to LED bulbs for upliftment of office areas and to adhere to the Ministry's Green Policy. |  | 2025-01-25 | 3 months | RFQ | No Contract
10 | 9/3/4. | 72152507 | Head Office - Upgrade to 4th Floor Flooring | Replacement of existing carpeted flooring finish to Luxury Vinyl Tile and Carpet material finish. |  | 2025-04-01 | 2 months | RFQ | No Contract
11 | 9/3/4. | 72153605 | Head Office - Washroom Refurbishment | The existing partitions have started to deteriorate at the base. This project will entail replacing all existing partitions on each floor of the building. |  | 2025-04-25 | 3 months | RFQ | No Contract
12 | 9/3/4. | 31211502 | Head Office - Painting of Internal Walls & Offices | Repainting of areas in 5th Floor & 4th Floor. Only purchase of materials is required as Maintenance Division will provide the labour. |  | 2025-01-25 | 1 week | RFQ | No Contract
13 | 9/3/4. | 30161601 | Head Office - Replacement of Ceiling Tiles | Replacement of damaged ceiling tiles throughout the building. |  | 2025-02-25 | 2 months | RFQ | No Contract
14 | 9/3/15. | 46191505 | Head Office - Supply & Install of New Fire Alarm Notification System | Fire Alarm System requires extensive repair works and parts for this system has become difficult and costly to souce due to the age of the system. A modern system will be sourced to replace the existing one. |  | 2025-06-25 | 6 months | RFQ | No Contract
15 | 9/3/15. | 30130000 30160000 | Relocation of Traffic Warden Division (TWD) - Penal Base to Siparia Works Complex - Purchase of Building Materials | In an effort to reduce the rental cost of the Ministry, an area in the Siparia Works Complex Building has been allotted to the Penal Base of the TWD. The area needs to be refurbished and the materials required for the civil, plumbing and electrical works along with building finishes such as floor tiles, cupboards, faucets will be purchased with the Maintenance Division completing the works. |  | 2025-02-25 | 1 month | RFQ | No Contract
16 | 9/3/4. | 72102801 | Head Office - Building Exterior Refurbishment | Refurbishment and cleaning of the external of the MOWT's Head Office. Works include: Cleaning of the façade and all windows. Repairing all external walls where necessary and repainting of plastered walls. Replacing of all window gaskets. Repairing of leaks in metal roof. Replacement of car park fencing. |  | 2025-06-25 | 6 months | RFQ | No Contract
17 | 9/3/4. | 72153600 | Head Office - Building Interior Refurbishment | Refurbishment of internal areas of the MOWT Head Office. Works include for Repairs to gypsum ceiling Repainting of Multi-Purpose Hall |  | 2025-03-25 | 3 months | RFQ | No Contract
18 |  | 72101507 | Maintenance and Upgrade Works at District Administration Offices | Upgrade of DAO offices -Painting and the maintenance of light fixtures and the refurbishing or replacing of A/C Units as some are obsolete and no longer functional |  | 2025-08-25 | 8 months | RFQ | No Contract
19 | 9/3/4. | 46171624 | Head Office - Supply & Install of Baggage Scanner | The existing baggage scanner has been non-functional over 5 years. |  | 2025-09-25 | 3 months | RFQ | No Contract
Human Resource Department
1 | XXXX | 86132100 | Employee Assistance Programme | The Employee Assistance Program intends; -To provide accessible, professional counselling, information sensitization workshops to employees of the Ministry of Works and Transport. -To tailor interventions which are reflective of each employee or their family’s capacity to problem solve with regard to their situation. -To promote knowledge and provide education to improve both personal and organizational well-being. -To assist organizations in improving employee health in the workplace. |  | 2025-01-01 | 2025-07-01 | RFQ | Fixed Price
2 | XXXX | 80101511 | Contracted Services | PENSION AND LEAVE CONSULTING- To provide an efficient and timely pension and leave service to employees of the Ministry of Works and Transport, ensuring that calculations and submissions are in accordance with pension laws, regulations and policies of the public service. DEVELOPING AND IMPLEMENTING AN ONLINE TRAINING SYSTEM- This will enhance the Ministry’s efforts in the administration of Training and Development activities through an integrated online learning platform that will be used for training and learning resource database. |  | 2025-01-01 | 2025-07-01 | RFQ | Fixed Price
3 | XXXX | 86132100 | Training | Training Programmes, Books, Periodicals, Minor Equipment, Stationery, Grocery Supplies |  | 2025-01-01 | 2025-07-01 | RFQ | No Contract
Legal Services
1 | XXXX | 80120000 | Fees | Payment of fees, Consultancy fees and other relevant legal reference books | Payment of fees, Consultancy fees and other relevant legal reference books | 2025-01-01 | 2025-07-01 | RFQ | Fixed Price

## Highways
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Highways Division
No. | Project Number | UNSPEC Code | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | 02/002/08 | 80131500 | Rent/Lease Office Accomodation and Storage | Rental of Office Space | 2023-11-01 | 2024-01-01 | 90 days | Single Source | Fixed Term Contract
2 | 02/002/17 | 86100000 | Training | Training for Members of Staff | 2023-11-01 | 2024-01-01 | 90 days | Request for Quotation | Invoice
3 | 02/002/43 | 92120000 | Security Services | Security Services Highways Compound | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2024 | 1 year | Open Tendering | Fixed Term Contract
4 | 02/002/58 | 85000000 | Medical Expenses | Pharmaceutical Items | 2023-11-01 | 2024-01-01 | 90 days | Request for Quotation | Invoice
5 | 02/002/62 | 55101500 | Promotions | Advertisement for Highways Dept. | 2023-11-01 | 2024-01-01 | 90 days | Request for Quotation | Invoice
6 | 03/002/02 | 44000000 | Office Equipment | Photocopying Machine, Laptops etc | 2023-10-01 | 2023-11-01 | 30 days | Request for Quotation | Invoice
1 | 1/2024 | 14111507 | Supply and Delivery of Copy Paper | Supply and Delivery of A4, Letter Size, Legal Size and Ledger Paper | 2023-10-23 | 2020-09-01 | 120 days | Request for Quotations | Invoice
2 | 2/2024 | 44120000 | Supply and Delivery of Ink/Toners | Ink/Toner for use in (8) District Offices | 2023-10-23 | 2024-02-20 | 120 days | Request for Quotations | Invoice
3 | 3/2024 | 44120000 | Supply and Delivery of Other Stationery | Supply and Delivery of Notebooks, Envelopes, File Folders, Steno Pads, Paper Clips, Staple Machines, Staples, Glue, Scissors, Paper Punch, Pencils, Pens, Carbon Paper, Correction Pens, Post It, Treasury Tags, Rulers, Bristol Board, Mouse Pads, Erasers, Self Inking Stamps. | 2023-10-23 | 2024-02-20 | 120 days | Request for Quotations | Invoice
4 | 5/2024 | 80111700 | Provisions for Interviews | 12 Occasions per year | 2023-10-23 | #REF! | 120 days | Not applicable | Not applicable
5 | 6/2024 | 56000000 | Supply and Deliver of Furniture and Furnishings |  | 2023-10-23 | #REF! | 120 days | Request for Quotations | Invoice
1 | 02/002/09 | 72141107 | Bridge on CRH over San Juan River, immediately West of East Bound to South Bound Overpass | Desilting/Debris Removal Works Average Area under Bridge - 72m x 26m, desilting 100m US and 100m DS of bridge | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
2 | 02/002/09 | 72141205 | Blackman River Crossing at CRH, immediately east of the Curepe Interchange | Desilting work, culvert cleaning and removal of debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
3 | 02/002/09 | 72141205 | Crossing at CRH in the vicinity of Savannah Drive | Desilting work along channel and culvert cleaning works | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
4 | 02/002/09 | 72141205 | Churchill Roosevelt Highway, westbound (from Aranguez Overpass Entrance to Advance Commercial Equipment Ltd) | Roadside drain cleaning work 0.75lin. m., with debris removal | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 24 days | Limited Bidding | Fixed Term Contract
5 | 02/002/09 | 72141107 | Bridges over the Caroni River: along the Uriah Butler Highway, along Southern Main Road, along St. Helena Bypass Road | Vegetation control and roadside drain cleaning work, with debris removal | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 30 days | Limited Bidding | Fixed Term Contract
6 | 02/002/09 | 72141107 | B 1/2 Valencia Road, Toco | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Limited Bidding | Fixed Term Contract
7 | 02/002/09 | 72141107 | B 1/40 Toco Road, Toco | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Limited Bidding | Fixed Term Contract
8 | 02/002/09 | 72141205 | Churchill Roosevelt Highway (eastbound from Mausica to O'Meara) | Clean and regrade 2km of earthern drain, as well as remove vegetation and debris, and cleaning of road verge. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Limited Bidding | Fixed Term Contract
9 | 02/002/09 | 72141205 | Churchill Roosevelt Highway, Eastbound from the University of the West Indies to Pasea Extension) | Clean and regrade 1km of earthern drain, as well as remove vegetation and debris, and cleaning of road verge. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 22 days | Limited Bidding | Fixed Term Contract
10 | 02/002/09 | 72141205 | Intersection of Audrey Jeffers Highway and Western Main Road, in the vicinity of Cocorite Fishing Facility | Cleaning and desilting of roadside drain and Culvert Crossing. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 12 days | Limited Bidding | Fixed Term Contract
11 | 02/002/09 | 72141205 | Priority Bus Route, eastbound from Ultimate Car Care to Republic Bank, St. Augustine. | Clearing and Removal of vegetation and debris along the box drain. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 20 days | Limited Bidding | Fixed Term Contract
12 | 02/002/09 | 72141107 | B 2/20 Churchill Roosevelt Highway, Wallerfield | Desilting of the underside of bridge, with vegetation control and debris removal. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 24 days | Limited Bidding | Fixed Term Contract
13 | 02/002/09 | 72141205 | Antigua Road, Wallerfield | Grass cutting along road verges, northbound and southbound, approximately 1.5km long. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 20 days | Limited Bidding | Fixed Term Contract
14 | 02/002/09 | 72141205 | Intersection of Eastern Main Road and Priority Bus Route, in Success / Laventille Composite Secondary School. | Roadside drain cleaning work, with the cleaning of two (2) underground crossing and desilting work. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
15 | 02/002/09 | 72141205 | Uriah Butler Highway, southbound & northbound, from Chaguanas Flyover to Endeavour Connector Road. | Clean and regrade drain, as well as remove vegetation and debris, approximately 1.5km long. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 20 days | Limited Bidding | Fixed Term Contract
16 | 02/002/09 | 72141205 | Solomon Hochoy Highway, southbound in the vicinity of Brentwood Mall, Chaguanas and northbound from Chase Village Walkover to Mid Center Mall. | Clean and regrade drain, as well as cleaning of cylinder crossing, inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
17 | 02/002/09 | 72141205 | Southern Main Road, Aripero 66.5km (in the vicinity of Davey's Radiator Works) | Cleaning of underground double cylinder crossing (6.5m long x 0.60m diameter bore), inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 10 days | Limited Bidding | Fixed Term Contract
18 | 02/002/09 | 72141205 | Uriah Butler Highway 9.40 to 9.50 km Bovell Channel, Munroe Road | Clean drain between Ramlal Trace ext. to Warren Road. Clean inlet, median and outfall of Bovell channel, to remove vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
19 | 02/002/09 | 72141205 | Solomon Hochoy Highway, B 1/4 Chase Village Flyover, 3.55km | Cleaning of two (2) cylinder crossings, with drain cleaning (500m long), inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
20 | 02/002/09 | 72141205 | Solomon Hochoy Highway, Preysal Flyover (northbound & southbound) | Culvert and catchpit cleaning, with drain cleaning, inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
21 | 02/002/09 | 72141205 | Solomon Hochoy Highway between the Freeport Overpass (21.7km) and the Claxton Bay Overpass (32.5km) | Clearing and Removal of vegetation and debris along the median. Verge edging and grass cutting around the cable barriers (total distance of 21.6km) | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
22 | 02/002/09 | 72141205 | Uriah Butler Highway, northbound & southbound shoulders, from Caroni Flyover to Caroni River Bridge. | Clearing and Removal of vegetation and debris along the median. Verge edging and grass cutting around the cable barriers (total distance of 2km) | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 25 days | Limited Bidding | Fixed Term Contract
23 | 02/002/09 | 72141205 | Solomon Hochoy Highway, Harmony Hall, northbound and southbound and along Gasparillo Bypass Road to T&TEC. | Cleaning and regrading of 1km long earthen drain, inclusive of the removal of all vegetation and debris Desilting of 1m x 1m Box Culvert under highway, and 0.6m x 0.6m Crossing under Gasparillo Bypass Road, as well as catchpits. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 18 days | Limited Bidding | Fixed Term Contract
24 | 02/002/09 |  | BP Compound, Galeota to Victoria East District Office, Matilda, Princes Town | Collection and transportation of Reinforcing Steel from BP compound to MOWT office, Matilda. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
25 | 02/002/09 | 72141205 | Uriah Butler Highway, in the vicinity of John Peter Road. | Desilting of underground cylinder crossing, inclusive of the removal of all vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
26 | 02/002/09 | 72141205 | St. Croix Road, Lengua | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
27 | 02/002/09 | 72141205 | Rivulet Road, Couva | Grass cutting along road verges, westbound, approximately 5.5km long. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
28 | 02/002/09 | 72141205 | Southern Main Road - from Chandernagore Road, Chaguanas to Mc Bean Junction, Couva | Grass cutting along road verges, northbound and southbound, approximately 6km long. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
30 | 02/002/09 | 72141205 | B 1/8 Penal Rock Road, Penal | Desilting work along channel, as well as cleaning of the underside of the bridge, inclusive of the removal of vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
31 | 02/002/09 | 72141205 | Southern Main Road 83.550km Guapo Government School and Southern Main Road 83.70km Guapo Community Centre | Desilting of underground cylinder crossing, inclusive of the removal of all vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
32 | 02/002/09 | 72141205 | Southern Main Road 66.5km Vicinity of Boodoos Air conditioning, Southern Main Road 74.9km Vicinity of M.P's Office and Southern Main Road 74.7km Vicinity of Jackie's Main Road La Brea | Desilting of underground cylinder crossing, and covered box drain, inclusive of the removal of all vegetation and debris. | N/A, approval is being sought | 2nd Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
33 | 02/002/09 | 72141205 | Rental of mechanical equipment | excavator, backhoe, hiab, skid steer, gully sucker | N/A, approval is being sought | 4th Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
34 | 02/002/09 | 72141205 | Rental of mechanical equipment | dump truck, crew cab truck | N/A, approval is being sought | 4th Quarter of Fiscal 2024 | 15 days | Limited Bidding | Fixed Term Contract
1 | 02/002/28 | 72141107 | Remedial works to B 1/26 Churchill Roosevelt Highway W/B, Arima | Construction of R.C. Retaining Wall, Channel Lining works and Road restoration works. | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
2 | 02/002/28 | 72141107 | Scour Protection Works at B 1/16 Priority Bus Route (PBR), Macoya | Channel Lining works | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
3 | 02/002/28 | 81101500 | Conditional and Performance Based Assessment and Recommendations for Repair Methods for O 1/1 Western Main Road (St. James Overpass)” | To engage a professional engineering firm to provide engineering solutions for the structural repairs to B 1/6 Mayaro Guayaguayare Road, Mayaro. | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 30 days | Open Bidding | Fixed Term Contract
4 | 02/002/28 | 72141107 | Scour protection works at B 2/1 Corosal Road, Brasso, 0.21km mark | Construction of R.C. Retaining Wall, Channel Lining works and Road restoration works. | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
5 | 02/002/28 | 72141107 | Scour Protection works at B 2/1 Garth Road, Williamsville, 0.80km mark | Construction of R.C. Channel lining, Desilting of watercourse and Road Restoration works. | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
6 | 02/002/28 | 81101500 | Provision of Structural Repairs to B 1/6 Mayaro Guayaguayare Road, Mayaro | To engage a professional engineering firm to provide engineering solutions for the structural repairs to B 1/6 Mayaro Guayaguayare Road, Mayaro. | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 30 days | Open Bidding | Fixed Term Contract
7 | 02/002/28 | 72141107 | Rehabilitation works to B 1/1 Mausica Road, Arima | Repairs to bridge structure and Road works. | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
8 | 02/002/28 | 72141107 | Emergency Scour Protection works at B 1/38 EMR, Valencia. | Construction of R.C. Channel Lining, Desilting of the watercourse | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
9 | 02/002/28 | 72141107 | Emergency Scour Protection works at B 2/20 Cumuto Main Road, Coryal | Construction of R.C. Channel Lining, Desilting of the watercourse | 2023-09-01 | 2024-02-01 | 45 days | Open Bidding | Fixed Term Contract
10 | 02/002/28 | 72141107 | Reconstruction of B 2/1 Vega de Oropouche Road, Sangre Grande | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 2023-09-01 | 2024-04-01 | 60 days | Open Bidding | Fixed Term Contract
11 | 02/002/28 | 72141107 | Reconstruction of B 2/6 Oropouche Road, Sangre Grande | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 2023-09-01 | 2024-04-01 | 60 days | Open Bidding | Fixed Term Contract
12 | 02/002/28 | 72141000 | Handrail Replacement Programme Phase 3 | Replacement of damaged, broken or missing handrails, repainting of Headwalls and existing handrails and vegetation control. | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
13 | 02/002/28 | 72141000 | Guardrail Replacement Programme Phase 3 | Installation of new guardrails along the Highways and Main Roads | 2023-09-01 | 2024-02-01 | 30 days | Open Bidding | Fixed Term Contract
14 | 02/002/28 | 72141107 | Scour Protection works at B 1/9 Saddle Road, Santa Cruz. | Construction of R.C. Channel Lining, Desilting of the watercourse | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | Fixed Term Contract
15 | 02/002/28 | 72141107 | Scour Protection works at B 1/26 Churchill Roosevelt Highway, E/B | Construction of R.C. Channel Lining, Desilting of the watercourse | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | Fixed Term Contract
16 | 02/002/28 | 72141107 | Repairs to B 1/1 Chin Chin Road and B1/13 SMR, Cunupia | Repairs to Bridge Handrails, Road Restoration Works and Bridge rehabilitation works | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | Fixed Term Contract
17 | 02/002/28 | 72141107 | Repairs to B 2/5 Cottage Road, Lengua | Conversion of Timber deck to R.C. Deck Slab, Desilting of watercourse, Construction of R.C. Channel Lining and Road Rehabilitation | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | Fixed Term Contract
18 | 02/002/28 | 72141107 | Repairs to B 1/3 Lengua Road, Princes Town | Conversion of Timber deck to R.C. Deck Slab, Desilting of watercourse, Construction of R.C. Channel Lining and Road Rehabilitation | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | Fixed Term Contract
19 | 02/002/28 | 72141107 | Scour Protection works at B 1/2 Hermitage Road, Hermitage. | Construction of R.C. Channel Lining, Desilting of the watercourse | 2023-11-01 | 2024-06-01 | 30 days | Open Bidding | Fixed Term Contract
20 | 02/002/28 | 72141107 | Widening of B 2/4 Penal Rock Road, Penal | Widening of Bridge and Road restoration works | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
21 | 02/002/28 | 72141107 | Reconstruction of B 3/13 Penal Rock Road, Siparia | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
22 | 02/002/28 | 72141107 | Reconstruction of B 2/8 San Francique Road, La Brea | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
23 | 02/002/28 | 72141107 | Widening of 2/2 Sisters Road | Widening of Bridge and Road restoration works | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
24 | 02/002/28 | 72141107 | Widening of B 1/4 Sisters Road | Widening of Bridge and Road restoration works | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
25 | 02/002/28 | 72141107 | Reconstruction of B 1/1 Robertson Road | Construction of Box Culvert, Desilting of the watercourse, Road Rehabilitation and construction of temporary diversion route. | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
26 | 02/002/28 | 72141000 | Handrails along Penal Rock Road | Repairs to Handrails | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
27 | 02/002/28 | 77111603 | Repairs to B 1/67 Southern Main Road rousillac | Slope stabilization works | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | TBD | Open Bidding | Fixed Term Contract
1 | 02/002/28 | 72141000 | Sectional Milling and Paving along Morne Coco Road, 5km - 10km mark | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
2 | 02/002/28 | 72141000 | Sectional Milling and Paving along Saddle Road, 12km to 19km marks | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
3 | 02/002/28 | 72141000 | Sectional Milling and Paving Works at Beetham Highway, East and Westbound, 0.0km - 4.7km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
4 | 02/002/28 | 72141000 | Sectional Milling and Paving Works at Churchill Rooservelt Highway, East and Westbound, 4.7km - 11.4km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
5 | 02/002/28 | 72141000 | Sectional Milling and Paving Works at Eastern Main Road 1.0km - 11.4km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
6 | 02/002/28 | 72141000 | Sectional Milling and Paving Works at Uriah Butler Highway, North and Southbound 0.0km - 3.8km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
7 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Churchill Roosevelt Highway, 11.8km to 34.8km, Eastbound | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
8 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Churchill Roosevelt Highway, 34.8km to 11.8km, Westbound | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
9 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Trincity Central Road | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
10 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Eastern Main Road, 11.4km to 34.8km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
11 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Lopinot Road, 2.9km to 4.6km marks | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
12 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Cumuto Road, 7.6km to 9.3km marks PHASE 2 | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
13 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Tamana Road, 4.7km to 6.1km marks | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
14 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Cumuto Tumpuna Road, 1.4km to 5.3km marks | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
15 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along Guaico Tamana Road 7km - 15km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
16 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along Plum Mitan Road 3.5km - 12km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
17 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Caigual Road 0km - 4km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
18 | 02/002/28 | 72141000 | Sectional Road Rehabiliation along Paria Main Road 51km - 72km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
19 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Cunapo Southern Road, 9.2km to 21kmkm mark | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
20 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Grand Fond Road 0km to 6km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
21 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along Waterloo Road 0.0km - 13.0km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
22 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along Carli Bay Road 0.0km - 2.1km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
23 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along Calcutta #2 Road 0.0 - 5.3km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
24 | 02/002/28 | 72141000 | Sectional Milling and Paving along Freeport Todds Road, 3.5km to 5km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
25 | 02/002/28 | 72141000 | Sectional Milling and Paving along Southern Main Road, 26.1km to 28.1km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
27 | 02/002/28 | 72141000 | Sectional Milling and Paving along Caparo valley Brasso Road, 1.9km to 18.8km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
28 | 02/002/28 | 72141000 | Sectional Milling and Paving along Sir Solomon Hochoy, Northbound, 43.5km - 32km mark | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
29 | 02/002/28 | 72141000 | Sectional Milling and Paving Works along Gasparillo Bye Pass Road, 0.0km to 1.6km marks | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
30 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Hermitage Road, 0.0km - 4.8km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
31 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Southern Main Road, 42km - 47.0 km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
32 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along Naparima Mayaro Road 5.6km - 10.0km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
33 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along M2 Ring Road Road 7.5km - 15.5km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
34 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along M1 Tasker Road 0.0km - 4.8km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
35 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along Piparo Road 7km - 8.4km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
36 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Naparima Mayaro Road, 14.5km - 28km marks | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
37 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Buen Intento Road 2.8km - 6.5 km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
38 | 02/002/28 | 72141000 | Sectional Milling and Paving along M1 Tasker Road 1.9km - 2.8km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
39 | 02/002/28 | 72141000 | Sectional Milling and Paving along Matilda Road 0.0km - 0.9km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
40 | 02/002/28 | 72141000 | Sectional Road Rehabiliation along St. Julien Road 2.4km - 3.4km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
41 | 02/002/28 | 72141000 | Sectional Road Rehabiliation along Naggee Road 0.5km - 1.5km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
42 | 02/002/28 | 72141000 | Sectional Road Rehabilitation along Mayaro Guayaguayare 18.0km - 21.0 km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
43 | 02/002/28 | 72141000 | Sectional Milling and Paving along Mayaro Guayaguayare 0.0 km - 4.0 km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
44 | 02/002/28 | 72141000 | Sectional Milling and Paving along San Pedro Road, 0.0 km - 2.5km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
45 | 02/002/28 | 72141000 | Sectional Milling and Paving along Biche Ortoire Road, 0.0km to 3km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
46 | 02/002/28 | 72141000 | Road Rehabilitation and Paving works along Southern Main Road 74.0km to 77.5km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
47 | 02/002/28 | 72141000 | Milling, Strenghtening and Paving along Southern Main Road 65.9km to 72km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
48 | 02/002/28 | 72141000 | Sectional Road Rehabilitation and Paving works along Southern Main Road 85.6km to 91.7km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
49 | 02/002/28 | 72141000 | Milling, Strenghtening and Paving works along Mon Desir Delhi Road 0.0km to 2.44km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
50 | 02/002/28 | 72141000 | Sectional Strengthening, Milling and Paving along M2 Ring Road 5km to 7km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
51 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along SS Erin Road 10.5km to 13.6km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
52 | 02/002/28 | 72141000 | Sectional Road Rehabilitation works along SS Erin Road 15.5km to 19.0km | Sectional Road Rehabilitation Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 21 days | Limited Bidding | Fixed Term Contract
53 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Saddle Road, 9.5km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
54 | 02/002/28 | 72103300 | Critical Repairs to Landslip at North Coast Road, 10.5km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
56 | 02/002/28 | 72103300 | Critical Slope Stabilization works along Blanchisseuse Road, 6km- 6.1km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
57 | 02/002/28 | 72103300 | Critical Repairs to Landslip along Cumuto Road, 15.7km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
58 | 02/002/28 | 72103300 | Emergency Repairs to Landslip at Cumaca Road, 1.5km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
59 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Guaico Tamana Road, 7.6km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
64 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Fishing Pond Road, 1.6km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
65 | 02/002/28 | 72103300 | Critical Repairs to Landslip along North Manzanilla Road, 0.5km | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
69 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Cipero Road, 9.8km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
70 | 02/002/28 | 72103300 | Critical Repairs to Landslips along Corosal Road, 3km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
71 | 02/002/28 | 72103300 | Emergency Repairs to Landslip along Papourie Road, 13km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
72 | 02/002/28 | 72103300 | Critical Repairs to Landslip along Sir Solomon Hochoy Highway, 34.5km mark, Southbound | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
73 | 02/002/28 | 72103300 | Critical Repair to Landslip at St. Croix Road, 6.7km mark in vicinity of LP#29 | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
74 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Garth Road, 4.5 km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
75 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Garth Road, 3.3km mark in vicinity of LP #119 | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
76 | 02/002/28 | 72103300 | Repair to landslips and restoration of roadway along St Julien Road, 1km to 4km marks | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
78 | 02/002/28 | 72103300 | Repairs to Landslips along Jaipaulsingh Road, 0.3 km and 0.8 km marks | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
79 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Whatts Road, 3.5km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
80 | 02/002/28 | 72103300 | Repair to Landslips at Torrib Tabaquite, 2.0km and 2.2km marks | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
81 | 02/002/28 | 72103300 | Repairs to Landslip at Dades Road, 2.5km and reconstruction of crossing at 2.7km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
82 | 02/002/28 | 72103300 | Critical Slope Stabilization Works on Tabaquite Rio Claro Road 49.1km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
83 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Cunapo Southern Road, 28.5km | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
84 | 02/002/28 | 72103300 | Emergency Repairs to Landslip along Southern Main Road, 96.3km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Open Tendering | Fixed Term Contract
85 | 02/002/28 | 72103300 | Emergency Repairs to Landslip along Southern Main Road, 106.9km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
86 | 02/002/28 | 72103300 | Emergency Repairs to Landslip along Southern Main Road, 95.6km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
87 | 02/002/28 | 72103300 | Emergency Repairs to Landslip at Penal Rock Road, 13.5km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
88 | 02/002/28 | 72103300 | Critical Repairs to Landslip at S.S. Erin Road, 12.5km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
89 | 02/002/28 | 72103300 | Critical Slope Stabilization Works along Fyzabad Branch Road, 3.5km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
90 | 02/002/28 | 72103300 | Critical geotechnical Investigation for Landslip at Realize Road, 1.8km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
91 | 02/002/28 | 72103300 | Critical Slope Stabilization works along Paria Main Road, 52km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
92 | 02/002/28 | 72103300 | Critical Repairs to Landslip at Brasso Caparo Station Road, 4km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
93 | 02/002/28 | 72103300 | Repairs to Landslip along Penal Rock Road, 22.2 km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
94 | 02/002/28 | 72103300 | Repairs to Landslip along Realize road, 1.6km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
96 | 02/002/28 | 72103300 | Repairs to Landslip at Martiste Road, 0.3km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
97 | 02/002/28 | 72103300 | Repairs to Landslip at Siparia Road, 0.1km mark | Slope Stabilization Works | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
1 | XXXX | 72141000 | Sectional Road Rehabilitation along Eastern Main Road, Malick to Curepe | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
2 | XXXX | 72141000 | Sectional Road Rehabilitation along Morne Coco Road, 5km to 10km mark | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
3 | XXXX | 72141000 | Sectional Road Rehabilitation along Saddle Road, 12km to 19km mark | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
4 | XXXX | 72141000 | Sectional Road Rehabilitation along Aripo Road, Phase 1 | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
5 | XXXX | 72141000 | Sectional Road Rehabilitation along Eastern Main Road, Curepe to Tunapuna | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
6 | XXXX | 72141000 | Sectional Road Rehabilitation along Cumuto Road, Phase 2 | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
7 | XXXX | 72141000 | Sectional Road Rehabilitation along Tamana Road, Phase 1 | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
8 | XXXX | 72141000 | Sectional Road Rehabilitation and Safety Works along Caroni North Bank Road, 0km to 3.2km marks | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
10 | XXXX | 72141000 | Sectional Road Rehabilitation along Plum Mitan Road 3.5km - 12km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
11 | XXXX | 72141000 | Sectional Road Rehabilitation along Caigual Road Phase 2 | Road Rehabilitation | Mar-24 | N/A | 21 days | Limited Bidding | Fixed Term
12 | XXXX | 72141000 | Sectional Road Rehabiliation along Paria Main Road 51km - 72km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
13 | XXXX | 72141000 | Sectional Road Rehabilitation along Cunapo Southern Road, 9.2km to 21km mark | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
16 | XXXX | 72141000 | Sectional Road Rehabilitation along Tabaquite Rio Claro Road, 35.5km to 37.0km marks | Road Rehabilitation | 2024-02-01 | N/A | 21 days | Limited Bidding | Fixed Term
17 | XXXX | 72141000 | Sectional Road Rehabilitation along Naparima Mayaro Road, 31.0km - 40.0km marks | Road Rehabilitation | 2024-02-01 | N/A | 21 days | Limited Bidding | Fixed Term
18 | XXXX | 72141000 | Sectional Road Rehabilitation along Naparima Mayaro Road, 52.0km - 59.0km marks | Road Rehabilitation | 2024-02-01 | N/A | 21 days | Limited Bidding | Fixed Term
19 | XXXX | 72141000 | Sectional Road Rehabilitation and Safety Works along Southern Main Road, Licensing Office Caroni | Road Rehabilitation | 2024-04-01 | N/A | 21 days | Limited Bidding | Fixed Term
22 | XXXX | 72141000 | Sectional Road Rehabilitation along Southern Main Road, 33.5km to 42km | Road Rehabilitation | 2024-02-01 | N/A | 21 days | Limited Bidding | Fixed Term
25 | XXXX | 72141000 | Sectional Road Rehabilitation along Gasparillo Bye Pass Road, 0.0km to 1.6km marks | Road Rehabilitation | 2024-02-01 | N/A | 21 days | Limited Bidding | Fixed Term
26 | XXXX | 72141000 | Sectional Road Rehabilitation along Hermitage Road, Phase 1 | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
27 | XXXX | 72141000 | Sectional Road Rehabilitation along Southern Main Road, 42km - 47.0 km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
28 | XXXX | 72141000 | Sectional Road Rehabilitation works along Naparima Mayaro Road 5.6km - 10.0km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
32 | XXXX | 72141000 | Sectional Road Rehabilitation along Hindustan Road | Road Rehabilitation | 2024-02-01 | N/A | 21 days | Limited Bidding | Fixed Term
34 | XXXX | 72141000 | Sectional Road Rehabilitation along Southern Main Road 65.9km to 70km mark | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
35 | XXXX | 72141000 | Sectional Road Rehabilitation along Southern Main Road 72km to 92km mark | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
36 | XXXX | 72141000 | Sectional Road Rehabilitation along Mon Desir Delhi Road Phase 1 | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
37 | XXXX | 72141000 | Sectional Road Rehabilitation along M2 Ring Road 5km to 7km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
38 | XXXX | 72141000 | Sectional Road Rehabilitation works along SS Erin Road Phase 1 | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
39 | XXXX | 72141107 | Replacement of Culvert Crossing and Ancillary Works at Old St Joseph Road, 2.8km mark | Drainage | 2024-02-01 | N/A | 14 days | Limited Bidding | Fixed Term
43 | XXXX | 72141107 | Drainage Upgrade along Morne Coco Road 1km mark | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
44 | XXXX | 72141107 | Drainage Upgrade Works, Audrey Jeffers Highway, 5.4km mark | Drainage | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
45 | XXXX | 72141107 | Replacement of Culvert Crossing at Cumuto Road, 18km mark | Drainage | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
46 | XXXX | 72141107 | Construction of Roadside Drainage along Aripo Road Phase 1 | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
47 | XXXX | 72141107 | Replacement of culvert crossing at Cumuto Road, 15.5km mark | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
48 | XXXX | 72141107 | Drainage Upgrade along CRH and Pasea Road South | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
49 | XXXX | 72141107 | Replacement of Culvert Crossing at Mausica Road South | Drainage | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
51 | XXXX | 72141107 | Drainage Upgrade and Desilting, Savannah Drive, CRH Network | Drainage | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
52 | XXXX | 72141107 | Drainage Upgrade and Desilting, Caroni District -Phase 2 | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
54 | XXXX | 72141107 | Drainage Upgrade and Desilting, Munroe Road -Phase 1 | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
55 | XXXX | 72141107 | Drainage Upgrade and Desilting, John Peter, Charlieville Network | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
57 | XXXX | 72141107 | Replacement of Culvert Crossing at Frederick Road 0.4km and Frederick 3rd Branch Road 0.4km | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
58 | XXXX | 72141107 | Construction of Reinforced Concrete Outfall Drain at Naparima Mayaro Road 28.2km | Drainage | 2024-03-01 | N/A | 14 days | Limited Bidding | Fixed Term
59 | XXXX | 72141107 | Reconstruction of Cylinder Crossing and Ancillary Works along Naparima Mayaro Road, 26.6km mark | Drainage | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
60 | XXXX | 72141107 | Repair of Cylindrical Crossings along Sir Solomon Hochoy Highway Phase 1 (Investigation and Construction) | Drainage | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
62 | XXXX | 72103300 | Critical Repair to Landslip at Saddle Road, 9.5km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
63 | XXXX | 72103300 | Critical Repair to Landslip along North Coast Road, 10.5km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
64 | XXXX | 72103300 | Critical Repair to Landslip along North Coast Road, 5.6km mark (Investigation and Construction) | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
65 | XXXX | 72103300 | Critical Repair to Landslip along Cumuto Road, 15.7km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
66 | XXXX | 72103300 | Critical Repair to Landslips along Blanchisseuse Road, Phase 1 | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
67 | XXXX | 72103300 | Critical Repair to Landslips along Aripo Road, Phase 2 | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
68 | XXXX | 72103300 | Critical Repair to Landslip along Paria Main Road, 63.5km mark | Slope Stabilization | 2024-03-01 | N/A | 60 days | Limited Bidding | Fixed Term
69 | XXXX | 72103300 | Critical Slope Stabilization Works along Paria Main Road, 52km mark | Slope Stabilization | 2024-03-01 | N/A | 60 days | Limited Bidding | Fixed Term
70 | XXXX | 72103300 | Critical Repair to Landslips along Bonair Road, Phase 1 | Slope Stabilization | 2024-03-01 | N/A | 60 days | Limited Bidding | Fixed Term
71 | XXXX | 72103300 | Critical Repair to Landslips along Guaico Tamana Road, Phase 1 | Slope Stabilization | 2024-03-01 | N/A | 60 days | Limited Bidding | Fixed Term
72 | XXXX | 72103300 | Critical Repair to Landslips along Guaico Tamana Road, Phase 2 | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
73 | XXXX | 72103300 | Critical Repair to Landslip along Fishing Pond Road, 1.6km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
74 | XXXX | 72103300 | Critical Repair to Landslip along North Manzanilla Road, 0.5km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
76 | XXXX | 72103300 | Critical Repair to Landslips along Torrib Tabaquite Road, 2.0km and 2.2km marks | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
77 | XXXX | 72103300 | Critical Repair to Landslip along Cunapo Southern Road, 28.5km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
79 | XXXX | 72103300 | Critical Slope and Drainage Repair along Dades Road, 2.5km to 2.7km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
82 | XXXX | 72103300 | Critical Repair to Landslip along Papourie Road, 13km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
83 | XXXX | 72103300 | Critical Repair to Landslip along Papourie Road, Trinidad Hill | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
84 | XXXX | 72103300 | Critical Slope Stabilization Works along Sir Solomon Hochoy Highway, 32.5km mark, Southbound | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
86 | XXXX | 72103300 | Critical Slope Stabilization Works along Sir Solomon Hochoy Highway, 34.5km mark, Southbound | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
87 | XXXX | 72103300 | Critical Slope Stabilization Works along Sir Solomon Hochoy Highway, 36.5km mark, Southbound | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
88 | XXXX | 72103300 | Critical Repair to Landslip at St. Croix Road, 6.7km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
89 | XXXX | 72103300 | Critical Repair to Landslips along Garth Road Phase 1 | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
90 | XXXX | 72103300 | Critical Repair to Landslip along Manahambre Road, 2km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
91 | XXXX | 72103300 | Critical Repair to Landslips along St Julien Road, Phase 2 | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
92 | XXXX | 72103300 | Critical Repair to Landslip at Naparima Mayaro Road, 31km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
93 | XXXX | 72103300 | Critical Repair to Landslip along Whatts Road, 3.5km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
94 | XXXX | 72103300 | Critical Repair to Landslip along Jaipaulsingh Road, 0.3 km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
95 | XXXX | 72103300 | Urgent Geotechnical Investigation for Landslip at Realize Road, 1.8km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
99 | XXXX | 72103300 | Critical Repair to Landslip along Penal Rock Road, 13.5km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
100 | XXXX | 72103300 | Critical Repair to Landslip along Southern Main Road, 95.6km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
101 | XXXX | 72103300 | Critical Repair to Landslip along Southern Main Road, 96.3km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
102 | XXXX | 72103300 | Critical Repair to Landslip along SS Erin Road, 24.6km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
103 | XXXX | 72103300 | Critical Repair to Landslip along Southern Main Road, 106.9km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
104 | XXXX | 72103300 | Critical Repair to Landslip along S.S. Erin Road, 12.5km mark | Slope Stabilization | 2024-05-01 | N/A | 60 days | Limited Bidding | Fixed Term
106 | XXXX | 7011503 | Cutting of Trees and Ancillary Works along Uriah Butler Highway, Champ Fleurs | Safety | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
109 | XXXX | 7011503 | Cutting of Trees and Ancillary Works along Priority Bus Route, Curepe to Tunapuna | Safety | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
110 | XXXX | 7011503 | Cutting of Trees and Ancillary Works along Uriah Butler Highway, Caroni to Chaguanas | Safety | 2024-04-01 | N/A | 14 days | Limited Bidding | Fixed Term
111 | XXXX |  | Upgrade of Emergency Response Capacity for Highways Division | Safety | 2024-05-01 | N/A | 14 days | Limited Bidding | Fixed Term
112 | XXXX |  | Production of PBR Passes | Safety | 2024-05-01 | N/A | 14 days | Limited Bidding | Fixed Term
113 | XXXX |  | Emergency Works within Various Districts | Safety | 2024-05-01 | N/A | 14 days | Limited Bidding | Fixed Term
116 | XXXX | 72141107 | Scour Protection Works at B 2/20 Cumuto Main Road, Coryal | Bridge Repair | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
118 | XXXX | 72141107 | Scour Protection Works at B 2/4 Caparo Valley Brasso Road | Bridge Repair | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
120 | XXXX | 72141107 | Critical Joint Repair along Highway Bridges, Phase 1 | Bridge Repair | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
121 | XXXX | 72141107 | Scour Protection works at B 1/3 Mon Desir Road, Rousillac | Bridge Repair | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
122 | XXXX |  | Median Protection along Uriah Butler Highway | Safety | 2024-05-01 | N/A | 14 days | Limited Bidding | Fixed Term
123 | XXXX |  | Median Protection along Sir Solomon Hochoy Highway | Safety | 2024-05-01 | N/A | 14 days | Limited Bidding | Fixed Term
124 | XXXX |  | Median Protection along Churchill Roosevelt Highway from Aranguez to Trincity | Safety | 2024-05-01 | N/A | 14 days | Limited Bidding | Fixed Term
125 | XXXX |  | Median Protection along Diego Martin Highway | Safety | 2024-05-01 | N/A | 14 days | Limited Bidding | Fixed Term
126 | XXXX | 72141000 | Sectional Road Rehabilitation Works at Beetham Highway, East and Westbound, 0.0km to 4.7km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
127 | XXXX | 72141000 | Sectional Road Rehabilitation Works at Churchill Roosevelt Highway, Eastbound, 4.7km to 11.4km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
128 | XXXX | 72141000 | Sectional Road Rehabilitation Works at Churchill Roosevelt Highway, Westbound, 11.4km to 4.7km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
129 | XXXX | 72141000 | Sectional Road Rehabilitation Works at Uriah Butler Highway, Northbound, 0.0km to 3.8km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
130 | XXXX | 72141000 | Sectional Road Rehabilitation Works at Uriah Butler Highway, Southbound 3.8km to 0km | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
131 | XXXX | 72141000 | Sectional Road Rehabilitation Works along Churchill Roosevelt Highway, 11.8km to 34.8km, Eastbound | Road Rehabilitation | 2024-04-01 | N/A | 21 days | Limited Bidding | Fixed Term
132 | XXXX | 72141000 | Sectional Road Rehabilitation Works along Churchill Roosevelt Highway, 34.8km to 11.8km, Westbound | Road Rehabilitation | 2024-04-01 | N/A | 21 days | Limited Bidding | Fixed Term
133 | XXXX | 72141000 | Sectional Road Rehabilitation along Sir Solomon Hochoy, Northbound, 43.5km - 32km mark | Road Rehabilitation | 2024-03-01 | N/A | 21 days | Limited Bidding | Fixed Term
134 | XXXX | 72103300 | Repair to Landslip along Maracas Royal Road, 3.7km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
135 | XXXX | 72103300 | Repair to Landslip along Arima Blanchisseuse Road, 13.7km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
136 | XXXX | 72103300 | Repair to Landslip along Tamana Road, 3.8km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
137 | XXXX | 72103300 | Repair to Landslip along Gajadhar Road, 4.8km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
138 | XXXX | 72103300 | Repair to Landslip along Plum Mitan Road, 3.7km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
140 | XXXX | 72103300 | Repair to Landslip along Tabaquite Brasso Road, 22.6km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
141 | XXXX | 72103300 | Repair to Landslip along Nagee Road, 1.9km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
142 | XXXX | 72103300 | Repair to Landslip along Samuel Cooper Road, 1.8km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
143 | XXXX | 72103300 | Repair to Landslip along Nagee Road, 4.1km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
144 | XXXX | 72103300 | Repair to Landslip along Mandingo Road, 2.6km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
145 | XXXX | 72103300 | Repair to Landslip along Hindustan Road, 5.2km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
146 | XXXX | 72103300 | Repair to Landslip along Dades Road, 1.4km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
147 | XXXX | 72103300 | Repair to Landslip along Southern Main Road, 91.8km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
148 | XXXX | 72103300 | Repair to Landslip along Penal Quinam Road, 0.5km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
150 | XXXX | 72103300 | Repair to Landslip along Granville Road, 3.5km to 4km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
152 | XXXX | 72103300 | Repair to Landslip along Moreau Road No. 1, 9.1km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
154 | XXXX | 72103300 | Critical Repair to Landslips along Cipero Road, 9.5km and 9.8km marks | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
155 | XXXX | 72103300 | Critical Repair to Landslip along Golconda Road, 0.7km | Slope Stabilization | 2024-03-01 | N/A | 60 days | Limited Bidding | Fixed Term
156 | XXXX | 72103300 | Critical Repair to Landslip along Martiste Road, 0.3km mark | Slope Stabilization | 2024-04-01 | N/A | 60 days | Limited Bidding | Fixed Term
157 | XXXX | 72103300 | Critical Repair to Landslip along Tortuga Road, 2km mark | Slope Stabilization | 2024-02-01 | N/A | 60 days | Limited Bidding | Fixed Term
1 | 02/002/28 | 81101500 | Engineering Consultancy Services For The Construction Of Cast-In-Place Concrete Barriers At The Median Of The Churchill Roosevelt Highway 4.7km - 7.4km (In The Vicinity Of Solo To Grand Bazaar Interchange) | To construct new median permanent concrete barriers along the highway inclusive of utility relocations | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
2 | 02/002/28 | 81101500 | Topographic Survey for Median Barriers installation along Uriah Butler Highway 8km-16km ( from Guayamare River Bridge to Chaguanas Overpass) | To perform topographic surveys for defining position for new Guard Rails | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
3 | 02/002/28 | 72141500 | Geotechnical Investigation for Papourie Road, 13.0km | To perform approximately 6 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
4 | 02/002/28 | 72141500 | Geotechnical Investigation for Reform Road, 1.8km | To perform approximately 5 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
5 | 02/002/28 | 72141500 | Geotechnical Investigation for Bon Air Road 0-2km | To perform approximately 6 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
6 | 02/002/28 | 72141500 | Geotechnical Investigation for Arima Blanchisseuse Road 6.1km | To perform approximately 3 boreholes and engineering geotechnical analysis report inclusive of reccomended solution based on a slope stability analyses | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
7 | 02/002/28 | 81101500 | Construction of a Cylindrical Road Crossing along Trinicity Central Road in the vicinity of Superpharm and East Gates Mall | Construction of a Double Cylindrical Road Crossing (20m long with 600mm diameter bore each) along with associated road works. | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
8 | 02/002/28 | 81101500 | Engineering Consultancy and Traffic Studies along Uriah Butler Highway 14.5km Mark in the vicinity of Priceplaza and Endeavour Pass | Engineering analysis and traffic studies to alleviate congestion | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
9 | 02/002/28 | 81101500 | Engineering Consultancy and Traffic Studies along Sir Solomon Hochoy Highway 5.7km Mark in the vicinity of Chase Village Overpass | Engineering analysis and traffic studies to alleviate congestion | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
10 | 02/002/28 | 81101500 | Engineering Consultancy and Traffic Studies along Sir Solomon Hochoy Highway 26.0km Mark in the vicinity of Tarouba Overpass | Engineering analysis and traffic studies to alleviate congestion | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
11 | 02/002/28 | 81101500 | Engineering Consultancy and Traffic Studies along Sir Solomon Hochoy Highway 22.0km Mark in the vicinity of Gasparillo Overpass | Engineering analysis and traffic studies to alleviate congestion | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
12 | 02/002/28 | 43201400 | Procurement of Materials for Bus Route Passes |  | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
13 | 02/002/28 | 81101500 | Mucurapo Overpass | Consultancy and reair of bridge | 2nd Quarter 2023/2024 | 3rd Quarter 2023/2024 | 60 days | Limited Bidding | Fixed Term Contract
Capital Expenditure/DP
Agua Santa Operations of
1 | XXXX | 30121600 | Maintenance of Plant & Equipment | Maintenance/repairs of machinery parts for batching drum mix asphalt plant and (loader) | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 30days | Three Quote System | Invoice
2 | XXXX | 46180000 | Personal Protective Equipment | PPE includes but is not limited to:-Safety Boots, Steel toe rubber boots, Hard Hat, Coveralls (flame resistant), Goggles, dust masks, welding glooves, Nitrile Glooves, Chemical resistant gloves, double sided gloves | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 10 days | Three Quote System | Invoice
3 | XXXX | 30121600 | Material & Supplies- | Purchase of Bitumen, CRSII, Diesel, for the production and application of Hot Mix Asphalt | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole select | Fixed Term Contract
4 | XXXX | 44120000 | Office Supplies | Purchase of office stationary, Printer/photocopier, furniture, computers, Paper, other supplies include cleaning materials, toiletries. | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Three Quote System | Invoice
5 | XXXX |  | Quality Control | Consultancy services for quality control. | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Three Quote System | Not applicable
6 | XXXX | 72101500 | Maintenance of Facilities | Maintenance of Office Building and compound:-Windows/door repairs, tiling, painting, air conditioning, furniture, cameras, refrigerator | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Three Quote System | Invoice
7 | XXXX | 83101800 83111501 83101500 | Utilities | Electricity, WASA, Phone and Internet | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole Select | Fixed Term Contract
8 | XXXX | 92120000 | Security Services | Security for the Agua Santa Asphalt Plant compound | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Open bidding | Fixed Term Contract
9 | XXXX | 86100000 | Safety Training and Development | All expenses associated with the training and development of staff both locally and abroad including: - cost of overseas travel pertinent to the training - cost of Contracted or Consultancy Services | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 | 21days | Sole select | Fixed Term Contract
10 | XXXX | 30121800 | Material & Supplies- | Purchase of Aggregate, Gravel for the production and application of Hot Mix Asphalt | 2nd Quarter of Fiscal 2024 | 3rd Quarter of Fiscal 2024 |  | Sole select | Fixed Term Contract
Formulas:
Expected Delivery/ Completion Date = [Expected Delivery/ Completion Date, row above]

## PBR Unit (hidden)
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
PBR Unit
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## PURE (hidden)
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
Programme for Upgrading Roads Efficiency
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type

## Maritime Division
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Maritime Division
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | xxxx | 80131500 | Rent / Lease - Office Accommodation & Storage | Rent / Lease of buildings which houses Government Offices. | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2025 | Not applicable | Sole Select | Not applicable
2 | xxxx | 72141700 | Rent / Lease - Vehicles & Equipment | Rent / Lease of vehicles & equipment. | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2025 | Not applicable | Sole Select | Not applicable
3 | xxxx | 15000000 | Fuel and Lubricants | To purchase diesel, gasoline, renew fleet cards etc. | 2nd Quarter Fiscal 2024 | 3rd Quarter Fiscal 2025 | Not applicable | Sole Selective Tendering | Fixed Term Contract
2 | xxxx | 41112900 | Supply and installation of fourteen (14) marine aids to navigation (buoys, marine lanterns, chains, swivels, with the respective shackles and subsea buoys along with seventeen concrete clumps | Twelve of these buoys have burst their respective moorings whereby this posses a significant danger to any mariner transiting within the respective vicinity of where the buoy are suppose to be located. | 28/10/24 | 18/11/24 | 3 months | sole select | Fixed Term Contract
4 | xxxx | 25111500 | The refurbishment of Motor Launch Inspector vessel | This would Aid MSD in being able to function in the following areas : Maintaining a regular schedule maintenance programme in regards to the Aton Lights. ( Tobago) Make regular visit to ports and private companies to ensure that they are in compliance with the Shipping Act rules and regulations. ( Tobago ) | 11-11-24 | 2013-12-24 | 3 months | sole select | Fixed Term Contract
5 | xxxx | 25111500 | The refurbishment of Motor Launch Surveyor vessel | This would Aid MSD in being able to function in the following areas : Maintaining a regular schedule maintenance programme in regards to the Aton Lights. ( Trinidad ) Make regular visit to ports and private companies to ensure that they are in compliance with the Shipping Act rules and regulations. ( Trinidad ) | 06-01-25 | 03-02-25 | 5 months | sole select | Fixed Term Contract

## Maintenance
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Maintenance Division
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | 02/007/03 | 53102700 | Purchase of Uniforms | Purchase of steel tip boots, rubber boots, coveralls, shirts, pants, welder apron, safety harness, leather gloves,helmets, goggles, ear muff, dust mask, etc. | Nov. 2024 | Jan.2025 | 1 month | RFQ | Fixed Term Contract
2 | 02/007/09 | 72141700 | Rental of Equipment | Rental of backhoe, jack hammer, terrazzo machine,hiab, shid steer, aerial work platform,bobcat,cherry picker, etc. | Nov. 2024 | Jan. 2025 | 2 months | RFQ | Fixed Term Contract
3 | 02/007/12 | 39121700 | Purchase of Electrical Materials | Correction of electrical defects in accordance with inspectorate standards for 1. Head Office MOWT-Richmond Street. 2. Farm Road MOWT Maintenance Office. 3. MOWT Couva Highways and Maintenance Office. | Oct. 2024 | Dec. 2024 | 4 months | Selective | Fixed Term Contract
4 | 02/007/12 | 39121700 | Purchase of Electrical Materials | Electrical materials associated with A/C installation for: 1. Laventille MOWT Maintenance Office, 2. Farm Road MOWT Maintenance Office | Jan. 2025 | Mar. 2025 | 2 weeks | Selective | Fixed Term Contract
5 | 02/007/12 | 76111602 | Duct Cleaning of MOWT Head Office. | Purchase of Materials | Oct. 2024 | Dec. 2024 | 2 months | Selective | Fixed Term Contract
6 | 02/007/12 | 72151511 | Contracted service to supply and install | Installation of Main Electrical Supply at MOWT Agua Santa Compound | 2024-12-01 | 2025-03-01 | 3 months | Selective Bidding | Fixed Term Contract
7 | 02/007/12 | 30100000 | Supply and delivery of items | The Supply and Delivery of Materials for Repairs to Maintenance Sub-Office Chaguanas, Electrical Building | 2025-01-01 | 2025-03-01 | 1 month | Selective Bidding | Fixed Term Contract
8 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the St. George West District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
9 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the St. George West District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
10 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the St. George East District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
11 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the St. George East District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
12 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the Caroni District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
13 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the Caroni District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
14 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the Victoria West District. | 2024-11-01 | 2025-01-01 | 2 Weeks | Selective Bidding | Fixed Term Contract
15 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the Victoria West District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
16 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the St. Andrew/St. David District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
17 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the St. Andrew/St. David District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
18 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the Victoria East District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
19 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the Victoria East District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
20 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the Nariva Mayaro District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
21 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the Nariva Mayaro District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
22 | 02/007/12 | 72102300 | Supply and delivery of items | The purchase of structural and plumbing consumables for routine maintenance works within the St. Patrick District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
23 | 02/007/12 | 72151511 | Supply and delivery of items | The purchase of electrical consumables for routine maintenance works within the St. Patrick District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
24 | 02/007/12 | 76111602 | Duct Cleaning of MOWT Caroni Licensing Office. | Purchase of Materials | Oct. 2024 | Dec. 2024 | 3 months | Selective | Fixed Term Contract
25 | 02/007/13 | 25175101 | Supply and delivery of items | The purchase of vehicle parts and consumables for vehicle repairs - Phase I | 2024-11-01 | 2025-01-01 | 1 month | Selective Bidding | Fixed Term Contract
26 | 02/007/13 | 25175101 | Supply and delivery of items | The purchase of vehicle parts and consumables for vehicle repairs - Phase II | 2025-01-01 | 2025-03-01 | 1 month | Selective Bidding | Fixed Term Contract
27 | 02/007/13 | 25175101 | Supply and delivery of items | The purchase of vehicle parts and consumables for vehicle repairs - Phase III | 2025-03-01 | 2025-05-01 | 1 month | Selective Bidding | Fixed Term Contract
28 | 02/007/17 | 42171917 | Training in First Aid & Specialist Skills. | To supply services | 2024-10-01 | 2025-12-01 |  | RFQ | Fixed Term Contract
29 | 02/007/21 | 72101511 | A/C Servicing of Licensing Office P.O.S ( 3 Services) | Purchase of Materials | Oct. 2024 | Dec. 2024 | 3 weekends | Selective | Fixed Term Contract
30 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the St. George West District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
31 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the St. George East District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
32 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the Caroni District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
33 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the Victoria West District. | 2024-11-01 | 2025-01-01 | 2 weeks | Selective Bidding | Fixed Term Contract
34 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the St. Andrew/St. David District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
35 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the Victoria East District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
36 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the Nariva Mayaro District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
37 | 02/007/21 | 72101511 | Supply and delivery of items | The purchase of air-conditioning consumables for routine maintenance works within the St. Patrick District. | 2024-12-01 | 2025-02-01 | 2 weeks | Selective Bidding | Fixed Term Contract
38 | 02/007/28 | 72101511 | Supply & Install Services | Supply and installation of energy efficient A/C mini split units for Laventille Maintenance Office- Ground Floor and First Floor. | Jan. 2025 | Mar. 2025 | 3 weeks | Selective | Fixed Term Contract
39 | 02/007/28 | 72101511 | Supply & Install Services | Supply and installation of energy efficient A/C mini spplit units for MOWT Maintenance Office- Farm Road | Jan. 2025 | Mar. 2025 | 2 weeks | Selective | Fixed Term Contract
40 | 02/007/28 | 46191505 | To Supply Services to Works Complex Rio Claro | To supply and install fire alarm and detection system for the compound - fire extinguishers with safety signage, smoke detectors and fire alarms. | Jan. 2025 | Mar. 2025 | 3 months | RFQ | Fixed Term Contract
41 | 02/007/28 | 72102104 | To Supply Services to Maintenance District Offices. | Pest control. | Oct . 2024 | Dec.. 2024 | 2 months | RFQ | Fixed Term Contract
42 | 02/007/28 | 72152707 | To Supply Services to Works Complex Princess Town. | Fencing and retaining wall. | Feb. 2025 | Apr. 2025 | 2 monhs | Selective | Fixed Term Contract
43 | 02/007/28 | 92121700 | To Supply Services to Works Complex Siparia | To install camera systems. | Jan. 2025 | Mar. 2025 | 3 months | RFQ | Fixed Term Contract
To install security gates (2) with motors and electrical .
Fire alarm and detection system.
44 | 02/007/28 | 92121700 | To Supply Services to Works Complex Maintenance Division, Main Office St. George East | Fire alarm and detection system. | Oct. 2024 | Sept. 2024 | 1 month | RFQ | Fixed Term Contract
A/C replacement.
45 | 02/007/28 | 92121700 | Supply & Install Services | Supply and installation of fire alarm and detection system for MOWT Rio Claro Office. | Jan. 2025 | Mar. 2025 | 4 weeks | Selective | Fixed Term Contract
46 | 02/007/28 | 92121700 | Supply & Install Services | Supply and installation of a fire alarm and detection system for MOWT Matilda Office. | Jan. 2025 | Mar. 2025 | 3 weeks | Selective | Fixed Term Contract
47 | 02/007/43 | 92121700 | Provision of Security Services - Maintenance Regional Office, Farah Street San Fernando. | For one (1) Year - One armed security officer for overnight security of compound and assets. | Oct. 2024 | Dec. 2024 | 2 months | RFQ | Fixed Term Contract
|  | 92121700 |  | 6pm - 6am shift, seven (7) days per week.
48 | 02/007/43 | 92121700 | Provision of Security Services - Maintenance Regional Office, Eastern Main Road, Laventille | For one (1) Year - One armed security officer and K9 for overnight security of compound and assets. | Oct. 2024 | Dec. 2024 | 2 months | RFQ | Fixed Term Contract
|  | 92121700 |  | 6pm - 6am shift, seven (7) days per week.
49 | 02/007/43 | 92121700 | Provision of Security Services - Maintenance Air Conditioning and Refrigeration Workshop, Frederick Street, Port of Spain | For one (1) Year - One armed security officer for overnight security of compound and assets. | Oct. 2024 | Dec.2024 | 2 months | RFQ | Fixed Term Contract
|  | 92121700 |  | 6pm - 6am shift, seven (7) days per week.
50 | 02/007/96 | 15101500 | Purchase of Fuels | Purchase of fuels for both eight containers and twenty-one vehicles. | Oct.2024 | Jun.2025 | 3 months | RFQ | Fixed Term Contract
51 | 03/007/01 | 25101601 | Procurement of a 1-Ton Dump Truck | Supply and Delivery | 2024-11-01 | 2025-02-01 | 3 months | Selective Bidding | Fixed Term Contract
52 | 03/007/01 | 25181702 | Procurement of a 3-Ton Flat Bed Truck | Supply and Delivery | 2024-11-01 | 2025-02-01 | 3 months | Selective Bidding | Fixed Term Contract
53 | 03/007/01 | 78111812 | Procurement of a 4 x 4 Pick Up Truck | Supply and Delivery | 2024-11-01 | 2025-02-01 | 3 months | Selective Bidding | Fixed Term Contract
54 | 03/007/01 | 25101600 | Procurement of a 3-Ton Double Cab Truck | Supply and Delivery | 2024-11-01 | 2025-02-01 | 3 months | Selective Bidding | Fixed Term Contract
55 | 03/007/02 | 44000000 | Purchase of Office Equipment | Purchase of Computers, printers, scanners, shredder, external hard drive, microwave, digital camera, gel wrist pads, white board, electronic adding calculator, etc. | Oct.2024 | Mar. 2025 | 3 months | RFQ | Fixed Term Contract
56 | 03/007/03 | 56101700 | Purchase of Furniture and Furnishings | Purchase of Computer desk, executive desk, metal desk, lateral filing cabinets, rubbish bins, wall clock swivel chairs, etc. | Oct.2024 | Mar. 2025 | 3 months | RFQ | Fixed Term Contract
57 | 03/007/04 | 44000000 | Purchase of Minor Equipment | Chop saw, electrical jack plane, belt sanders, extension cords, suction pump, leaf blower, rhino cables, table saw, welding plant, power washer, generator, road saw, drills, electric snake, auger, saw, standing fan, etc. | Oct. 2023 | Sept. 2024 | 1 yer | RFQ | Fixed Term Contract

## Mechanical Services Division
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Mechanical Services Division
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | 02/006/12-001/B | 27000000 | Operation Rigging Tools | To Purchase any tools for Heavy Equipment Operations or any specifications such as rigging equipment and harnesses, chains, ratcheting straps, binders chain hooks, lines man belt etc. | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
2 | 02/006/12 - 002/A | 27000000 | Machine Shop Consumables: Machinist, Carpenter, Industrial Electrican, Welding & Plate Section | To purchase machine shop consumables, welding tools and plate sections, electrical materials and tools, tyre tools and repair material, carpentry tools and materials, equipment bay tools and materials. | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
3 | 02/006/12 - 002/B | 27000000 | Garage Shop Consumables: Autobody, Upholtery, Mechanic and Electrical Section | To purchase machine shop consumables, and fittings, welding tools and plate sections, electrical materials and tools, tyre tools and repair material, Leather, glues, foams, threads, carpentry tools and materials, equipment bay tools and materials. | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
4 | 02/006/13 - 001 Repairs Maintenance of Excavators | 72154501 | Maintenance of Excavators | To purchase all parts for Excavators to conduct preventive maintenance, such as: oil, filters and tyres. To purchase parts for Excavators for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. |  |  |  | Request for Quotations | Fixed Term Contract
5 | 02/006/13-001/A | 72154501 | Repairs and Maintenance of XCH 434 Doosan Excavator 225LVC | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
6 | 02/006/13-001/B | 72154501 | Repairs and Maintenance of XCH 436 Doosan Excavator 225LVC | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
7 | 02/006/13-001/C | 72154501 | Repairs and Maintenance of XCH 437 Doosan Excavator 225LVC | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
8 | 02/006/13-001/D | 72154501 | Repairs and Maintenance of XCH 438 Doosan Excavator 225LVC | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
9 | 02/006/13-001/E | 72154501 | Repairs and Maintenance of XDG 4150 JCB Mini Excavator | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
10 | 02/006/13 - 002 Repairs and Maintenance of Trucks | 72154501 | Maintenance of Light Trucks, SUVs, Trucks, Trailers and other Heavy Equipment | To purchase all parts for Trucks, Trailers and other Heavy Equipment to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Trucks, Trailers and other Heavy Equipment for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. |  |  |  |  | Fixed Term Contract
11 | 02/006/13 - 002/A | 72154501 | Repairs and Maintenance of TCB 8046 Mitsubishi Hiab | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
12 | 02/006/13 - 002/B | 72154501 | Repairs and Maintenance of XCE 8498 John Deere Loader | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
13 | 02/006/13 - 002/C | 72154501 | Repairs and Maintenance of XCY 5724 John Deere Loader | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
14 | 02/006/13 - 002/D | 72154501 | Repairs and Maintenance of TDL 632 Water Master Dredger | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
15 | 02/006/13 - 002/E | 72154501 | Repairs and Maintenance of DW 3129 John Deere Bulldozer | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
16 | 02/006/13 - 002/F | 72154501 | Repairs and Maintenance of TDJ 3941 International Fuel Truck | Undercarraige, Hydraulic System, Auxillary Unit | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
17 | 02/006/13 - 003 Backhoes | 72154501 | Maintenance of Backhoes | To purchase all parts for Backhoes to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Backhoes for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. |  |  |  | Request for Quotations | Fixed Term Contract
18 | 02/006/13-003/A | 72154501 | TED8315 Caterpillar Backhoe 426f2 | To purchase all maintenance, upkeep and service items | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
19 | 02/006/13-003/B | 72154501 | TCX244 JCB Backhoe 4CX | To purchase all parts, labour, service and maintenance items | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
20 | 02/006/13-003/C | 72154501 | TDE9755 JCB Backhoe 3CX | To purchase all parts, labour, service and maintenance items | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract
21 | 02/006/13 - 004 Rollers and Skid Steer | 72154501 | Maintenance of Rollers and Skid Steer | To purchase all parts for Rollers and Skid Steers to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Rollers and Skid Steer for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. |  |  |  | Request for Quotations | Fixed Term Contract
22 | 02/006/13-004/A | 72154501 | XCE8498 John Deere Skid Steer | To purchase al parts, labour, service and maintenance items | Oct. - Aug. 2024 | Oct. - Aug. 2025 | 40-45 Weeks | Request for Quotations | Fixed Term Contract

## PURE 1
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Expenses of the Project Management Unit, Programme for Upgrading Roads Efficiency
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
1 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | 42nd Street [Road Rehabilitation],Off Laventille Road | 2025-02-01 | 2025-05-14 | 10 days | Selective Tendering/Limited Tendering | Unit Price
2 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | 4th Drive [Road Rehabilitation],Off Mt. Dor Road, Champ Fleurs | 2024-12-12 | 2025-03-25 | 15 days | Selective Tendering/Limited Tendering | Unit Price
3 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Adamsville Road [Slope Stabilization - Package 1],Off Lady Young Road | 2025-02-01 | 2025-06-17 | 60 days | Selective Tendering/Limited Tendering | Unit Price
4 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Adamsville Road [Slope Stabilization and Roadworks - Package 2],Off Lady Young Road | 2024-11-01 | 2025-05-07 | 120 days | Selective Tendering/Limited Tendering | Unit Price
5 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Alexander Street [Road Rehabilitation],Ste. Madeleine | 2025-06-01 | 2025-09-23 | 40 days | Selective Tendering/Limited Tendering | Unit Price
6 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Alyce Glen Garden [Road Works],Off Alyce Glen Main Road | 2024-05-01 | 2024-12-01 | 5 days | Selective Tendering/Limited Tendering | Unit Price
7 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Alyce Glen Network [Road Rehabilitation],Off Alyce Glen Main Road | 2024-05-01 | 2024-12-01 | 5 days | Selective Tendering/Limited Tendering | Unit Price
8 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Aranguez Main Road [Road Rehabilitation];Off Aranguez El Socorro Access Road | 2025-04-01 | 2025-07-01 | 10 days | Selective Tendering/Limited Tendering | Unit Price
9 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Aziz Lane [Road Rehabilitation],Off Eastern Main Road | 2025-06-15 | 2025-09-17 | 15 days | Selective Tendering/Limited Tendering | Unit Price
10 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Baroda Street [Road Rehabilitation],Off Tragarette Road | 2025-01-01 | 2025-05-29 | 10 days | Selective Tendering/Limited Tendering | Unit Price
11 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Beau Pres Road [Road Works],Off Saut D'eau Road | 2024-05-01 | 2024-12-01 | 10 days | Selective Tendering/Limited Tendering | Unit Price
12 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Beaucarro Road [Drainage Works], | 2025-11-15 | 2025-03-15 | 60 days | Selective Tendering/Limited Tendering | Unit Price
13 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Beetham Highway - NP Ramp Acceleration Lane Upgrade,Port of Spain | 2024-11-01 | 2025-06-01 | 240 days | Selective Tendering/Limited Tendering | Unit Price
14 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Beetham Highway [Road Works - Foam Bitumen Stabilisation],Sealots Market Intersection | 2024-12-10 | 2025-04-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
15 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Beharrylal Road [Roadworks],Off La Seiva Road | 2025-02-15 | 2025-06-01 | 15 days | Selective Tendering/Limited Tendering | Unit Price
16 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Beetham Highway/Churchill Roosevelt Highway - Barataria Ramp and Underpass Upgrade,In the vicinity of MOWT Stockpile, Barataria | 2024-11-01 | 2025-05-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
17 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Blanchisseuse Road - Package 11 [Roadworks],Chainage 17+000 to 18+800 [From Eastern Main Road] | 2024-10-01 | 2025-03-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
18 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Blanchisseuse Road - Package 12 [Road Works],Chainage 1+500 to 3 + 000 [from North Coast Road] | 2024-10-10 | 2025-02-26 | 15 days | Selective Tendering/Limited Tendering | Unit Price
19 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Blanchisseuse Road - Package 13 [Drainage Works],Chainage 3 + 000 to 4 + 500 [from North Coast Road] | 2024-10-10 | 2025-01-09 | 60 days | Selective Tendering/Limited Tendering | Unit Price
20 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Blanchisseuse Road - Package 14 [Road Works],Chainage 3 + 000 to 4 + 500 [from North Coast Road] | 2024-11-01 | 2025-03-03 | 15 days | Selective Tendering/Limited Tendering | Unit Price
21 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Blanchisseuse Road [Road Rehabilitation],from Scott quarry to La Laja road | 2024-11-01 | 2025-03-31 | 10 days | Selective Tendering/Limited Tendering | Unit Price
22 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Blanchisseuse Road [Road Works - Package 9] ,From Eastern Main Road, Chainage 15+700 to 17+000 | 2024-11-10 | 2025-03-11 | 20 days | Selective Tendering/Limited Tendering | Unit Price
23 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Blanchisseuse Road [Slope Stabilization],Chainage 6 + 400 to 7 + 500 | 2024-12-01 | 2025-04-05 | 60 days | Selective Tendering/Limited Tendering | Unit Price
24 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Bon Air Road [Slope Stabilization],LP# 183 - 185 | 2024-12-15 | 2025-05-03 | 60 days | Selective Tendering/Limited Tendering | Unit Price
25 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Bridge Reconstruction | Bosierre Trace (Bridge Reconstruction),Off Gran Couva Main Road | 2024-11-15 | 2025-06-11 | 120 days | Selective Tendering/Limited Tendering | Unit Price
26 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Boundary Road [Road Rehabilitation],Between Aranguez Main Road and Aranguez-El Socorro Access Road | 2024-07-19 | 2024-11-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
27 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Brasso Caparo Station Road [Slope Stabilization],5km Marker | 2025-03-01 | 2025-09-07 | 90 days | Selective Tendering/Limited Tendering | Unit Price
28 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Busby Street [Road Rehabilitation],From Dos Santos to Busby Street | 2024-11-01 | 2025-03-12 | 20 days | Selective Tendering/Limited Tendering | Unit Price
29 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Caliste Street [Road Rehabilitation],Off Mausica Road | 2025-01-01 | 2025-05-07 | 10 days | Selective Tendering/Limited Tendering | Unit Price
30 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Caparo Valley Brasso Road [Concrete Works - Pkg 1] | 2024-10-20 | 2025-01-30 | 60 days | Selective Tendering/Limited Tendering | Unit Price
31 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Caparo Valley Brasso Road [Concrete Works - Pkg 2] | 2024-10-20 | 2025-01-30 | 60 days | Selective Tendering/Limited Tendering | Unit Price
32 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Carrat Hill [Roadworks],Off New Colonial Road | 2025-01-01 | 2025-04-24 | 30 days | Selective Tendering/Limited Tendering | Unit Price
33 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cassia Street #1 [Road Rehabilitation],Off Lady Young Avenue | 2025-02-01 | 2025-06-24 | 20 days | Selective Tendering/Limited Tendering | Unit Price
34 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cassia Street #2 [Road Rehabilitation],OffCassia Street #1 | 2025-03-01 | 2025-07-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
35 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Chanka Trace, Chotoo Road and Hingoo Road [Sectional Patching],El Socorro South | 2024-10-01 | 2024-12-26 | 20 days | Selective Tendering/Limited Tendering | Unit Price
36 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Churchill Roosevelt Highway - Construction of 3rd Lane - Eastbound,From Andrew Lane to O'Meara Road | 2024-10-01 | 2025-12-01 | 365 days | Selective Tendering/Limited Tendering | Unit Price
37 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Churchill Roosevelt Highway [Road Rehabilitation - Eastbound],From Pinto Road to Demerara Intersection | 2024-10-05 | 2024-12-21 | 20 days | Selective Tendering/Limited Tendering | Unit Price
38 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Churchill Roosevelt Highway [Road Rehabilitation - Package 1 - East and Westbound],From Demerara Road to Cumuto Road | 2024-10-10 | 2024-12-24 | 30 days | Selective Tendering/Limited Tendering | Unit Price
39 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Churchill Roosevelt Highway [Road Rehabilitation - Package 2 - East and Westbound],From Cumuto Road to Antigua Road | 2024-10-01 | 2024-11-17 | 20 days | Selective Tendering/Limited Tendering | Unit Price
40 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Churchill Roosevelt Highway [Road Rehabilitation - Package 3 - East and Westbound],From O'Meara Road to Mausica Road | 2024-10-01 | 2024-10-30 | 30 days | Selective Tendering/Limited Tendering | Unit Price
41 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Churchill Roosevelt Highway [Road Rehabilitation - Package 4 - East and Westbound],From Tumpuna Road to O'Meara Road | 2024-10-01 | 2024-12-24 | 30 days | Selective Tendering/Limited Tendering | Unit Price
42 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Churchill Roosevelt Highway [Road Rehabilitation - Westbound],From Pinto Road to Tumpuna Road | 2024-10-01 | 2024-11-03 | 30 days | Selective Tendering/Limited Tendering | Unit Price
43 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation/Road Construction Works | Construction of CRHEM (Segment 4 - Railway Road) [Road Rehabilitaiton & Associated Works],Railway Road, from Railway Road Extension to Michael Street | 2024-10-01 | 2025-05-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
44 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cornelio Street [Road Rehabilitation],Off Tragarete Road | 2024-05-01 | 2024-12-31 | 5 days | Selective Tendering/Limited Tendering | Unit Price
45 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation/Road Construction Works | CRHEM to Cumuto Road Intersection [Road Rehabilitation/Road Construction],Cumuto Road | 2024-10-01 | 2025-03-01 | 70 days | Selective Tendering/Limited Tendering | Unit Price
46 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 |  | Crow Trace [Concrete, Drainage & Slope Stabilization],Off Laventille Road | 2024-10-05 | 2025-01-31 | 60 days | Selective Tendering/Limited Tendering | Unit Price
47 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Crown Trace [Road Rehabilitation],From ''S' Bend to Southern Main Road | 2024-06-25 | 2024-11-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
48 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cumuto Road [Patching] - Package 3,1+800 to 3+500 | 2024-12-12 | 2025-03-09 | 30 days | Selective Tendering/Limited Tendering | Unit Price
49 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cumuto Road [Patching] - Package 4,0+000 (@ Little Coora Road) to 1+800 | 2025-01-10 | 2025-04-06 | 30 days | Selective Tendering/Limited Tendering | Unit Price
50 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cumuto Road [Road Rehabilitation - Package 1],Between Churchill Roosevelt Highway & Eastern Main Road | 2024-06-04 | 2024-12-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
51 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cumuto Road [Road Rehabilitation - Package 2],Chainage 3+500 to 5+200 | 2024-06-04 | 2024-12-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
52 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cumuto Road [Road Rehabilitation],Barrackpore | 2025-03-01 | 2025-07-05 | 60 days | Selective Tendering/Limited Tendering | Unit Price
53 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cumuto Tamana Road [Sectional Rehabilitation - Package 1],LP#92 to Chainage 6+300 | 2024-06-06 | 2025-01-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
54 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Cumuto-Tamana Road - Package 2 [Patching],0+000 to 4+000 | 2025-04-01 | 2025-07-02 | 30 days | Selective Tendering/Limited Tendering | Unit Price
55 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Damian Street [Road Rehabilitation],Off Tragarette Road | 2025-03-01 | 2025-06-01 | 10 days | Selective Tendering/Limited Tendering | Unit Price
56 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | De La Marre Avenue [Road Rehabilitation],Off Trincity Boulevard | 2025-01-02 | 2025-03-24 | 20 days | Selective Tendering/Limited Tendering | Unit Price
57 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Don Miguel Road [Road Rehabilitation],Between Churchill Roosevelt Highway and 5th Street, Barataria | 2024-07-19 | 2024-11-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
58 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Eastern Main Road [Road Rehabilitation],NP Service Station to Silvermill Road | 2025-06-15 | 2025-09-15 | 45 days | Selective Tendering/Limited Tendering | Unit Price
59 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Flood Alleviation Works | Eastern Main Road Tunapuna (Flood Alleviation Project),From Mc Carthy Street to Scott Street | 2025-10-01 | 2025-05-24 | 120 days | Selective Tendering/Limited Tendering | Unit Price
60 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Flood Alleviation Works | Eastern Main Road Tunapuna (Flood Alleviation Project),From Tunapuna Road to Auzonville Bridge | 2025-10-01 | 2025-05-29 | 120 days | Selective Tendering/Limited Tendering | Unit Price
61 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Eastern Main Road, Sangre Grande [Road Rehabilitation - Package 3],From Baboolal Trace to Warden Road | 2024-06-06 | 2024-12-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
62 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Edinburgh Road [Road Rehabilitation],From Capary Valley Brasso Road to Cashew Boulevard | 2024-06-04 | 2024-11-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
63 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | El Socorro Main Road [Road Rehabilitation],Off Aranguez El Socorro Access Road | 2025-06-01 | 2025-09-27 | 30 days | Selective Tendering/Limited Tendering | Unit Price
64 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Eliza Avenue [Road Works],Off Madras Road, St. Helena | 2024-06-04 | 2024-11-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
65 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Foster Road Extension [Roadworks], | 2025-06-01 | 2025-09-14 | 10 days | Selective Tendering/Limited Tendering | Unit Price
66 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Ganges Street [Road Rehabilitation],Off Western Main Road | 2025-05-01 | 2025-08-10 | 10 days | Selective Tendering/Limited Tendering | Unit Price
67 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Bridge Reconstruction | Garth Road (Bridge Reconstruction),Scale Road Junction | 2024-12-12 | 2025-06-07 | 120 days | Selective Tendering/Limited Tendering | Unit Price
68 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Grand Couva - BSM - Ph 1, |  |  |  | Selective Tendering/Limited Tendering | Unit Price
69 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Greaves Trace [Roadworks],Off Quarry Road, off Santa Cruz Old Road | 2025-06-01 | 2025-09-03 | 15 days | Selective Tendering/Limited Tendering | Unit Price
70 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Guaico Tamana - Cement Stabilization | 2025-01-02 | 2025-05-13 | 30 days | Selective Tendering/Limited Tendering | Unit Price
71 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Guaico Village Street No. 3 Extension [Roadworks], | 2025-05-01 | 2025-08-24 | 15 days | Selective Tendering/Limited Tendering | Unit Price
72 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Guaracara Tabaquite Road [Roadworks - Package 1 ],7km to 8km mark | 2025-03-01 | 2025-06-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
73 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Guaracara Tabaquite Road [Roadworks - Package 2],9km to 10km mark | 2025-04-01 | 2025-07-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
74 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Hankey Street [Road Rehabilitation],Off Panco Lane, Vistabella | 2025-12-01 | 2025-07-07 | 15 days | Selective Tendering/Limited Tendering | Unit Price
75 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Bridge Reconstruction | Hermitage Road Union Village (Bridge Reconstruction),Claxton Bay, near Union Presbyterian School | 2025-10-01 | 2025-03-23 | 90 days | Selective Tendering/Limited Tendering | Unit Price
76 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Hillview Terrace [Road Works],Off La Belle Vue, Paramin | 2024-05-01 | 2024-12-01 | 5 days | Selective Tendering/Limited Tendering | Unit Price
77 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Hummingbird Drive & Casia Boulevard [Road Rehabilitation],Edinburgh 500, Montrose, Chaguanas | 2024-06-04 | 2024-11-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
78 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Hyderabad Street [Road Rehabilitation],Off Nepal Street | 2024-05-01 | 2024-12-01 | 5 days | Selective Tendering/Limited Tendering | Unit Price
79 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Improvement to Endeavour Interchange - Phase 2 (Chaguanas Traffic Alleviation),In the vicinity of Mulchan Seuchan Road | 2024-11-01 | 2025-08-01 | 300 days | Selective Tendering/Limited Tendering | Unit Price
80 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Jereton Street [Road Rehabilitation],Off Lady Young Avenue | 2025-12-20 | 2025-04-14 | 30 days | Selective Tendering/Limited Tendering | Unit Price
81 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Jerningham Avenue [Road Rehabilitation],Off Queen's Park East | 2025-03-01 | 2025-06-30 | 30 days | Selective Tendering/Limited Tendering | Unit Price
82 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | La Horquette Valley Road [Road Rehabilitation - Package 1],Off Western Main Road, Glencoe | 2025-03-01 | 2025-06-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
83 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | La Mango Road [Roadworks],Off Maracas Royal Road | 2025-02-01 | 2025-07-21 | 20 days | Selective Tendering/Limited Tendering | Unit Price
84 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | La Providence Road [Roadworks],Off Acono Road, Maracas Royal Road | 2025-05-01 | 2025-08-05 | 15 days | Selective Tendering/Limited Tendering | Unit Price
85 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Las Mercedes Trace [Roadworks],Off Todd's Station Road, Talparo | 2025-06-01 | 2025-09-08 | 15 days | Selective Tendering/Limited Tendering | Unit Price
86 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Little Coora Road - Package 1 [Roadworks],Off Cumuto Road (CH 0+000 to CH 2+000) | 2025-04-01 | 2025-07-21 | 20 days | Selective Tendering/Limited Tendering | Unit Price
87 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Little Coora Road - Package 2 [Roadworks],Off Cumuto Road (CH 2+000 to CH 4+000) | 2025-05-01 | 2025-08-09 | 20 days | Selective Tendering/Limited Tendering | Unit Price
88 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Lower Campo Street [Road Rehabilitation],Off Santa Cruz Old Road | 2025-06-01 | 2025-09-13 | 15 days | Selective Tendering/Limited Tendering | Unit Price
89 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Culvert Reconstruction | Lp # 159 Arima Old Road [Culvert Reconstruction], | 2024-12-01 | 2025-03-17 | 60 days | Selective Tendering/Limited Tendering | Unit Price
90 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Lp # 26 Lopinot Road [Slope Stabilization], | 2025-02-01 | 2025-05-27 | 90 days | Selective Tendering/Limited Tendering | Unit Price
91 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Lp # 29 Lopinot Road [Slope Stabilization], | 2024-10-01 | 2024-12-30 | 90 days | Selective Tendering/Limited Tendering | Unit Price
92 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Lp #84 Upper La Puerta Avenue [Slope Stabilization],Diego Martin | 2025-03-01 | 2025-06-13 | 45 days | Selective Tendering/Limited Tendering | Unit Price
93 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | LP1-LP7 Sea Lots [Road Rehabilitation],Off Pioneer Drive Sea Lots | 2025-02-01 | 2025-05-24 | 10 days | Selective Tendering/Limited Tendering | Unit Price
94 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | M1 Tasker Road [Road Rehabilitation - Package 2],From Naparima Mayaro Road to Calladium Drive | 2024-06-06 | 2024-11-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
95 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Malabar Road [Sectional Rehabilitation],Between Quensel Street & Lennox Yearwood Expressway | 2024-06-06 | 2024-12-01 | 14 days | Selective Tendering/Limited Tendering | Unit Price
96 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Maloney Boulevard [Road Rehabilitation],From Jacana Avenue to Sanderling Terrace | 2025-01-01 | 2025-05-12 | 20 days | Selective Tendering/Limited Tendering | Unit Price
97 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Maria David Trace [Road Rehabilitation],Off San Francique Road | 2024-06-06 | 2024-11-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
98 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Moka Road [Road Works],From Trinity College to Orchard Gardens, Maraval | 2024-05-01 | 2024-12-01 | 5 days | Selective Tendering/Limited Tendering | Unit Price
99 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Monsegue Lane [Road Rehabilitation], | 2025-03-01 | 2025-06-20 | 15 days | Selective Tendering/Limited Tendering | Unit Price
100 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Morne Coco Road [Road Rehabilitation],From Four Roads to Majuba Cross Road | 2024-02-01 | 2024-04-30 | 60 days | Selective Tendering/Limited Tendering | Unit Price
101 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Morne Roach Road [Road Works],Off Caco Road, Paramin | 2024-05-01 | 2024-12-01 | 5 days | Selective Tendering/Limited Tendering | Unit Price
102 | 701/43/003/15/D/288 Construction of Moruga Highway | 72152700 | Slope Stabilization Works | Moruga Road Ch 13+700 [Slope Stabilization & Associated Works],Moruga Road | 2024-05-20 | 2025-03-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
103 | 701/43/003/15/D/288 Construction of Moruga Highway | 72152700 | Slope Stabilization Works | Moruga Road Ch 14+400 [Slope Stabilization & Associated Works],Moruga Road | 2024-05-20 | 2025-05-01 | 150 days | Selective Tendering/Limited Tendering | Unit Price
104 | 701/43/003/15/D/288 Construction of Moruga Highway | 72152700 | Slope Stabilization Works | Moruga Road Ch 15+550 [Slope Stabilization & Associated Works],Moruga Road | 2024-05-20 | 2025-03-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
105 | 701/43/003/15/D/288 Construction of Moruga Highway | 72152700 | Slope Stabilization Works | Moruga Road Ch 16+700 [Slope Stabilization & Associated Works],Moruga Road | 2024-05-20 | 2025-04-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
106 | 701/43/003/15/D/288 Construction of Moruga Highway | 72152700 | Slope Stabilization Works | Moruga Road Ch 17+200 [Slope Stabilization & Associated Works],Moruga Road | 2024-05-20 | 2025-04-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
107 | 701/43/003/15/D/288 Construction of Moruga Highway | 72152700 | Slope Stabilization Works | Moruga Road Ch 19+100 [Slope Stabilization & Associated Works],Moruga Road | 2024-05-20 | 2025-04-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
108 | 701/43/003/15/D/288 Construction of Moruga Highway | 72152700 | Slope Stabilization Works | Moruga Road Ch 4+700 [Slope Stabilization & Associated Works],Moruga Road | 2024-05-20 | 2025-03-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
109 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Mt. Hope South Access Road [Road Rehabilitation],Off Arthur Lok Jack Roundabout | 2024-10-01 | 2024-12-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
110 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Mt. Pleasant Road [Road Rehabilitation],Arima | 2025-02-01 | 2025-05-29 | 15 days | Selective Tendering/Limited Tendering | Unit Price
111 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Murray Street [Road Rehabilitation],Off Tragarette Road | 2025-06-01 | 2025-09-13 | 20 days | Selective Tendering/Limited Tendering | Unit Price
112 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Naparima Mayaro Road [Road Works],From Spring Fresh Hardware to Hindustan Road | 2024-06-06 | 2025-01-01 | 60 days | Selective Tendering/Limited Tendering | Unit Price
113 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Naparima Mayaro Road, Lazare Road to Dades Trace | 2025-02-01 | 2025-06-01 | 60 days | Selective Tendering/Limited Tendering | Unit Price
114 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Oilfield Road [Roadworks],Off S.S Erin Road | 2025-03-01 | 2025-07-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
115 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Ojar Avenue [Road Rehabilitation],Off Caliste Street, Mausica | 2024-12-01 | 2025-03-26 | 15 days | Selective Tendering/Limited Tendering | Unit Price
116 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Culvert Reconstruction | Orange Grove Road [Culvert Rehabilitation],Dry River Intersection | 2024-11-01 | 2025-04-22 | 90 days | Selective Tendering/Limited Tendering | Unit Price
117 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Oropouche Road [Road Rehabilitation - Package 1],From South Trunk Road to Fyzabad Road | 2024-07-19 | 2025-02-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
118 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Oudai Trace [Drainage and Roadworks],Off Johnny King | 2025-10-01 | 2025-01-13 | 45 days | Selective Tendering/Limited Tendering | Unit Price
119 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Bridge Reconstruction | Paria Main Road [Bridge Reconstruction],69km Marker | 2025-11-01 | 2025-07-29 | 200 days | Selective Tendering/Limited Tendering | Unit Price
120 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Bridge Reconstruction | Paria Main Road [Bridge Reconstruction],B 1/71 | 2024-12-15 | 2025-09-19 | 200 days | Selective Tendering/Limited Tendering | Unit Price
121 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Culvert Reconstruction | Paria Main Road [Culvert Reconstruction],Chainage 6+ 000 to 7+ 000 | 2024-12-01 | 2025-03-07 | 60 days | Selective Tendering/Limited Tendering | Unit Price
122 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Paria Main Road [Road Rehabilitation],From Pepper Hill Street to Mervyn Dillion Road | 2025-05-01 | 2025-08-30 | 60 days | Selective Tendering/Limited Tendering | Unit Price
123 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Paria Main Road [Slope Stabilization],LP #175 | 2024-11-15 | 2025-04-04 | 30 days | Selective Tendering/Limited Tendering | Unit Price
124 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Paria Main Road LP# 996 [Concrete & Drainage Works],Toco | 2024-05-27 | 2025-01-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
125 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Parshley Street [Road Rehabilitation],Off Old St. Joseph Road | 2025-05-01 | 2025-08-20 | 30 days | Selective Tendering/Limited Tendering | Unit Price
126 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Pelican Extension [Road Rehabilitation],Off Cicada Street, Morvant | 2025-12-02 | 2025-04-20 | 20 days | Selective Tendering/Limited Tendering | Unit Price
127 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Petit Curcucaye Branch Road [Drainage and Roadworks],Santa Cruz Old Road, San Juan | 2025-04-01 | 2025-08-07 | 60 days | Selective Tendering/Limited Tendering | Unit Price
128 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Pinto Road [Sectional Rehabilitation],Arima | 2024-06-06 | 2024-11-01 | 14 days | Selective Tendering/Limited Tendering | Unit Price
129 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Pipiol Road [Roadworks],Off Cantaro Extension Road | 2025-03-01 | 2025-07-10 | 30 days | Selective Tendering/Limited Tendering | Unit Price
130 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Pleasantville Circular [Road Rehabilitation] | 2025-01-02 | 2025-06-01 | 60 days | Selective Tendering/Limited Tendering | Unit Price
131 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Power Street [Roadworks], | 2025-06-01 | 2025-09-10 | 20 days | Selective Tendering/Limited Tendering | Unit Price
132 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Prince of Wales Street [Road Rehabilitation], | 2024-10-10 | 2024-12-16 | 15 days | Selective Tendering/Limited Tendering | Unit Price
133 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Princes Charles Street [Road Rehabilitation],Between Cipero Street & Princess Margaret Street | 2025-03-01 | 2025-07-09 | 15 days | Selective Tendering/Limited Tendering | Unit Price
134 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Prizgarlands Network [Road Rehabilitation],Off the Eastern Main Road, Laventille | 2025-03-01 | 2025-06-03 | 30 days | Selective Tendering/Limited Tendering | Unit Price
135 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Quarry Road [Roadworks],Morne Diablo Leading to the beach | 2025-02-01 | 2025-05-18 | 30 days | Selective Tendering/Limited Tendering | Unit Price
136 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Queen Street [Road Rehabilitation],Arima | 2024-12-15 | 2025-03-24 | 15 days | Selective Tendering/Limited Tendering | Unit Price
137 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Quinam Road [Drainage and Roadworks],Penal | 2025-03-01 | 2025-06-04 | 30 days | Selective Tendering/Limited Tendering | Unit Price
138 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Railway Road (Eastbound) and 5th Street [Road Rehabilitation],Off Aranguez Main Road | 2025-03-10 | 2025-06-13 | 30 days | Selective Tendering/Limited Tendering | Unit Price
139 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Rameo Street [Road Rehabilitation],Off Western Main Road St James | 2025-07-01 | 2025-09-30 | 10 days | Selective Tendering/Limited Tendering | Unit Price
140 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Ramjattan Trace [Roadworks],Off SS Erin Road, Debe | 2025-02-01 | 2025-05-04 | 20 days | Selective Tendering/Limited Tendering | Unit Price
141 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Ramlal Trace [Road Rehabilitation],Off Johnny King | 2025-03-01 | 2025-06-27 | 15 days | Selective Tendering/Limited Tendering | Unit Price
142 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Redwood Street [Road Rehabilitation],Off Plover Street, Morvant | 2024-12-15 | 2025-03-04 | 20 days | Selective Tendering/Limited Tendering | Unit Price
143 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Robinson Drive [Road Rehabilitation],Off Mt. Dor Road, Champ Fleurs | 2025-03-01 | 2025-07-10 | 15 days | Selective Tendering/Limited Tendering | Unit Price
144 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Rodney Road [Road Rehabilitation],Between ANSA McAL and Prestige Glass | 2024-06-25 | 2024-11-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
145 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Rupert Trace Bellevue [Slope Stabilization & Associated Works], | 2025-04-01 | 2025-08-01 | 60 days | Selective Tendering/Limited Tendering | Unit Price
146 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Sadhoo Trace [Road Rehabilitation],Off El Socorro Extension No 1 | 2025-04-01 | 2025-06-24 | 15 days | Selective Tendering/Limited Tendering | Unit Price
147 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Sahai Road [Road Rehabilitation],Barrackpore | 2025-01-02 | 2025-05-19 | 60 days | Selective Tendering/Limited Tendering | Unit Price
148 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Samuel Cooper Road [Slope Stabilization - Package 1],LP #15 | 2025-02-01 | 2025-07-01 | 60 days | Selective Tendering/Limited Tendering | Unit Price
149 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Samuel Cooper Road [Slope Stabilization - Package 2],LP #17 | 2025-04-01 | 2025-09-01 | 60 days | Selective Tendering/Limited Tendering | Unit Price
150 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Sandy Trace [Road Rehabilitation],Off Upper St Francois Valley Road | 2024-10-01 | 2024-11-18 | 30 days | Selective Tendering/Limited Tendering | Unit Price
151 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Sangre Grande to Manzanilla [Road Rehabilitation, Road Widening & Culvert Reconstruction - Package 5],Chainage 8+000 to 10+000 | 2024-11-01 | 2025-08-01 | 240 days | Selective Tendering/Limited Tendering | Unit Price
152 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Santa Barbara Boulevard & Extension [Road Works],Off Saddle Road, Santa Cruz | 2024-07-19 | 2024-12-01 | 40 days | Selective Tendering/Limited Tendering | Unit Price
153 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Second Avenue [Road Rehabilitation],Off Cascade Road | 2025-10-01 | 2024-11-13 | 30 days | Selective Tendering/Limited Tendering | Unit Price
154 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Sierra Leone Road [Road Rehabilitation],From Diego Martin Main Road to Diego Martin Highway | 2024-12-10 | 2025-02-25 | 30 days | Selective Tendering/Limited Tendering | Unit Price
155 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Sisters Road Ch. 0+350 to Ch. 0+750 [Drainage & Road Works],Williamsville | 2024-06-06 | 2025-02-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
156 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Sisters Road [Roadworks - Package 1],0km to 1km mark | 2025-03-01 | 2025-07-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
157 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Sisters Road [Roadworks - Package 2],2km to 3km mark | 2025-04-01 | 2025-08-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
158 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Southern Central Road [Road Works - Package 2],from Dunlop Roundabout to Cap De Ville Junction | 2025-02-01 | 2025-06-27 | 60 days | Selective Tendering/Limited Tendering | Unit Price
159 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Southern Main Road Intersection, Claxton Bay [Concrete, Drainage & Road Works],At Super Foods Supermarket | 2024-06-06 | 2025-01-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
160 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Southern Main Road Upgrade,From HDC Development to Farm Road | 2024-11-01 | 2025-04-01 | 120 days | Selective Tendering/Limited Tendering | Unit Price
161 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Southern Main Road, La Brea [Road Work - Package 2],From Cochrane to Dunlop Roundabout [Chainage 6+000 to 9+400] | 2024-07-19 | 2025-02-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
162 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Southern Main Road, La Brea [Road Works - Package 1],From La Brea Roundabout to Sobo/Boodoosingh Road [Chainage 0+000 to 4+260] | 2024-07-19 | 2025-02-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
163 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Southern Main Road, La Brea to Otaheite [Package 2],From Sobo/Boodoosingh Road to Aadi Marketing Auto Parts [Chainage 4+260 to 12+210] | 2025-05-01 | 2025-08-03 | 20 days | Selective Tendering/Limited Tendering | Unit Price
164 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Southern Main Road [Drainage, Road Widening with Foam Bitumen Stabilization Works - Package 1],Between Washington Roundabout and Warren Road | 2024-11-01 | 2025-06-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
165 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Southern Main Road [Drainage, Road Widening with Foam Bitumen Stabilization Works - Package 2],Between Washington Roundabout and Warren Road | 2024-11-01 | 2025-06-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
166 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | St. Clair Avenue [Road Rehabilitation],Off Queen's Park Savannah | 2024-11-01 | 2025-02-13 | 30 days | Selective Tendering/Limited Tendering | Unit Price
167 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Ste. Madeleine Circular [Road Rehabilitation], | 2024-11-01 | 2025-02-20 | 30 days | Selective Tendering/Limited Tendering | Unit Price
168 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Third Street [Road Rehabilitation],Off Andrew Lane, D'Abadie | 2025-01-05 | 2025-04-05 | 10 days | Selective Tendering/Limited Tendering | Unit Price
169 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Tragarete Road [Road Rehabilitation],From Gray Street to Roxy Roundabout | 2024-05-01 | 2024-12-01 | 5 days | Selective Tendering/Limited Tendering | Unit Price
170 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Traffic Management Measure | Tumpuna Road Upgrade,Arima | 2024-10-01 | 2025-06-21 | 240 days | Selective Tendering/Limited Tendering | Unit Price
171 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | UBH Dedicated Bus Route Lane,Between Arthur Lok Jack Roundabout to Laventille Regional Corp | 2025-03-01 | 2025-07-01 | 30 days | Selective Tendering/Limited Tendering | Unit Price
172 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Unis Street [Drainage Works],Off Salazar Trace | 2025-12-15 | 2025-04-03 | 60 days | Selective Tendering/Limited Tendering | Unit Price
173 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road - Package 1 [Road Rehabilitation],CH 0+000 to Gov Trace (CH 0+700) | 2024-04-17 | 2025-01-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
174 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road - Package 2 [Road Rehabilitation],CH 0+700 to Gov Trace (CH 1+400) | 2024-04-17 | 2025-01-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
175 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road - Package 3 [Road Rehabilitation],CH 0+700 to Gov Trace (CH 1+400) | 2024-04-17 | 2025-01-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
176 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road - Package 4 [Road Rehabilitation],CH 1+400 to 2+000 (Corner to Las Lomas #2) | 2024-04-17 | 2025-01-01 | 90 days | Selective Tendering/Limited Tendering | Unit Price
177 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road [Concrete & Drainage Works - Package 1],At Batcha Cane Trace to Ch. 1+400 - South Side | 2025-02-01 | 2025-05-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
178 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road [Concrete & Drainage Works - Package 2],Ch. 2+000 - South Side | 2025-03-01 | 2025-06-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
179 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road [Concrete & Drainage Works - Package 3],From Gov Trace to Ch. 1+900 - North Side | 2025-04-01 | 2025-07-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
180 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Chin Chin Road [Concrete & Drainage Works - Package 4],From Ch. 2+000 to Ch. 2+400 | 2025-05-01 | 2025-08-01 | 20 days | Selective Tendering/Limited Tendering | Unit Price
181 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Hillside Street [Road Rehabilitation], | 2025-04-01 | 2025-07-29 | 40 days | Selective Tendering/Limited Tendering | Unit Price
182 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Slope Stabilization Works | Upper Moraldo Street [Slope Stabilization and Associated Works],Off Saddle Road Maraval | 2024-08-01 | 2024-03-01 | 180 days | Selective Tendering/Limited Tendering | Unit Price
183 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Upper Ravine Road [Road Rehabilitation],Petit Valley | 2025-01-15 | 2025-03-27 | 15 days | Selective Tendering/Limited Tendering | Unit Price
184 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Uriah Butler Highway [Road Rehabilitation - North and Southbound],Between Arthur Lok Jack Roundabout to Priority Bus Route | 2024-10-01 | 2024-11-16 | 30 days | Selective Tendering/Limited Tendering | Unit Price
185 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Victoria Gardens South [Road Rehabilitation],Off Morne Coco Road | 2025-02-01 | 2025-04-21 | 20 days | Selective Tendering/Limited Tendering | Unit Price
186 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | Western Main Road [Road Rehabilitation],From La Horquette Valley Road to Haig Street | 2025-02-01 | 2025-04-17 | 20 days | Selective Tendering/Limited Tendering | Unit Price
187 | 701/43/003/15D/247 Road Construction/Major Road Rehabilitation | 72152700 | Road Rehabilitation Works | William Street [Road Rehabilitation],Off Old St. Joseph Road | 2025-02-15 | 2025-05-14 | 10 days | Selective Tendering/Limited Tendering | Unit Price

## TECU
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
TECU
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | XXXX | 141000000 | Poly Pro Ticket paper | Procurement of Poly Pro Ticket paper | March, 2025 | May,2025 | 3 months | Sole Source Selection | Supply and Delivery
2 | XXXX | 72101507 | Expansion of office space | Expansion of office space | October, 2024 | April, 2025 | 7 months | Request for Quotation/ Limited bidding | Design and Build
3 | XXXX | 141000000 | Citation Notice Paper | Procurement of Citation Notice Paper | January, 2025 | March,2025 | 3 months | Open Tender | Supply and Delivery
4 | XXXX | 46161500 | Mobile enforcement devices and printers | Procurement of Mobile enforcement devices and printers | November,2024 | February, 2025 | 6 months | Selective Tender | Supply and Delivery
5 | XXXX | 46161500 | Data Center Hosting Fees | Data Center Hosting Fees: UTURN Primary Licensing Data Hosting fees - Oct 01 2025 to Sep 30 2026 | March,2025 | September, 2025 | 6 months | Sole Source Selection | Service Level Agreement
6 | XXXX | 46161500 | Data Center Hosting Fees | Data Center Hosting Fees: Appointment and Queue Management System Oct 01 2025 to Sep 30 2026 | March,2025 | March,2025 | 1 month | Sole Source Selection | Service Level Agreement
7 | XXXX | 46161500 | Data Centre hosting fees | Data Centre hosting fees: UTURN Data Backups at TSTT’s Thompson Exchange Datacentre for the period Oct 01 2025 to Sep 30 2026 | March,2025 | March,2025 | 1 month | Sole Source Selection | Service Level Agreement
8 | XXXX | 46161500 | Data Center Hosting Fees | Data Center Hosting Fees: UTURN Application and database hosting fees - Oct 01 2025 to Sep 30 2026 | March,2025 | March,2025 | 1 month | Sole Source Selection | Service Level Agreement
9 | XXXX | 46161500 | Datacenter hosting resources | Datacenter hosting resources from TSTT to facilitate the Implementation of an Online Driver’s License Renewal System for the MOWT’s Licensing Division for a period Oct 01 2025 to Sep 30 2026 | March,2025 | March,2025 | 1 month | Sole Source Selection | Service Level Agreement
10 | XXXX | 46161500 | Datacenter hosting resources | Datacenter hosting resources from TSTT to facilitate third party access for the MOWT’s Licensing Division for the period Oct 01 2025 to Sep 30 2026 | March,2025 | March,2025 | 1 month | Sole Source Selection | Service Level Agreement
11 | XXXX | 46161500 | UTURN configuration | UTURN configuration and system changes | January, 2025 | Fberuary,2025 | 2 month | Sole Source Selection | Change request with Service Level Agreement
12 | XXXX | 46161500 | Upgrade of HCI Nutanix | Upgrade of HCI Nutanix for the TECU and Licensing Division | March,2025 | March,2025 | 1 month | Sole Source Selection | No Contract

## TMB
MINISTRY OF WORKS AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Traffic Management Branch
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | 03/003/01 | 25100000 | Vehicles | Purchase of 1 Hiab and 4 new vans to the existing fleet | January 2 2025 | March 31 2025 | 3 months | open bidding | Fixed term
2 | 09/003/15G/170 | 46161500 | Provision for Data Collection | Purchase of analytical devices | January 2 2025 | April 30 2025 | 4 months | open bidding | Fixed term
3 | 09/003/15G/171 | 46161500 | Provision of Road Safety Audit on the Roadways of Trinidad | Consultancy services and road safety services | January 2 2025 | March 31 2025 | 3 months | open bidding | Fixed term of 1 year
4 | 09/003/15G/159 | 46161500 | Provision of Backup Power Supply for Traffic Signalised Intersections | Purchase of UPS and generators for traffic signal controls | January 2 2025 | March 31 2025 | 3 months | open bidding | Fixed term
5 | 09/003/15G/172 | 22101624 | Provision of Equipment for Road Marking Purposes | Purchase of pre melter boilers, line spraying machines | January 2 2025 | April 30 2025 | 4 months | open bidding | Fixed term
6 | 09/003/15G/164 | 46161500 | Provision to Upgrade Obsolete Traffic Control Equipment | Initiation of this project began in fiscal 2023/2024. Due to time contstraints, this project will keep its due course and be completed in fiscal 2024/2025 | January 2 2025 | April 30 2025 | 4 months | open bidding | Fixed term

## Traffic Warden
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Traffic Warden Division
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | 5/3/11 | 25100000 | Vehicle | Purchase of two (2) 18 Seater Bus | 2024-12-01 | 2025-05-01 | 180 days | Open Biding | Invoice/Quotation
2 | 5/10/6 | 44000000 | Office Equipment | Purchase of eleven (11) computers, 11 small shedders | 2025-01-01 | 2025-03-01 | 90 days | Selective | Invoice/Quotation
3 | 5/9/1 | 56000000 | Furniture & Furnishings | Purchase of various furniture and furnishings such as Chairs, Desks and Cabinets for Traffic Warden Offices | 2025-01-01 | 2025-03-01 | 90 days | Selective | Invoice/Quotation
4 | 5/10/5 | 44000000 | Other Minor Equipment | Purchase of 50 FPN Devices | 2025-01-01 | 2025-03-01 | 90 days | Selective | Invoice/Quotation
5 | 3/1/4 | 53102700 | Uniforms | Purchase of Uniforms for replacements and new recruits | 2025-02-01 | 2025-04-01 | 60 days | Selective | Invoice/Quotation
6 | 5/11/1 | 80131500 | Rent/Lease | Payment of rent Invoice for Traffic Warden Division for Penal and Point Fortin | 1st Quarter Fiscal | 3rd Quarter Fiscal | N/A | Sole Select | Fixed Term
7 | 5/3/1 | 78181500 | Maintenance of Vehicles | Purchase of all items necessary for the upkeep and maintenance / service of Traffic Warden Vehicles | 2024-12-01 | 2025-01-01 | 60 days | 3 Quote System and Permanent Secretary Approval | Invoice/Quotation
8 | 5/14/1 | 92120000 | Security Services | Payment for Security services for Port of Spain and Point Fortin | 1st Quarter Fiscal | 3rd Quarter Fiscal | N/A | Sole Select | Fixed Term

## URP (hidden)
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2020/2021
URP
No. | Project Number | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
Note on H16: Akido Ford
Note on H17: Akido For

## Transport Licensing
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Transport (Licensing Division)
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
RECURRENT EXPENDITURE
1 | XXXX | 83101800 | Electricity | Supply of electricity to all Licensing Offices (Princes Town, Sangre Grande, Caroni, Point Fortin, Wrightson Road, St James, Arima, San Fernando) | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Sole Select | Not applicable
2 | XXXX | 83101500 | WASA | Pyments to WASA Jerningham Junction Cunupia and PBR Macoya | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Sole Select | Not applicable
3 | XXXX | 53102700 | Uniform | Supply uniform for Motor Vehicle Officers, Motor Vehicles Drivers Messenagers , Estate Constables and Chauffeur | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
4 | XXXX | 83111501 | Telephone | Supply of Telephone Servies, Internetand Communication and Wireless Broadban to all Licensing Offices (Princes Town, Caroni, Point Fortin, Wrightson Road, St James, Arima, San Fernando) | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Sole Select | Not applicable
5 | XXXX | 80131500 | Rental | Rental of office space to Licensing Offices (Princes Townand Point Fortin.) | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Not applicable | Not applicable
6 | XXXX | 44100000 | Equipment | Rental of Linx machine | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
7 | XXXX | 44120000 | Office stationary and supplies | Purchase of cleaning, toiletries, office stationary, household cleaning items etc | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
8 | XXXX | 55101500 | Books and periodicals | Supply of newspaper and transport related journals | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Not applicable | Not applicable
9 | XXXX |  | Material and supplies | Supply of items for core functions within Transport Division (Ink, Toners, Security registration cards, Consumables for cash register, bonding paper, printery items) | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
10 | XXXX | 78181500 | Vehicles | Purchase of Oil, filter, batteries, tyres, wipers, parts for repairs. | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
11 | XXXX | 811120306 | Repairs and Maintenance of equipment | Repairs and service to photocopying machines, printers, cash registers, lift, money counters, weigh bridge, water pumps.* | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
12 | XXXX | 86100000 | Training | Training for customer service, law enforcement | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
13 | XXXX | 72101500 | Repairs and Maintenance of buildings | Repairs and maintenance to buildings, bulbs, elevators, generator, air-condition, fire alarm, windows, doors, rolling gates, Painting | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
14 | XXXX |  | Other Contracted Services | Air refresheners, soap dispensers, urinal flush, landscaping | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
15 | XXXX | 76110000 | Janitorial Services | Provision of services; Cleaning of washrooms, windows, sanitizing, shampoo floors for Caroni Licensing | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
16 | XXXX | 92120000 | Security services | Provision of armed and unarmed sercurity service as well as courrier and expansion of services | 2nd Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
17 | XXXX | 92120000 | Security services | Provision of cash InTransit service for all Transport Divisions | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
18 | XXXX | 44121500 | Postage | Purchase of stamps | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Not applicable | Not applicable
19 | XXXX | 14111800 | Promotion, publicity and printing | Informative advertising- Licensing procedures (in respect to closure of offices) | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
20 | XXXX | 80141902 | Hosting of conferences, seminars and other functions | Hosting of conferences, seminars and other functions | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Not applicable | Not applicable
21 | XXXX | 15000000 | Fuels & Lubricants | Gas, fuels and oils for all Licensing offices. | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Not applicable | Not applicable
22 | XXXX | 25100000 | Minor Equipment | Vehicles: Purchase of new vehicles (SUV). Office Equipment: Printers, Registers, Ultra-Violet lights, Photocopier, Money Counter. Furniture: Dexion, Cabinets, Filing Cabinets, Carpet, Shelving units, Steep cupboards, Blinds, Six seater chairs. | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
23 | XXXX | 44100000 | Other minor equipment | Air condition, trolleys, hand trucks, ladders, fridge, kettles, tri-pod stands, microphone systems. | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Request of quotations | Invoice/ Quotation
Capital Expenditure/DP
1 | XXXX | 43232400 | Upgrade Electronic Vehicle Registration System | Reinvent Web offerings and format - Deploy Online Transfer System and Vehicle Registration | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
2 | XXXX | 43223100 | Data Migration Validation | Digitization of Maxi Taxi Records Digitization of Taxi Badge Records (ongoing) Digitization of Registration documents (ongoing) Digitiazation of HR, GA, TC and TECU Operational Files | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
3 | XXXX | 64101700 | Expand Debit Card Acceptance | Expansion of KIosk Payment and Other Electronic Payment Methods | 1st Quarter Fiscal 2025 | 4th Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
4 | XXXX | 81102500 | Modernization of the Drivers Permit and Taxi Badge Issuance System | GPS plotting of vehicles used for Driving Test (Extension of Pilot) - Purchase of two vehicles Online renewal processing for Drivers Licence | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
5 | XXXX | 85122100 | Proactively monitor and respond to laws and their impact on the Division’s Services and work processes | Proactively monitor and respond to laws and their impact on the division's Services and work processes: implementation of comprehensive program for drivers’ rehabilitation - Expansion | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
6 | XXXX | 78141600 | Modernization of the Vehicle Inspection System | system upgraded (distribution of handheld devices to garages | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
7 | XXXX | 64101700 | Speedier Certified Copy Request and Delivery | Develop Fulfilment Software Implement Online Payment for Certified Copies Deliver Self-Service request | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
8 | XXXX |  | Modernization of the number plate system | Implement Bidding Software ImplemenatSee Cabinet approval for new revenue stream Develop and Deploy Number Plate Requisition Management System | 1st Quarter Fiscal 2025 | 4th Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
9 | XXXX | 81141800 | Facilities Maintenance and Enhancements | Enhance Customer Waiting Areas all sites Acquisition one Wrecker for Enforcement | 1st Quarter Fiscal 2025 | 4th Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
10 | XXXX | 86101800 | Training | Customer Service Leadership Management - People, culture and leadership Chassis Forensics Chassis Impressing | 1st Quarter Fiscal 2025 | 3rd Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract
11 | XXXX | 80111500 | Human Resource (HR) Enhancement | Seek PMCD - Continuation) Seek Cabinet Approval Recruitment/Implementation | 1st Quarter Fiscal 2025 | 4th Quarter Fiscal 2025 | Not applicable | Open Bidding | Fixed Term Contract

## URP
MINISTRY OF WORK AND TRANSPORT
Annual Schedule of Planned Procurement Activities 2024/2025
Unemployment Relief Programme (URP)
No. | Project Number | UNSPCS CODE | Project Name | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Contract Type
Recurrent Expenditure
1 | MOWT/URP 6/1/5 | 81111500 | Renewal of Fortigate Firewall Appliance Licenses | Supply an delivery of Licences for the Fortigate Firewall at the Head Office | 2024-10-01 | 2024-12-01 | 3 months | Single Source | Invoice/Quotation
2 | MOWT/URP 6/1/5 | 81111500 | Additional Modules re:NID SCANNING | Creation of an additional module to scan National Identification Cards to attached to profile and the required equipment for Payroll processing | 2024-10-01 | 2024-12-01 | 3 months | Single Source | Fixed Term Contract
3 | MOWT/URP 6/2/3 | 26111600 | Supply and Delivery of Office Equipment - Power Supply | Supply and Delivery of 1500V Uninterrupted Power Supply Units | 2024-10-01 | 2025-12-01 | 3 months | Request for Quotation | Invoice/Quotation
4 | MOWT/URP 6/1/3 | 44100000 | Service and Repairs of Office Equipment | Servicing and supply and installation replacement parts for photocopies and printers | 2024-10-01 | 2025-12-01 | 3 months | Request for Quotation | Invoice/Quotation
5 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Stationery and Supplies | STATIONERY SUPPLIES (Envelopes, writing pads, Staples, etc. | 2024-10-01 | 2024-12-01 | 3 months | Request for Quotation | Invoice/Quotation
6 | MOWT/URP 6/1/1 | 90101700 | Supply and Delivery of Office Stationery and Supplies - GROCERS | Refreshments for meetings | 2024-10-01 | 2025-01-01 | 4 months | Request for Quotation | Invoice/Quotation
7 | MOWT/URP 6/1/2 | 72101500 | Supply and Delivery of Material - BUILDING MATERIAL (maintenance) | Electrical fixtures and fittings, door locks and handles. | 2024-10-01 | 2025-01-01 | 4 months | Request for Quotation | Invoice/Quotation
8 | MOWT/URP 6/2/2 | 56000000 | Supply, Delivery and Furniture and Furnishings | Supply and Delivery of Chairs, Desk and Filing Cabinets - REGIONS | 2024-10-01 | 2025-01-01 | 4 months | Request for Quotation | Invoice/Quotation
9 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Supplies - PAPER | STATIONERY SUPPLIES - Copy paper and Book Binding Material | 2024-10-01 | 2025-01-01 | 4 months | Request for Quotation | Invoice/Quotation
10 | MOWT/URP 6/1/2 | 46181500 | Supply and Delivery of HEALTH & SAFETY EQUIPMENT AND SUPPLIES | Gloves and cones, | 2024-10-01 | 2025-01-01 | 4 months | Request for Quotation | Invoice/Quotation
11 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Supplies - TONERS | STATIONERY SUPPLIES - Toners for photocopiers and printers | 2024-10-01 | 2025-01-01 | 4 months | Request for Quotation | Invoice/Quotation
12 | MOWT/URP 6/2/1 | 43211500 | Supply and Delivery of Office Equipment - DESKTOPS | Supply and Delivery of 75 Desktops | 2024-10-01 | 2025-01-01 | 4 months | Request for Quotation | Invoice/Quotation
13 | MOWT/URP 6/1/5 | 81111500 | Procurement of Additional Modules re: Daily Paid Payroll (NIS Module) Phase I | Conversion of the Daily Paid Payroll from 2002-2016 | 2024-10-01 | 2025-02-01 | 5 months | Request for Quotation | Invoice/Quotation
14 | MOWT/URP 6/1/5 | 81111500 | SharePoint | Application required as manadate by MOWT for Documentation Management | 2024-10-01 | 2025-05-01 | 8 months | Request for Proposal | Invoice/Quotation
15 | MOWT/URP 6/1/1 | 47131700 | Supply and Delivery of Office Stationery and Supplies - TOILETRIES | TOILETRIES (Toilet Paper, Hand Paper Towel, Hand Liquid Soap, Hand Sanitizer) | 2024-11-01 | 2025-01-01 | 3 months | Request for Quotation | Invoice/Quotation
16 | MOWT/URP 6/1/4 | 76110000 | Supply and Delivery of Janitorial Supplies | JANITORIAL SUPPLIES (All Cleaning Supplies) | 2024-11-01 | 2025-01-01 | 3 months | Request for Quotation | Invoice/Quotation
17 | MOWT/URP 6/1/5 | 81111500 | Supply and Delivery of Office Equipment - Software Application Licenses | Supply and Delivery of MS Office Licenses | 2024-11-01 | 2025-01-01 | 3 months | Sole Source | Invoice/Quotation
18 | MOWT/URP 6/2/3 | 44000000 | Supply and Delivery of Office Equipment - IT Peripherals | Supply and Delivery of mouse, keyboards, hardrives, memory sticks, compress air, CMOS Batteries, networking cables, etc. | 2024-11-01 | 2025-02-01 | 4 months | Request of Quotations | Invoice/Quotation
19 | MOWT/URP 6/2/1 | 44000000 | Supply and Delivery of Office Equipment - Photocopiers | PHOTOCOPIERS for HO | 2024-11-01 | 2025-03-01 | 5 months | Request for Quotation | Invoice/Quotation
20 | MOWT/URP 6/1/5 | 81111500 | Supply and Delivery of Licenses for Draughting Software | Supply and Delivery of AUTOCAD (upgrade) LICENSES FOR ENGINEERING DEPT | 2024-11-01 | 2025-04-01 | 6 months | Sole Source | Fixed Term Contract
21 | MOWT/URP 6/2/1 | 44000000 | Supply and Delivery of Office Equipment - Printers | PRINTERS for Regions | 2024-11-01 | 2025-03-01 | 5 months | Request for Quotation | Invoice/Quotation
22 | MOWT/URP 6/2/1 | 44000000 | Supply and Delivery of Office Equipment - Laptops | Supply and Delivery of 2 Laptops | 2024-12-01 | 2025-03-01 | 4 months | Request for Quotation | Invoice/Quotation
23 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Supplies - BOOK-BINDING MATERIAL | STATIONERY SUPPLIES - Book Binding Material for pay record cards | 2024-12-01 | 2025-03-01 | 4 months | Request for Quotation | Invoice/Quotation
24 | MOWT/URP 6/2/1 | 92121700 | Consultation, Supply and Delivery and Installation of Information Management Security Systems | SECURITY SYSTEM UPGRADE CHAGUANAS AND HEAD OFFICE | 2024-12-01 | 2025-04-01 | 5 months | Request for Proposal | Invoice/Quotation
25 | MOWT/URP 6/5/1 | 72141100 | Procurement of Materials, supplies and transport for approximately 105 projects | CONSTRUCTION PROJECTS | 2024-01-01 | 2024-05-01 | 5 months | Request for Quotation | Invoice/Quotation
26 | MOWT/URP 6/2/3 | 81111500 | Upgrade of Telephony System | Upgrade of IP TELEPHONY SYSTEM | 2024-01-01 | 2024-07-01 | 6 months | Request for Proposal | Invoice/Quotation
27 |  | 76121500 | Disposal of Unserviceable | Disposal of obsolete/defective computer hardware, photocopiers, furniture and filing cabinets, fax machines, printers etc. | 2024-01-01 | 2025-04-01 | 4 months | Request for Quotation | Invoice/Quotation
28 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Stationery and Supplies - BOXES | STATIONERY SUPPLIES Storage Boxes, | 2024-02-01 | 2025-04-01 | 3 months | Request for Quotation | Invoice/Quotation
29 | MOWT/URP 6/1/2 | 78181500 | Supply, Delivery and Buschcutters Accessories | Buschcutter string, two stroke oil, auto cut head etc | 2025-03-01 | 2025-05-01 | 3 months | Request for Quotation | Invoice/Quotation
30 | MOWT/URP 6/2/3 | 44100000 | Supply and Delivery of Powerwashers | (3) Powerwasher for HO, Northern Regions and Southern Regions | 2025-03-01 | 2025-05-01 | 3 months | Request for Quotation | Invoice/Quotation
31 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Supplies - Paper | STATIONERY SUPPLIES - Copy paper and Book Binding Material | 2025-03-01 | 2025-06-01 | 4 months | Request for Quotation | Invoice/Quotation
32 | MOWT/URP 6/2/2 |  | Supply and Delivery of Tent Carvas | Canvas for 2 (20*20) Tents. | 2025-03-01 | 2025-06-01 | 4 months | Request for Quotation
33 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Stationery and supplies - Toners | STATIONERY SUPPLIES - Toners for photocopiers and printers | 2025-03-01 | 2025-06-01 | 4 months | Request for Quotation | Invoice/Quotation
34 | MOWT/URP 6/1/4 | 76110000 | Supply and Delivery of Janitorial Supplies | JANITORIAL SUPPLIES (All Cleaning Supplies) | 2025-04-01 | 2025-06-01 | 3 months | Request for Quotation | Invoice/Quotation
35 | MOWT/URP 6/1/1 | 44120000 | Supply and Delivery of Office Stationery and Supplies | STATIONERY SUPPLIES (Envelopes, writing pads, Staples, etc). | 2024-04-01 | 2024-06-01 | 3 months | Request for Quotation | Invoice/Quotation
36 | MOWT/URP 6/1/2 | 46181500 | Supply and Delivery of HEALTH & SAFETY EQUIPMENT AND SUPPLIES | Traffic signage, safety signs, | 2025-04-01 | 2025-06-01 | 3 months | Request for Quotation | Invoice/Quotation
37 | MOWT/URP 6/1/5 | 81111500 | Contract Renewal for the URP Registration and Payroll Application | Maintenance, Technical support, Additional Modules and SSL Security | 2025-05-01 | 2025-06-01 | 2 month | Sole Source | Invoice/Quotation
38 | MOWT/URP 6/2/2 | 56000000 | Supply, Delivery and Furniture and Furnishings | Supply and Delivery of Chairs, Desks and Filing Cabinets -HEAD OFFICE | 2025-05-01 | 2025-08-01 | 4 months | Request for Quotation | Invoice/Quotation
38 | MOWT/URP 6/1/4 | 47131700 | Supply, Delivery and Maintenance of Automatic Sanitary Bins | Lease Agreement for 69 Automatic Sanitary Bins for HO and Regions | 2024-07-01 | 2024-08-02 | 2 month | Request for Quotation | Invoice/Quotation